## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Church Valley Road Area Wide Treatment ITP | itp |  |  |  |  | Church Valley Road Area Wide Treatment ITP
section | Details
checkpoint | 1 - AP40 Material Quality
label | Inspection Point: Quality Control Activity - Record TNZ/M4 Test Document
label | Acceptance Criteria - Confirm material meets M4 Crushing resistance test
label | Verifying Document - Report
label | Frequency - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PE
label | Inspection: By (Role Key) - Supplier
checkpoint | 2 - Stabi Agent (Cement)
label | Inspection Point: Quality Control Activity - Record NZS 3122
label | Acceptance Criteria - Confirm material as per NZS 3122
label | Verifying Document - Report
label | Frequency - per Batch
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PE
label | Inspection: By (Role Key) - Supplier
checkpoint | 3 - Weather Limitation
label | Inspection Point: Quality Control Activity - Measure temperature
label | Acceptance Criteria - Minimum ambient air temp.
label | ○ Cement 5°C
label | ○ Lime 10°C" & Maximum windspeed of 25km/hr
label | Verifying Document - Site notes
label | Frequency - Daily
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 4 - Spreading rate
label | Inspection Point: Quality Control Activity - Average usage test
label | Acceptance Criteria - Target = 2.4kg/m2,Within ±0.5km/m² of the specified rate
label | Verifying Document - Site notes
label | Frequency - Daily
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 5 - Time limitation
label | Inspection Point: Quality Control Activity - Maximum time period from mixing to primary compaction
label | Acceptance Criteria - 2 hours, TNZB/5
label | Verifying Document - Site notes
label | Frequency - Post stabilisation
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - In-situ Mixing
label | Inspection Point: Quality Control Activity - Cut depth
label | Acceptance Criteria - -5mm +15mm of design depth
label | Verifying Document - Site notes
label | Frequency - At both ends of cut & every 200m
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 7 - In-situ Mixing
label | Inspection Point: Quality Control Activity - Join Overlap
label | Acceptance Criteria - 100mm overlap
label | Verifying Document - Site notes
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 8 - In-situ Mixing
label | Inspection Point: Quality Control Activity - Particle Breakdown
label | Acceptance Criteria - Well mixed material with acceptable particle size distribution
label | Verifying Document - Site notes
label | Frequency - within the first 20m of each run, and where ever material changes
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 9 - Construction (Site Extent)
label | Inspection Point: Quality Control Activity - String line & survey
label | Acceptance Criteria - As per the design
label | Verifying Document - Image
label | Frequency - One for whole site
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - PE
label | Inspection: By (Role Key) - Alliance
checkpoint | 10 - Construction (Compaction & Degree of Saturation)
label | Inspection Point: Quality Control Activity - NDM - Maximum Dry Density & Degree of Saturation (DOS)
label | Acceptance Criteria - Base:Average ≥ 98% MDD,
label | ○ Minimum ≥ 95% MDD")
label | Verifying Document - Report
label | Frequency - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - PE
label | Inspection: By (Role Key) - LAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Construction (Surface, Profile & layer thickness)
label | Inspection Point: Quality Control Activity - Visual inspection, Check string records, straight edge
label | Acceptance Criteria - No ponding if crossfall > 1% , Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | Verifying Document - Site notes
label | Frequency - 1 test per 20m
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - PE
label | Inspection: By (Role Key) - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Pavement finished surface
label | Inspection Point: Quality Control Activity - Ride quality & Mosaic surface
label | Acceptance Criteria - As per LDM
label | Verifying Document - Site notes
label | Frequency - 1 ride test for each lane following Basecourse completion prior to surfacing
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - PE
label | Inspection: By (Role Key) - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Shoulders
label | Inspection Point: Quality Control Activity - Slope, Compaction & Soil support
label | Acceptance Criteria - Consistent slope, Vehicles can drive on shoulders without becoming stuck
label | Verifying Document - Visual Inspection
label | Frequency - All shoulders
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Ready for sealing (Strength)
label | Inspection Point: Quality Control Activity - B Beam
label | Acceptance Criteria - Maximum deflection = 1.3mm
label | Verifying Document - Report
label | Frequency - Staggered every 10m
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - PE
label | Inspection: By (Role Key) - LAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Ready for sealing (Slope)
label | Inspection Point: Quality Control Activity - Levelling
label | Acceptance Criteria - 3m Straight edge deviation 10mm deviation
label | Verifying Document - Image
label | Frequency - Entire site
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 16 - Ready for sealing (Surface to seal texture)
label | Inspection Point: Quality Control Activity - Mosaic surface
label | Acceptance Criteria - NTLDM 4.17.5.2
label | Verifying Document - photos
label | Frequency - Entire site
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 17 - Binder application
label | Inspection Point: Quality Control Activity - Verify m2 treated vs litres used
label | Acceptance Criteria - -0.05
label | Verifying Document - QA operator
label | Frequency - Entire site
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 18 - Traffic services
label | Inspection Point: Quality Control Activity - Marker pegs, sign & marking
label | Acceptance Criteria - Replaced in same position/height unless specified otherwise
label | Verifying Document - Site notes
label | Frequency - Entire site
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance
checkpoint | 19 - Asset As built Data
label | Inspection Point: Quality Control Activity -
label | Acceptance Criteria - All relevant as built information collected
label | Verifying Document - RAMM forms
label | Frequency - During Construction
label | Inspection Type (Visual, other) - Verification
label | Inspection: Key - PS
label | Inspection: By (Role Key) - Alliance