## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | EGM_Ver1.3_08.03.24_ Component 1_Manufacture issued Timber Cut Production_Inspection | [5 empty] | EGM_Ver1.3_08.03.24_ Component 1_Manufacture Issued Timber Cut Production_Inspection
section | Element_Component 1_Manufacture Issued-Timber Cut Production Inspection
checkpoint-no-status | Manufacure Issued Timber Cutting List _Files.
checkpoint | Check and review as per Approved Manufacture Issued Saw Cutting File.
tickbox | Ostendo - Timber Component Line Bar Code, completed.
tickbox | Station - Correct manufacture issued auto-saw cut files for each element code.
checkpoint | Station - Cutting Element lot completed, checked, and as per approved element code plan.
textbox | Operator name:
checkpoint | Improvement or Re-Occuring Issues Records - Document / Attachment / Link / Photo
checkpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
section | Component 1 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Component 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Component 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Component 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Component Pre-Assembly 1_Structural Stud_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Component Pre-Assembly 1_Structural Stud_Inspection
section | Component Pre-Assembly 1_Structural Stud Inspection
checkpoint | Check and review as per Approved Shop Drawing & Template Pilot Hole, and provide picture of the respective Plan.
tickbox | Station - Mark up correct, as per correct template (if required)
checkpoint | Component - Pre-Stud brackets & Rothoblaas install, as per specification and tolerance, (photo sample where required)
checkpoint | Component - Pre-Stud nail stitching install, as per specification and tolerance, (photo sample where required).
checkpoint | Component - Glue laminate Lintels, with correct glue and method, completed, (photo sample where required).
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 1 Inspection__Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Component 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_ Component Pre-Assembly 2_Pilot Holes_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Component Pre-Assembly 2_Pilot Holes_Inspection
section | Component Pre-Assembly 2_Pilot Holes Inspection
checkpoint-no-status | Review
tickbox | Check and review as per Approved Shop Drawing - Template pilot hole, and provide photo of the respective Template.
checkpoint | Station - Mark up correct, as per correct template, and photo required
checkpoint | Station - Pilot Holes, as per specification and tolerance and (photo if required).
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 1 Inspection__Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Component 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_12.03.24_Component Pre-Assembly 3_Pre-Cut Lining Materials_Inspection | [5 empty] | EGM_Ver1.1_12.03.24_Component Pre-Assembly 3_Pre-Cut Lining Materials_Inspection
section | Component Pre-Assembly 3_ Pre-Cut Lining Inspection
checkpoint-no-status | Manufacure Issued Shop Drawing Lining Plan - Ply & Plasterboard GIB Cutting List _Files.
tickbox | Check and review as per Approved Shop Drawing Lining Plan Ply & Plasterboard GIB Cutting Plan,
tickbox | Ostendo - Common Line Bar Code_Ply, GIB Plasterboard Line Bar Code, completed.
tickbox | Station - Mark up correct, as per Approved Shop Drawing Plan
checkpoint | Station - lining sheet 1 (typically Ply), as per Approved Shop Drawing Lining Plan, (pallet lot photo required).
checkpoint | Station - lining sheet 1 (typically Gib Plasterboard), as per Approved Shop Drawing Lining Plan, (pallet lot photo required).
checkpoint | Station - lining sheet 2 (typically Gib Plasterboard), as per Approved Shop Drawing Lining Plan, (pallet lot photo required).
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 1 Inspection__Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Component 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_30.02.24_Element Assembly 1_Wall Structure - EW / MW / CW / TW_Inspection | [5 empty] | EGM_Ver1.1_30.02.24_Element Assembly 1_Wall Structure - EW / MW / CW / TW_Inspection
section | Element Assembly 1_Wall Structural Framing and Preline Inspections
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install all wall framing components and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
textbox | Diagonal #1:
textbox | Diagonal #2:
checkpoint | Check and verify installed components as per Approved Shop Drawing Plan, and photo required.
checkpoint | Check and verify installed structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, has NO screw or nail passing through, as accepted.
checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, has NO screw or nail passing through, as accepted.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 1_Ply Bracing Lining 1st Layer
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Manufacture plan, and photo required.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 1_Fire Lining 1st Layer
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
textbox | Operator name:
checkpoint | Hold point: Overview photo required and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 1_Fire Lining 2nd Layer
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install 2nd Layer and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and verify Wet Area GIB plasterboard is installed as per Approved Shop Drawings and Specification, and photo required.
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Component 1 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Component 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Component 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Component 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_30.02.24_Element Assembly 2_Frame Structure_Floor Cassette / F _Inspection | [5 empty] | EGM_Ver1.1_30.02.24_Element Assembly 2_Frame Structure_Floor Cassette / F _Inspection
section | Element Assembly 2_Structural Floor Cassette Frame and Preline Inspection
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install all floor framing elements and fixings as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
textbox | Diagonal #1:
textbox | Diagonal #2:
checkpoint | Check and verify installed elements as per Approved Shop Drawing Plan
checkpoint | Check and verify installed structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 2_Floor Ply Brace Sheeting
checkpoint | Check and review correct Approved Shop Drawing
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install floor sheeting and fixing as per Approved Shop Drawing Plan and Specification, photo required
textbox | Operator name:
checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
textbox | Diagonal #1:
textbox | Diagonal #2:
checkpoint | Check and verify sheet edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 2 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 2_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 2_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Element Assembly 2_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_18.03.24_Element Assembly 3_Frame Structure_Ceiling Cassette / CE _Inspection | [5 empty] | EGM_Ver1.1_18.03.24_Element Assembly 3_Frame Structure_Ceiling Cassette / CE _Inspection
section | Element Assembly 3_Structural Framing and Pre-line Inspection
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install all ceiling framing elements and fixings as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
textbox | Diagonal #1:
textbox | Diagonal #2:
checkpoint | Installation of Proclima as per manufacturers specification (Level 2 (2f) only)
checkpoint | Check and verify structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint | Hold point: Review and Signoff by Operator before going to next step
section | Element Assembly 3_Fire Lining 1st Layer
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo - Element material Scan, completed.
checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 3_Fire Lining 2nd Layer
checkpoint-no-status | Review
tickbox | Check and review correct Approved Shop Drawing
tickbox | Ostendo - Element material Scan, completed.
checkpoint | Install 2nd Layer and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 3_Ply Sheet Bracing (where applicable Level 2)
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo - Element material Scan, completed.
checkpoint | Install sheeting bracing and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
textbox | Diagonal #1:
textbox | Diagonal #2:
checkpoint | Check and verify sheet edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 3 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 3_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 3_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Element Assembly 3_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_Element Assembly 4_Electrical & Mechanical_Ceiling Cassette / CE _Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Element Assembly 4_Electrical & Mechanical_Ceiling Cassette / CE1_Inspection
section | Element Assembly 4_Electrical & Mechanical Team_Pre-wiring and Pre-ducting_Module A or B
checkpoint | Check and review correct Approved Shop Drawing Electrical and mechanical service plan.
checkpoint | Install and secure electrical cable bundle as per electrical service plan
tickbox | Ostendo - Element material Scan, completed.
textbox | Operator name:
checkpoint | Hold point: overview photo required and Signoff by Lead
signoff | Hold point: Signoff by Electrical & Mechanical Team Leader before going to next step (If No RFI)
section | Element Assembly 4 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 4_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 4_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | ElemElement Assembly 4_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Element Assembly 5_Plumbing & Drainage - Floor Cassette_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Element Assembly 5_Plumbing & Drainage - Floor Cassette_Inspection
section | Element Assembly 5_Pre-plumbing and Drainage Inspection_Module B
checkpoint | Check and review as per Approved Shop Drawing Plumbing and Drainage services Plan, and provide picture of the respective plan.
tickbox | Ostendo - Element material Scan, completed.
checkpoint | Install pipes as per approved plans and manufacturer instructions.
textbox | Operator Name:
checkpoint | Check and verify the pipework installed as per Approved Shop Drawing and photo required.
checkpoint | Check and verify foul water pipe gradients compliant and photo required.
checkpoint | Lagging to drainage pipework, as per specifications/ manufacturer, and photo required.
checkpoint | Timber joist stiffeners where drainage pipework penetration occur, and photos required.
textbox | Operator Name:
checkpoint | Complete air test to AS/NZS3500 and photo required.
checkpoint | Complete water test to AS/NZS3500 and photo required.
textbox | Operator Name:
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 5 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 5_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 5_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Element Assembly 5_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_18.03.24_Element Assembly 6_Wall Frame /IW_Inspection | [5 empty] | EGM_Ver1.1_18.03.24_Element Assembly 6_Wall Frame /IW_Inspection
section | Element Assembly 6_Internal Wall Frame and Preline Inspections_Module A or B
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo - Assembly Elements Scan, completed.
checkpoint | Install all wall framing elements and fixing as per Approved Shop Drawing Plan & Specification
checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan, and photo required
checkpoint | Check and Verify correct GIB plasterboard installed as per Shop Drawing Plan, (and photo required if GIB Fyrline or Aqualine install required, and fixing)
textbox | Internal Wall ID:
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 6 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
tickbox | Review of Ostendo Element materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Element Assembly 5_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.3_22.03.24_Podium Inspection | [5 empty] | EGM_Ver1.3_22.03.24_Podium Inspection
section | Podium_ Module Assembly Team_Structure connection/ Fixing Inspection_Module A or B
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
tickbox | Ostendo Podium Module material scan, completed
tickbox | Locate and position floor cassette on the podium
textbox | Operator Name:
checkpoint | Install all external walls, internal walls, and ceiling cassette as per Approved Shop Drawing. Support/Prop necessary.
textbox | Operator Name:
tickbox | Check and verify installed floor, ceiling, and walls as per Approved Shop Drawing.
checkpoint | Check and verify all structural nail fixings as per Approved Shop Drawing and photos required (show fixing).
checkpoint | Check and verify all structural screw fixings as per Approved Shop Drawing and photos required.
checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted
checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
tickbox | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted.
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
section | Podium_ Module Assembly _Passive Fire Inspection
checkpoint-no-status | Review
tickbox | Check and review correct Approved Shop Drawing
checkpoint | Fire seal/acoustic sealant installed as per approved plan and manufacturer specification, apply to all external wall butting edge to, floor and ceiling. Part of Passive Fire System and photos required.
tickbox | Ostendo Podium Module material scan, completed
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Podium_Module Assembly - Penetrations
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
tickbox | Ostendo Podium Module material scan, completed
checkpoint | Locate and cut out all penetrations as per manufacturer plan
checkpoint | Check and verify all penetrations as per manufacturer plan and photos required.
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Podium_ GIB Stopping Contractor Inspection
checkpoint-no-status | Review
tickbox | Check and review correct Approved Shop Drawing
tickbox | Ostendo Podium Module material scan, completed
checkpoint | Install 1st coat of stopping to ceiling and external facing internal wall, as per approved plans and manufacturer specifications.
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Review and Signoff by Contractor Operator before going to next step (If No RFI)
signoff | Hold point: Signoff by Contractor before going to next step (If No RFI)
section | Podium Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader confirms all Podium works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Podium_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Podium_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Podium_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.2_22.03.24_Station 1_Inspection | [5 empty] | EGM_Ver1.2_22.03.24_Station 1_Inspection
section | Station 1_Electrical & Mechanical - First Fix_DB_Ducting_Penetrations Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing Electrical Services Plan and provide photo
tickbox | Ostendo Station 1 Module material scan, completed
checkpoint | Install Distribution Board as per approved electrical services plan
checkpoint | Install all electrical cabling as per approved electrical services plan
checkpoint | Check and verify installed switchgear values as per plan
checkpoint | All conduit, cables are noted correctly
checkpoint | Drill penetrations through timber frame from external for internal wires
checkpoint | Ensure all screws are torqued to correct specification
checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
checkpoint | External mark-out and cut fireboxes through ply/GIB, and overview photo required
checkpoint | Mechanical Ducting install as per mechanical service plan, and overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
section | Station 1_Plumber & Drainage Team_First Fix Wingbacks Inspection_Module B
checkpoint | Check and review as per project Architectural Drawing and reference respective detail plan.
checkpoint | Ensure all plumbing pipework is secure with applied sealant where required, prior to overview photo's
checkpoint | Install all required wingbacks (cylinder) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (water meter) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (toilet) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (laundry) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (shower) as per manufacturers specification, and overview photo required.
checkpoint | Water pipework, complete water test test to AS/NZS 3500, (by-pass mixer) require photo.
checkpoint | Install shower mixer as per manufacturers specification, and overview photo required.
textbox | Operator Name:
signoff | Hold point: confirm photo taken and signed off by Operator before going to next step (If No RFI)
checkpoint | Hold point: Team Leader
Signoff | Hold point: Signed off by Team Leader before going to next step (If No RFI)
section | Station 1_ Module Assembly _Bulkhead Inspection_Module B
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan.
checkpoint | Install bulkhead partially (leave bottom open for ducting install) as per approved plan and manufacturer specification
tickbox | Ostendo Station 1 Module material scan, completed
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 1 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader confirma all station 1 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Station 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 2_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 2_Inspection
section | Station 2_Electrical & Mechanical Team - First Fix_Firebox and Penetrations Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing Electrical Services Plan and provide photo
tickbox | Ostendo Station 2 Module material scan, completed
checkpoint | Locate and cut out all firebox penetrations as per manufacturer plan
checkpoint | Drill penetrations for external wiring down frame as per manufacturer plan
checkpoint | Install and secure mechanical ducting as per mechanical service plan
checkpoint | On completion of first fix, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 2_Electrical & Mechanical Team - First Fix_Firebox and Passive Fire Inspection_Module A or B
checkpoint | Fix firebox with pads and fire seal as per Approved Shop Drawing, and photo required.
tickbox | Ostendo Station 2 Module material scan, completed
checkpoint | Check and verify all penetrations and passive fire as per manufacturer plan
checkpoint | On completion of firebox with pads, and passive fire, an overview photo is required
textbox | Operator Name:
checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 2_Module Assembly Team_Acoustic Floor Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing and specifications, and provide picture of the respective plan.
tickbox | Ostendo Station 2 Module material scan, completed
checkpoint | Install acoustic floor as per approved plans and manufacturer specifications.
checkpoint | Install acoustic flooring and fixing as per approved plans and manufacturer specifications.
checkpoint | Install Batten and cradle as per manufacturer specification, and overview photo required
checkpoint | Install underfloor acoustic insulation as per manufacturer specification, and overview photo required
checkpoint | Install Fire fire sealant to perimeter and photo required.
checkpoint | Install wet area flooring and fixing as per approved plans and manufacturer specifications.
checkpoint | On completion of Acoustic Floor, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 2_Module Assembly Team_Insulation_Module A or B
checkpoint | Check and review as per Approved Shop Drawing and specifications, and provide picture of the respective plan.
tickbox | Ostendo Station 2 Module material scan, completed
checkpoint | Install all insulation material as per approved plans and manufacturer specifications.
checkpoint | Attach Insulation Certificate, and overview photo required (wall and ceiling for each R-value insulation material used).
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 2_ Air-Conditioner Contractor _Pre-wiring/pipework Inspection_Module A
checkpoint | Check and review as per Approved Shop Drawing and specifications, and provide picture of the respective plan.
tickbox | Ostendo Station 2 Module material scan, completed
checkpoint | Install pre-wiring and pipework from external wall to internal wall, as per approved plans and manufacturer specifications.
checkpoint | On completion of works, an overview photo is required
textbox | Operator Name:
signoff | Hold point: Review and Signoff by Contractor Operator before going to next step (If No RFI)
checkpoint | Hold point: Contractor
signoff | Hold point: Signoff by Contractor before going to next step (If No RFI)
section | Station 2 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader confirms all station 2 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Station 2_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 2_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 2_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 3_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 3_Inspection
section | Station 3_Electrical & Mechanical - First Fix_DB Wiring and SS Shower-tray Earthing Inspection_Module B
checkpoint | Check and review as per Electrical and Mechanical Services Approved Plan.
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Distribution Board wiring placement as per approved electrical services plan
checkpoint | Check and verify installed switchgear values as per plan
checkpoint | All cables are noted correctly
checkpoint | Ensure all screws are torqued to correct specification
checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
checkpoint | Stainless Steel shower tray earthing connection as per electrical/mechanical service approved plan,
checkpoint | Install ventilation fan in bulkhead area, as per approved electrical/ mechanical plan.
checkpoint | On completion of Distribution Board, SS shower tray earthing, and ventilation fan, an overview photo is required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 3_ Smoke Alarm Contractor _Pre-wiring Inspection_Module A or B
checkpoint | Check and review as per approved manufacturer plan.
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Install pre-wiring and pipework from external wall to internal wall, as per approved plans and manufacturer specifications.
checkpoint | On completion of works, overview photo is required.
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 3_Fitout Team_Wall (RAB) Inspection_Module A or B
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan.
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Install balance RAB and install fixings as per manufacturer specification, an overview fixing photo is required
checkpoint | Install all RAB joint tapes/Sealants to RAB joints, windows, doors, penetrations. Etc, as required.
checkpoint | On completion of RAB joint tape and penetration tapes, an overview photo is required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 3_Penetration_Modules A or B
checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint | Install all penetrations, as required.
textbox | Operator Name:
checkpoint | Hold point: Review and signed off by Team leader before going to next step
section | Station 3_Fitout Team_Opening Flashing Tapes & Sill Support Inspection_Module A or B
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan.
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Install opening flashing tapes to Sill, Head, Jamb, window/door etc., as required.
checkpoint | On completion of opening flashing tapes, an overview photo is required
textbox | Operator Name:
checkpoint | Install with SS screw fixing all sill supports window/door etc., as required.
checkpoint | On completion of sill support fixing, an overview photo is required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 3_Fitout Team_Fire Door and Fire Seal/Airseal Inspection_Module B
checkpoint | Check and review as per approved plans and specifications
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Install Fire door as per door schedule and PF backing rod, fire seal/airseal
checkpoint | On completion of stage of installation of PF baking rod and fire seal/airseal, an overview photo is required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 3_ Module Assembly _Passive Fire Inspection_Module A or B
checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report.
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Install wall and ceiling fire sealant, fire dampers, collars and sealants as per approved plans and manufacturer specifications.
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 3_ Fitout Team_Stainless Steel Shower-tray Inspection_Module B
checkpoint | Install SS shower-tray as per approved plan and manufacturer specification
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | On completion of works, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 3_ Fitout Team_Bulkhead bottom_Module B
checkpoint | Install balance of bulkhead bottom battens as per approved plan and manufacturer specification
tickbox | Ostendo Station 3 Module material scan, completed
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 3_ Fitout Team_Internal GIB Plasterboard Inspection_Module A or B
checkpoint-no-status | Review
tickbox | Install internal GIB plasterboard as per approved plan and manufacturer specification
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Check and Verify correct GIB plasterboard installed as per Shop Drawing Plan, (and photo required if GIB Fyrline or Aqualine install required, and fixing)
textbox | Type of GIB plasterboard:
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 3_ External Membrane Waterproofing Contractor Inspection_Module A
checkpoint | Check and review as per approved manufacturer plan.
tickbox | Ostendo Station 3 Module material scan, completed
checkpoint | Install waterproof membrane to sliding door sill area including upstand as per approved plans and manufacturer specifications.
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold Point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 3 Inspection_Signoff
checkpoint-no-status | Review
tickbox | Review of Ostendo Component materials where scanned (Confirmed).
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader confirms all Station 3 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Station 3_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 3_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 3_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 4_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 4_Inspection
section | Station 4_Electrical & Mechanical Team_First Fix Electrical & Mechanical_Module B
checkpoint | Check and review as per Electrical and Mechanical Services Plan and provide photo
tickbox | Ostendo Station 4 Module material scan, completed
checkpoint | Install earth and neutral wiring as per electrical plan.
checkpoint | Install ducting fitout to bulkhead area, as per mechanical plan.
checkpoint | On completion of works, an overview photo is required
textbox | Operator Name:
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint | Hold Point: Team Leader
signoff | Hold point: Review and signoff by Team Leader before going to next step (If No RFI)
section | Station 4_Windows and Ranch Slider Doors_Module A
checkpoint | Check and review as per approved manufacturer plans and specifications, photo required
tickbox | Ostendo Station 4 Module material scan, completed
checkpoint | Install all windows as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | Install all window backing rod & air-seal as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | Install all Ranch-slider as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | On completion at each stage of installation, (PF backing rod, sealant air-seal), overview photo required for Window and Ranch Slider
textbox | Operator Name:
signoff | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint | Hold Point: Team Leader
signoff | Hold point: photo required and Signoff by Team Leader before going to next step (If No RFI)
section | Station 4_Fitout Team_Internal Riser Insulation & GIB Lining_Module B
checkpoint | Check and review as per approved manufacturer plans and specifications
tickbox | Ostendo Station 4 Module material scan, completed
checkpoint | Install all internal riser insulation, as per manufacturer issued plan
checkpoint | Install all internal riser Gib lining where required, as per manufacturer issued plan
checkpoint | Install Riser access panel where required, as per manufacturer issued plan
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 4_Fitout Team_Internal Doors / Wardrobe Doors & Architraves/ Skirting_Module A or B
checkpoint | Check and review as per approved manufacturer plans and specifications
tickbox | Ostendo Station 4 Module material scan, completed
checkpoint | Install all internal doors and wardrobe doors, as per manufacturer plan
checkpoint | Install all architraves and skirting where required, as per manufacturer plan
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 4 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Review of Station 4 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader confirms all Station 4 works completed.
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 4_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 4_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 4_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 5_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 5_Inspection
section | Station 5_First Fix Plumbing and Drainage_Module B
checkpoint | Installed pipework as per approved plans and manufacturer instructions.
textbox | Operator Name:
checkpoint | Installation of floor waste flange (if required) require photo.
checkpoint | Visual inspection, after installation of inner wall water pipework, pressurised pipework complete. (no leaks detected)
checkpoint | Visual inspection, after plasterboard (GIB) installation, complete. (water pipework, no leaks detected)
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint | Hold Point: Team Leader
signoff | Hold point: Review ond Signoff by Plumbing Team Leader before going to next step (If No RFI)
section | Station 5_Gib Stopping 1st Coat - Internal Walls_Module A or B
checkpoint-no-status | Review
tickbox | Install internal Gib stopping as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed GIB stopping as per approved plans
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 5_Gib Stopping 2nd Coat - Wall and Ceiling_Module A or B
checkpoint-no-status | Review
tickbox | Install internal Gib stopping as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed GIB stopping as per specifications & approved plans
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 5_Putty Holes - Architraves & Skirting_Module A or B
checkpoint-no-status | Review
tickbox | Install internal putty holes to architraves & skirting as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed putty to holes of architraves and skirting as per specifications & approved plans
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 5 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Contractor Name:
tickbox | Review of Station 5 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 5 works completed.
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint | Hold point: Team Leader
checkpoint | Hold point: Team Leader confirms all Station 5 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 5_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 5_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 5_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 6_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 6_Inspection
section | Station 6_Gib Stopping 3rd Coat - Wall and Ceiling_Module A or B
checkpoint-no-status | Review
tickbox | Install internal Gib stopping as per approved plans
checkpoint | Check and verify the installed GIB stopping as per approved plans
textbox | Operator name:
checkpoint | on completion of work, overview photo required
signoff | Hold point: Review and Signoff by Operator before going to next step
section | Station 6_Putty Sanding - Architraves & Skirting_Module A or B
checkpoint-no-status | Review
tickbox | Install internal putty sanding to architraves & skirting as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed putty to holes of architraves and skirting as per specifications & approved plans
signoff | Hold point: photo required and Signoff by Operator before going to next step
section | Station 6 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
tickbox | Review of Station 6 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 6 works completed.
signoff | Hold point: Review and Signoff by Contractor before going to next step (If no RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If no RFI)
section | Station 6_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 6_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 6_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 7_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 7_Inspection
section | Station 7_Gib Stopping Sanding - Wall and Ceiling_Module A or B
checkpoint-no-status | Review
tickbox | Install internal Gib stopping as per approved plans
checkpoint | Check and verify the installed GIB stopping sanding as per specification & approved plans
checkpoint | On completion of work, overview photo required
textbox | Operator name:
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 7_Sealer Coat_Wall, Ceiling, Architraves & Skirting_Module A or B
checkpoint-no-status | Review
tickbox | Check and review as per approved plans and specifications,
checkpoint | Complete the sealer coat internal painting as per approved plans and manufacturer specifications
textbox | Operator name:
checkpoint | Check the sealer paint coat and apply dent stopping and dent sanding completed (overview photo required)
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 7 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
tickbox | Review of Station 7 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 7 works completed.
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 7_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 7_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 7_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 8_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 8_Inspection
section | Station 8_1st and 2nd Coat Painting Plasterboard - Wall & Ceiling_Module A or B
checkpoint-no-status | Review
tickbox | Check and review as per approved plans and specifications,
checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacturer specifications
textbox | Operator name:
checkpoint | Check the painting
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 8_1st and 2nd Coat Painting - Architraves, Skirting - Doors & Window Jambs_Module A or B
checkpoint-no-status | Review
tickbox | Check and review as per approved plans and specifications,
checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacturer specifications
textbox | Operator name:
checkpoint | Check the painting, completed. (no touch-up required)
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 8 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
tickbox | Review of Station 8 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 8 works completed.
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 8_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 8_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 8_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_22.03.24_ Station 9_Inspection | [5 empty] | EGM_Ver1.1_22.03.24_Station 9_Inspection
section | Station 9_3rd Coat Painting Plasterboard - Wall & Bathroom Ceiling_Module A or B
checkpoint-no-status | Review
tickbox | Check and review as per approved plans and specifications, and provide picture of the respective plan.
checkpoint | Complete the 3rd coat internal painting as per approved plans and manufacturer specifications
textbox | Operator name:
checkpoint | Check the painting, completed. (no touch-up required)
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint | Hold point: Contractor
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 9 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
tickbox | Review of Station 9 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 8 works completed.
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Station 9_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 9_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 9_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_19.03.24_Station 10_Inspection | [5 empty] | EGM_Ver1.1_19.03.24_Station 10_Inspection
section | Station 10_Floor Covering - Vinyl Inspection_Module B
checkpoint-no-status | Contractor - Floor Covering
checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan.
checkpoint | Install all floor coverings as per specifications and approved shop drawings (overview photo required)
checkpoint | Install floor protection, completed (as required)
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 10_Fitout Assembly _Shower Area Hydrapanel & Fitout Inspection_Module B
checkpoint | Hydrapanel installed as per specification and approved shop drawings.
tickbox | Ostendo Module material scan, completed
checkpoint | Shower curtain, toilet roll holders, towel rail, installed as per specifications and approved shop drawings.
checkpoint | Vanity, vanity mirror cabinet, installed as per specification and approved shop drawings
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 10_Windows and Ranch Slider Door Flashings_Module A or B
checkpoint | Check and review as per approved manufacturer issued plans and specifications, and Window/Ranchslider Supplier & Engineer Approved Shop Drawings
tickbox | Ostendo Station 10 Module material scan, completed
checkpoint | Install all window head flashings with stop-end & sealant or EPDM tape as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | Install all window jamb flashings as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | Install all Ranch-slider head flashing with stop-end & sealant or EPDM tape as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | Install all Ranch-slider jamb flashing with sealant (to window flange & Head to Jamb junction) as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint | On completion at each stage of installation, (head & jamb flashing), overview photo required for Window and Ranch Slider
textbox | Operator Name:
signoff | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint | Hold Point: Team Leader
signoff | Hold point: photo required and Signoff by Team Leader before going to next step (If No RFI)
section | Station 10_Fitout Assembly - Fitout Wardrobes Inspection_Module A
checkpoint-no-status | Review
tickbox | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan.
tickbox | Ostendo Module material scan, completed
checkpoint | Wardrobe rail and shelfs as per specification and approved shop drawings
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 10 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
tickbox | Review of Station 10 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 10 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 10_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 10_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 10_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_19.03.24_Station 11_Inspection | [5 empty] | EGM_Ver1.1_19.03.24_Station 11_Inspection
section | Station 11_Kitchen Cabinets Inspection_Module B
checkpoint-no-status | Contractor - Kitchen Cabinets
checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan.
checkpoint | Install all kitchen cabinets as per specifications and approved shop drawings
checkpoint | Install benchtop, completed (sealant as required)
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 11_Electrical & Mechanical Team_Second Fix Electrical & Mechanical Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing Electrical and Mechanical Services Plan and provide picture of the respective plan.
tickbox | Ostendo Module material scan, completed
checkpoint | Install all power points and light switches.
checkpoint | Install all lights.
checkpoint | Install heat pumps. (Onsite install)
checkpoint | Install heat towel rail. (If required)
checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint | Install HW cylinder
checkpoint | Install Kitchen oven/hob.
checkpoint | Install wall heaters.
checkpoint | Check, by contractor smoke alarm, installed - completed
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold Point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
section | Station 11_Final Fix Plumbing and Drainage Inspection_Module B
checkpoint | Check and review as per Approved Shop Drawing Plumbing and Drainage services Plan, and provide picture of the respective plan.
tickbox | Ostendo Module material scan, completed
checkpoint | Install HW cylinder as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install toilet as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install kitchen sink plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install shower fittings as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install vanity plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install floor waste as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install supertub & plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install shower tray waste plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 11 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Review of Station 11 Module materials were scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 11 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 11_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 11_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 11_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_19.03.24_ Station 12_Inspection | [5 empty] | EGM_Ver1.1_19.03.24_Station 12_Inspection
section | Station 12_Final Testing Plumbing and Drainage Inspection - Module B
checkpoint | Check and review as per approved shop drawing plumbing and drainage services Plan, and provide picture of the respective plan.
checkpoint | SW pipework flood test, provide photo
checkpoint | Hot and Cold Water test for 30mins at 1550KPa as per AS/NZS 3500, provide photo
checkpoint | Visual check all pipework, no leaking detected, during testing
checkpoint | Visual check all fixtures & fitting, no leaking detected, during testing
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 12_Electrical Testing (Inform electrician to carry out the required electrical testing of all installation)_Module A & B
checkpoint | Electrical Testing-Earth Resistance and Continuity, Insulation Resistance, Polarity and Phase, Correct Circuit connection, etc.
checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint | RCD Test, provide photo
checkpoint | Hold point: Review and Signoff by Electrical Team Leader before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 12_Hardware_Module A or B
checkpoint-no-status | Review
tickbox | Check and review as per approved Shop Drawing Plans and specifications
checkpoint | Complete all hardware as per approved Shop Drawing plans and specifications, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 12 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
tickbox | Review of Station 12 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 12 works completed.
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 12_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 12_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 12_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_12.03.24_Station 13_Packing Onsite Items-Packaging & External Wrap Cover Inspection | [5 empty] | EGM_Ver1.1_12.03.24_Station 13_Packing Onsite Items-Packaging & External Wrap Cover Inspection
section | Station 13_Fitout Team_Items to be included in Module for onsite_Module A or B
checkpoint | Check and review as per Approved Shop Drawings Plans, specifications and as per list
tickbox | Ostendo Station 13 Module material scan, completed
checkpoint | Check all items as per list included in Module
tickbox | Check all items are secured in place
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
section | Station 13_Internal Fixtures and Fittings Packaging_Module A or B
checkpoint | Toilet: Cistern fixed by using blue 14 day tape
checkpoint | Shower: Shower head taped in place to shower rail
checkpoint | Cabinets and Doors: All cabinet doors, mirror cabinet doors and drawers fixed using blue 14 day tape.
checkpoint | Bathroom: Bathroom Shower curtain is supplied and protected
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 13_Packaging_External Protective Wrap Cover_Module A or B
checkpoint | Use protective film to cover a module completely
tickbox | Ostendo Station 13 Module material scan, completed
checkpoint | Use heat Gun to seal the protective film.
textbox | Operator Name:
checkpoint | Make sure there are no gaps in the film
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 13 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
tickbox | Review of Station 13 Module materials where scanned
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Contractor confirms all Station 12 works completed.
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 13_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 13_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 13_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_12.03.24_Yard_Lifting, Loading & Shipment Inspection | [5 empty] | EGM_Ver1.1_12.03.24_Yard_Lifting, Loading & Shipment Inspection
section | Yard_Lifting, Loading & Shipment_Module A or B
checkpoint | 18-24T Forkhoist will be used to load a module onto a Specialised Transport Vehicle. Perform Forklift Startup Check, Completed.
checkpoint | Check if the Specialised Transport Company meet the approved transport criteria. Correct Module as per schedule.
checkpoint | The Specialist Transport Operator/ Driver will tie the module to the Transport Vehicle, using strops or with the approved equipment.
checkpoint | The Specialist Transport Operator/ Driver will make sure the module is correctly sitting on the Transport vehicles.
checkpoint | Make sure the Module wrap is secured and weathertight.
checkpoint | On completion of Module Loading, overview photo required.
textbox | Operator Name:
signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Yard_Lifting, Loading & Shipmen_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Yard_Lifting, Loading & Shipmen_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Yard_Lifting, Loading & Shipmen_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.0_08.03.24_Floor Covering - Inspection_Module A or B | [5 empty] | EGM_Ver1.0_08.03.24_Floor Covering - Inspection_Module A or B
section | Contractor - Floor Covering
checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan.
checkpoint | Install all floor coverings as per specifications and approved shop drawings (overview photo required)
checkpoint | Install floor protection, completed (as required)
textbox | Operator Name:
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 10_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 10_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 10_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_08.03.24_Kitchen Cabinets Inspection_Module B | [5 empty] | EGM_Ver1.0_08.03.24_Kitchen Cabinets Inspection_Module B
section | Contractor - Kitchen Cabinets
checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan.
checkpoint | Install all kitchen cabinets as per specifications and approved shop drawings
checkpoint | Install benchtop, completed (sealant as required)
checkpoint | On completion of work, overview photo required
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Kitchen Cabinets Inspection_Module B_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Kitchen Cabinets Inspection_Module B_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Kitchen Cabinets Inspection_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.1_19.03.24_ Notified QA NCR_RFI Process | [5 empty] | EGM_Ver1.0_19.03.24_Notified QA NCR_RFI Process
section | Notified NCR_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Notified NCR_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Notified NCR_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.1_19.03.24_Document/ Works_Records | [5 empty] | EGM_Ver1.1_19.03.24_Document/ Works_Records
section | Document / Attachment / Link / Photo
checkpoint | Records
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Document/ Works Record_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Correct Record uploaded
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
signoff | Hold point: Review and Signoff by Team Leader/Contractor before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Document/ Works Record_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Document/ Works Record_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Document/ Works Record_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
signoff | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.1_30.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE | [5 empty] | EGM_Ver1.1_30.10.23_ITEMS INCLUDED IN MODULE FOR ONSITE
section | ITEMS INCLUDED IN MODULE FOR ONSITE_Module A_B
checkpoint | GIB 16MM FYRELINE X SHEET SIZE
checkpoint | GIB 13MM FYRELINE x SHEET SIZE
checkpoint | GIB AQUALINE x SHEET SIZE (note thickness)
checkpoint | GIB 10MM STANDARD X SHEET SIZE
checkpoint | GIB WEATHERLINE X 1 SHEET SIZE
checkpoint | STRAND-BOARD FLOORING X SHEET SIZE
checkpoint | INTERNAL PRE-HUNG DOOR RH or LH
checkpoint | INTERNAL PRE-HUNG DOOR STOPS
checkpoint | ARCHITRAVES X LENGTH
checkpoint | SKIRTING X LENGTH
checkpoint | DISHWASHER X UNIT
checkpoint | SHOWER CURTAIN
checkpoint | CEILING INSULATION X R-VALUE
checkpoint | ITEMS SECURED IN MODULE
checkpoint | VANITY & KITCHEN DOORS, SHOWER HEAD TAPED TO AVOID OPENING/DAMAGE
checkpoint | MODULE CLEANING COMPLETED
textbox | ADDITIONAL ITEMS:
textbox | ADDITIONAL ITEMS:
textbox | ADDITIONAL ITEMS:
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
checklist | EGM_Ver1.0_08.03.24_ QA CONTINUAL IMPROVEMENT RECORD | [5 empty] | EGM_Ver1.0_08.03.24_ QA CONTINUAL IMPROVEMENT RECORD
section | QA Continual Improvement_Record
checkpoint-no-status | Record
textbox | Operator Name:
textbox | Safety, Quality & Compliance, Production, Material/ Product, Supplier
textbox | Review, Recommendation, Investigation, Identified, Improvement
textbox | Corrective Action, Preventative Action, Record Action
checkpoint-no-status | 5 Why Note:
Checkpoint | Review Note:
Checkpoint | Final Outcome Note:
checkpoint | Evaluated RFI Minor - Major - Critical Issue - Photo required:
checkpoint | Hold point: Team Leader
signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)