## Guardrail & Wire Rope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F- Tangoio Falls Steep Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Guardrail Installation |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Teams message from Dave Hooker 21/12/23 | Andrew Harrall / behalf Trudy- 08/01/24 | Quality Eng.
Lot No: B1004F- Tangoio Falls Steep Underslip |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 608 RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | OFI or NTD/NTC | CPS Engineer | CPS Engineer
2 | Survey Setout | H | Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing. | Site Engineer | CPS Engineer
3 | Material Compliance | H | All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4 | Prior to commencement | Visual inspection/ Document review | TNZ M/23:2009 | Manufacturing certificates and delivery dockets | Site Engineer | CPS Engineer
4 | Guardrail Installation | W | Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 | Site Engineer
5 | Guardrail Installation | W | Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 | Site Engineer
6 | Guardrail Installation | W | Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 | Site Engineer
7 | RSHDS Inspection | H | Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings | At completion of Safety Barrier Installation | Visual Inspection |  | RSHDS Audit Form | Site Engineer | CPS Engineer
Post-Construction
8 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Quality
9 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer
10 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer