## Reinforced Slope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F - Tangoio Fall Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Reinforced Slope (Rock Bolts, Soil Nails) |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Dave Hooker / Gre Bailey via Teamsmessage | Andrew Harrall/ Belhalf Trudy Guy | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEB-SH2SOUTHHAWKESBAY/ETnWr4WChDhGjRR1PaDE0vgBodebGIpsi1M9S9fvWr5ZOg?e=U8xS4r |  | Compliance with Work Instructions and Specifications
Detailed Location: Tangoio Falls Steep Underslip- SH 02- RS 608 -RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Preliminary & Setout
1 | Vegetation Clearance | H | Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed | Prior to commencement | Visual Inspection | In accordance with TNZ F/1 | Photos | Site Engineer
2 | Excavation Clearance | H | Any excavation and filling required is to be carried out. Excavation should be kept to a minimum | Prior to commencement | Visual Inspection | In accordance with TNZ F/1. | Photos | Site Engineer
3 | Survey Setout | H | Arrange for a set out survey to be carried out & check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer | CPS Engineer
Material Compliance
4 | Material Compliance - Rock Bolt & Soil Nail | H | Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings | Prior to commencement | Document Review | Grade 500E soil nail Class II corrosion protection Lengths and diameters shown on drawings are the minimum required | Delivery Docket | Site Engineer
5 | Material Compliance - reinforcing steel | W | Reinforcing steel manufactureers test reports and certificates | Prior to undertaking works | Submission | Including despatch records | Email | Site Engineer
6 | Concrete quality plan | H | Concrete quality plan to be produced and approved before work starts | Prior to commencement | Submission | Including: - Name, qualificationand expoerience of concrete works inspector - Form and content of concrete placement card | Email | Site Engineer | CPS Engineer
7 | Concrete plant compliance cert | W | Details of concrete supply plant, copy od certificate of audit for plant | Three weeks prior to pouring concrete | Submission | Including: - Plant test Results - ASR Compliance Records | Email | Site Engineer
8 | Concrete mix designs | H | Submit all concrete mix designs, trial mixes and compliance records | Three weeks prior to pouring concrete | Submission | Mix Design to be approved by CPS Engineer before commencing construction | Email | Site Engineer | CPS Engineer
9 | Grout Mix | H | Test to be carried out on Grout mix before it is ordered for construction | Prior to commencement | Testing | Mix design to be approved by CPS Engineer before commencing construction | Test results to CONQA Procore | Site Engineer | CPS Engineer
10 | Grout Checks | W | Grout checked if its free from lumps & segregation | Prior to commencement | Visual Inspection |  |  | Site Engineer
11 | Request for use of alternative Drilling Fluid | H | Request for use of alternative Drilling Fluid (Section 7.5.2) | Prior to Commencement | Submission | If required |  | Site Engineer | CPS Engineer
12 | Soil Nail construction methodology | H | Soil Nail construction methodology plan must be submitted two weeks prior to works starting | Prior to commencement | Submission | Include sprayed concrete, grouting and tremie concrete in methodology |  | Site Engineer | CPS Engineer
Sacfrifical Testing has been Completed and the Results are in the Design Report
Construction
13 | Working Bench | H | The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times. | Prior to commencement | Measure |  | Photos | Site Engineer | CPS Engineer
14 | Test Nail Locations | H | Location of all Test Nails to be agree on site (Section 7.8.1) | Prior to Trial | Inspection |  | Photos, Site Diary | Site Engineer | CPS Engineer
15 | Insert micropile bar | H | Insert micropile bar (ReidBar RB32) to full required length | During Construction | Measure | Embedded length of micropile 3.0m into ground | Photos | Site Engineer | CPS Engineer
16 | Drill Holes | H | Drill hole | During construction | Submission | Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any. Submit all installation records for each soil nail and pile. |  | Site Engineer | CPS Engineer
17 | Flush holes | H | Flush all soil nail holes with water and air after drilling to remove smear and drilling debris | During Construction | Visual Inspection |  |  | Site Engineer | CPS Engineer
18 | Insert soil nails | H | Insert soil nails as specified | During Construction | Visual Inspection | Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage | Subcontractor QA Records | Site Engineer | CPS Engineer
19 | Installation Records | W | A record is to be maintained showing the type and installation date for each soil nail | During Construction | Submission | Installation records shall include: - Length of bar - Depth of drill hole - Inclination/Verticality achieved - Level of grout placed - Batch numbers associated with grout placed in each hole | Subcontractor QA Records | Site Engineer
20 | Install Grout | W | Install Grout on the same day of drilling unless otherwise approved by designer | During Construction | Visual Inspection | Including : - Concrete despatch records - Compression test results Must notify CPS for any failed result and cease works until resolved | Subcontractor QA Records | Site Engineer
21 | Grout Sample Testing | H | Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch | During Construction | Testing | Must reach specified minimum 7-day and 28-day compressive strengths | CONQA | Site Engineer | CPS Engineer
22 | Monitoring of grout loss | W | Loss of grout shall be monitored and recorded for each hole during and immediately after grouting | During Construction | Submission |  | Subcontractor QA Records | Site Engineer
23 | Install Bolts/Nails washers & nuts | H | Install Bolts/Nails washers & nuts | During Construction | Measure | All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed. | Delivery Dockets | Site Engineer | CPS Engineer
24 | Testing of Soil Nails | H | All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified | After Construction | Submission | Certifications of all testing equipment within the last 3 months | Certifications | Site Engineer | CPS Engineer
25 | Testing of Soil Nails | W | Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved | After Construction | Measure |  |  | Site Engineer
26 | Testing of Soil Nails | H | Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2) | After Construction | Testing | Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails | Test results to CONQA Procore | Site Engineer | CPS Engineer
27 | Soil Nail Final Inspection | H | Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails | After Construction | Document Review | CPS Engineer to give approval via a NTC | Email | Site Engineer | CPS Engineer
28 | Shotcreting- prepare surface | H | Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened | During Construction | Visual Inspection |  | Photos | Site Engineer | CPS Engineer
29 | Shotcreting- apply vertical | W | Apply shotcrete - 200mm Nominal thick (Vertical) | During construction | Visual Inspection |  | Photos | Site Engineer
30 | Shotcreting- apply horizointal | W | Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal) | During Construction | Visual Inspection |  | Photos | Site Engineer
31 | Shotcreting- compression testing | H | Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores | After Construction | Visual Inspection |  | Test results to CONQA Procore | Site Engineer | CPS Engineer
32 | Shotcreting- surface inspection | H | Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m | After Construction | Visual Inspection | Surface Inspected by CPS Engineer & Approval given to carry on with works | Email | Site Engineer | CPS Engineer
Post-Construction
33 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Quality
34 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer
35 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer