## Asphalt - Surfacing
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F - Tongoio Falls Steep Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Stormwater Drainage |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Teams message from Dave Hooker 21-Dec-23 | Andrew Harrall / behalf Trudy Guy 08-Jan-24 | Quality Eng.
Lot No: B1004F - Tongoio Falls Steep Underslip |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 608 RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Pre-Construction
1 | Drawings and Specification | M | Check drawings and spec are the latest version. | Prior to commencement | Review |  |  | Site Engineer
2 | Survey Setout | W | Set out as per design | Prior to commencement | Survey | Check against plans for any discrepancies | Survey receipt | Site Engineer
3 | Material Approval | M | Materials as per design | Prior to commencement | Review | Only require approval if proposing an alternative material than that specificed in the drawings |  | Site Engineer
4 | Location of underground services | H | Ensure underground services are positively identified and asbuilt. If the service conflicts with the design confirm resolution with CPS | Prior to commencement | Review |  |  | Site Engineer | CPS
5 | Drainlayer Qualifications | W | Drainlayer to be appropriately qualified and skilled to undertake work | Prior to commencement | Review | Drainlayer Certs |  | Site Engineer
Construction
6 | Trench and excavate for pipeline to design subgrade | W | Check subgrade with visual inspection and | During Construction | Site Measurements | Delivery temperature, mat thickness before compaction, mix temperature during compaction | Subcontractor QA Records | Higgins
7 | Surface finish visual inspection | H | Site walk over | Post Construction | Visual Inspection | No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. | Subcontractor QA Records | Site Engineer | CPS
Post-Construction
8 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Quality
9 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer
10 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer