## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt Surfacing | itp |  |  |  |  | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt Surfacing V2 | 9d617e70-f1e5-4686-9238-4584fd472829
section | Asphalt - Surfacing (AC 14)
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out pegs installed every 20m if required
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Mark out on site
label | Records - Subcontractor QA Records
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Mix Design approved including peer review
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Material is approved by a Notice to Supplier being issued
label | Records - Mix Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Asphalt Material Quality Testing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius
label | Records - Asphalt Plant Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Asphalt Production Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Full volumetric and air voids test 1 test - 1 test per day
label | ○ Binder content and grading 1 test per 100t.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing and measurements
label | Conformance Criteria - Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature
label | Records - Asphalt Plant Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Tack Coat
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - A Spray sheet for every day
label | Frequency - Prior to placing Surfacing AC
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2
label | Records - Subcontractor QA Records
checkpoint | 7 - Construction of Surfacing Asphaltic Concrete
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site team QA Checks
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site walk over
label | Frequency - Post Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
section | Asphalt - Surfacing (AC 14)
checkpoint | 9 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Guardrail | itp |  |  |  |  | ITP - B1004F - Tangoio Falls Steep Underslip - Guardrail V2 | 55202a61-8adc-463d-9d6e-a561a18f7c95
section | Guardrail Installation
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - OFI or NTD/NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117
checkpoint | 5 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117
checkpoint | 6 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117
checkpoint | 7 - RSHDS Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
label | Frequency - At completion of Safety Barrier Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - RSHDS Audit Form
holdpoint | AUTHORITY HOLDPOINT
section | Post-Construction
checkpoint | 8 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel | itp |  |  |  |  | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel V2 | 0fc5c6f1-0c06-4185-bc2b-075e2b9573c7
section | Kerb & Channel
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out kerb line and level at 1m offset to EOS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | Frequency - 1/600m3, minimum of 1 per source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | Conformance Criteria - 20MPa at 28 days
label | Records - Concrete Delivery Dockets and lab test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Kerb Foundation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Sub base construction is completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Stringing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check weather forecast and avoid adverse conditions
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 6 - Stringing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 7 - Stringing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 8 - Slip forming
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | Frequency - Prior to slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 9 - Slip forming
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - To ensure the correct concrete mix is delivered
label | Records - Concrete Delivery Dockets and lab test results
checkpoint | 10 - Slip forming
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Expansion joints to be formed at 5m centres
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Kerbing Specification
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 11 - Tie-in with pre-cast components
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Work Instruction
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 12 - Protection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Backfilling to commence only after 72 hours
section | Post-Construction
checkpoint | 13 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Reinforced Slope (Rock Bolts, Soils Nails) | itp |  |  |  |  | ITP - B1004F - Tangoio Falls Steep Underslip - Reinforced Slope (Rock Bolts, Soils Nails) V2 | dc159693-1a67-4606-aacf-3e9ab154c94b
section | Preliminary & Setout
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Vegetation Clearance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation Clearance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
section | Material Compliance
checkpoint | 4 - Material Compliance - Rock Bolt & Soil Nail
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Grade 500E soil nail
label | ○ Class II corrosion protection
label | ○ Lengths and diameters shown on drawings are the minimum required
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance - reinforcing steel
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Reinforcing steel manufacturer's test reports and certificates
label | Frequency - Prior to undertaking works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including despatch records
label | Records - Email
checkpoint | 6 - Concrete quality plan
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete quality plan to be produced and approved before work starts
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | ○ Name, qualificationand expoerience of concrete works inspector
label | ○ Form and content of concrete placement card
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Concrete plant compliance cert
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of concrete supply plant, copy of certificate of audit for plant
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | ○ Plant test Results
label | ○ ASR Compliance Records
label | Records - Email
checkpoint | 8 - Concrete mix designs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Grout Mix
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Grout Checks
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Grout checked if its free from lumps & segregation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 11 - Request for use of alternative Drilling Fluid
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - If required
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Soil Nail construction methodology
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
section | Construction
checkpoint | 13 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Test Nail Locations
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | Frequency - Prior to Trial
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Records - Photos, Site Diary
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Insert micropile bar
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert micropile bar (ReidBar RB32) to full required length
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Embedded length of micropile 3.0m into ground
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Drill Holes
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill hole
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | ○ Submit all installation records for each soil nail and pile.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Flush holes
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Insert soil nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert soil nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Installation Records
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Installation records shall include:
label | ○ Length of bar
label | ○ Depth of drill hole
label | ○ Inclination/Verticality achieved
label | ○ Level of grout placed
label | ○ Batch numbers associated with grout placed in each hole
label | Records - Subcontractor QA Records
checkpoint | 20 - Install Grout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Including:
label | ○ Concrete despatch records
label | ○ Compression test results
label | – Must notify CPS for any failed result and cease works until resolved
label | Records - Subcontractor QA Records
checkpoint | 21 - Grout Sample Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Monitoring of grout loss
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Subcontractor QA Records
checkpoint | 23 - Install Bolts/Nails washers & nuts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Testing of Soil Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | Records - Certifications
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 25 - Testing of Soil Nails
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria -
checkpoint | 26 - Testing of Soil Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 27 - Soil Nail Final Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 28 - Shotcreting- prepare surface
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - Shotcreting- apply vertical
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 30 - Shotcreting- apply horizointal
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 31 - Shotcreting- compression testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 32 - Shotcreting- surface inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
section | Post-Construction
checkpoint | 33 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 34 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 35 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Stormwater | itp |  |  |  |  | ITP - B1004F - Tangoio Falls Steep Underslip - Stormwater V2 | 65ebef39-f04f-4380-b48a-0346fd4e743b
section | Pre-Construction
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Drawings and Specification
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check drawings and spec are the latest version.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out as per design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Check against plans for any discrepancies
label | Records - Survey receipt
checkpoint | 3 - Material Approval
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Materials as per design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
checkpoint | 4 - Location of underground services
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure underground services are positively identified and asbuilt. If the service conflicts with the design confirm resolution with CPS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Drainlayer Qualifications
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Drainlayer Certs
section | Construction
checkpoint | 6 - Trench and excavate for pipeline to design subgrade
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check subgrade with visual inspection and
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | Records - Subcontractor QA Records
checkpoint | 7 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site walk over
label | Frequency - Post Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
section | Post-Construction
checkpoint | 8 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's