## Guardrail
|  |  |  | Inspection Test Plan |  |  | Approved / Signature
|  |  |  | Contract Name: | F5001A Hicks Bay slip repair |  | GHD Approver | Quality Approver | GHD Eng. | Fred Rewa
|  |  |  | Procedure: | Guard Railing |  | Name / Signature | Name / Signature | Site Engineer | Amritpal Singh
Inspection & Test Plan / Checklist | [6 empty] | #VALUE! |  | Quality Eng. | Jose Buernaventura
Lot No: F5001A |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: SH35 RS132 RP3.394
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specifications/Drawing Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Guardrail Posts Installation | H | Design check locations of posts and check for any clashes with underground services or similar. | Prior to commencement | Document review | Contractor to confirm that installation of posts avoids culvert clash | Site pics, NTE/NTC | Site Engineer | GHD Engineer
2 | Survey Setout | H | Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing | Site Engineer | GHD Engineer
3 | Material Compliance | W | All roadside barriers shall comply with NZTA M/23:2023. Only MASH TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware. | Prior to commencement | Visual inspection/ Document review | Comply with NZTA M/23:2023. MASH TL3 approved systems only | Manufacturing certificates, delivery dockets, Photo's | Site Engineer
4 | Guardrail Installation | W | Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. All Guardrail laps are to be lapped in the traffic direction | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
5 |  | W | Hazard markers to be installed on all terminal ends. Edge markers posts to be secure to the guard rail face. Face of Guardrail to be a minimum of 1.2m from edge line. Engineer to confirm min of 1m support width behind the barrier at a desirable grade of 10:1 | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
5 |  | H | Terminal anchor points ground conditions assessed and confirmed as being adequate based on barrier manufacturer requirements. | During installation and on completion | Visual inspection, measurement | As per manufacturers specifications | GHD COR, Photo's | Site Engineer | GHD Engineer
6 |  | W | Hazard markers to be installed at terminal ends. Edge markers posts to be secure to the guard rail face. Face of guardrail to be a minimum of 1.2m from edge line. Engineer to confirm min of 1m support width behind the barrier at a desirable grade of 10:1 | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
7 |  | W | Barrier face is to be a maximum clearance of 200mm from the kerb face in the location where there is kerbing. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing single post signs are to be repositioned behind the barrier. Offset of fence is to be confirmed to ensure that there is sufficient room for barrier installation | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
8 | Fit for purpose Inspection | H | Barrier to undergo fit for purpose inspection by competent person System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM by contractor | Prior to trafficking, | Visual inspection | Pass inspection | Written Confirmation from NZTA IMI qualified inspector | Site Engineer | GHD Engineer
9 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, GHD COR | Site Engineer | GHD Engineer
Section 4 : Final Inspection and Handover
11 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
12 | Completion Sign Off From Fields Below | H |  |  |  |  | Signatures | PM | GHD | QM
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: