## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-134-CIV-Stormwater drainage materials and CCTV | itp |  |  |  |  | ITP-134-CIV-Stormwater drainage materials and CCTV Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-134-CIV-SSB-Stormwater drainage materials and CCTV
label | ITP Description: SSB-Stormwater drainage materials and CCTV
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 134-CIV
label | Revision Number: 0
label | Revision Date: 30/01/2023
label | ITP created by: Hiruni Wickramarathne
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 701 (May 2020)
label | 1.2 Non Dependent
label | Reference: VicRoads Section 705 (June 2021)
label | 1.3 Non Dependent
label | Reference: IFC Drawings
section | Preliminaries-Materials
checkpoint | 2.2 Drainage Flexible Pipes
label | REFERENCE: Section 701.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Flexible pipes shall be supplied in accordance with 701.08
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Precast Drainage Pit
label | REFERENCE: Section 705.07, Section 705.04, Section 705.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Cast in Place Drainage Pit
label | REFERENCE: Section 705.06 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Drainage Pit - Step Irons
label | REFERENCE: Section 705.04, Section 705.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 Drainage Bedding Material
label | REFERENCE: Section 701.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 Drainage Backfill Material
label | REFERENCE: Section 701.09, Section 701.19
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Construction / Installation Activities
checkpoint | 5.1 Pits - installation
label | REFERENCE: IFC Drawings VR 701, VR 705
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All the pits for this separable package are installed and respecting Lots are closed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each drainage separable package
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This separable package Pit installation Lots
date | Date Completed:
checkpoint | 5.1 Pipes - installation
label | REFERENCE: IFC Drawings VR 701, VR 705
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All the pipe runs for this separable package are installed and respecting Lots are closed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each drainage separable package
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This separable package Pipe installation Lots
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Flushing & CCTV
label | REFERENCE: Section 701.28, Section 701.30
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Record Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, CCTV Reports
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 As Built Survey
label | REFERENCE: Section 701.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
date | Date Completed:
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Repairs to Damaged Pipes
label | REFERENCE: Section 701.31
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | ○ cracks wider than 0.5 mm
label | ○ spalling of concrete
label | ○ exposed reinforcement
label | ○ joints that are not fully engaged.
label | Any pipes with defects greater than the following limits shall be removed and replaced:
label | ○ longitudinal cracks greater than 2 mm
label | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | ○ penetrations with area greater than 400 mm2
label | ○ pipe joints that are separated.
label | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP