## Folder Structure
Ground Level | A. Baffles Checklist
B. Perimeter Panel Checklist
C. Internal Panel Checklist
Level 1 | A. Baffles Checklist
B. Perimeter Panel Checklist
C. Internal Panel Checklist
Level 2 | A. Baffles Checklist
B. Perimeter Panel Checklist
C. Internal Panel Checklist
Level 3 | A. Baffles Checklist
B. Perimeter Panel Checklist
C. Internal Panel Checklist
Level 4 | A. Baffles Checklist
B. Perimeter Panel Checklist
C. Internal Panel Checklist

## A.Baffles Checklist
Type | Name | Value
Checklist | Façade Baffle & Soaker Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Install Sika Facade Battle to vertical joints | Photo Required
Checkpoint | Install S/S pin into rebate and mechanically fix to panel | Photo Required
Checkpoint | Install SS soaker - beadseal with Sikaflex 11 FC & mechanically fixed to one panel | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## B. Perimeter Panel Checklist
Type | Name | Value
Checklist | Joint Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install expansion tape to horizontal & vertical inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer to horizontal & vertical joints | Photo Required
Checkpoint | Apply sealant to horizontal & vertical joints | Photo Required
Checkpoint | Write initials and date beside each joint | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## C. Internal Panel Checklist
Type | Name | Value
Checklist | Joint Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install expansion tape to horizontal & vertical inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer to horizontal & vertical joints | Photo Required
Checkpoint | Apply sealant to horizontal & vertical joints | Photo Required
Checkpoint | Write initials and date beside each joint | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required