## Table 1
Line marking |  |  |  | Hayden Brett Created Tue, 16 Jan 2024, 3:49 PM (UTC+11)
Subcontractor (if applicable)
ITP Details:
| Client |  | Construction Process |  |  | Contract Number: |  | Speciﬁcations |  | Structure / Component |  |  | Prepared By |  |  | Approved By
| Regional Roads Victoria |  | Linemarking |  |  |  |  | Vicroads Speciﬁcation Section 721 |  | Linemarking
Project location
Lot no.
Lot details
Lot size/qtys
Date Start: - End: -
Text Legend:
1. Preliminary Works
Task/Activity Description |  | Speciﬁcati on Reference |  |  | Acceptance Criteria |  | Test/Inspection Method |  | Responsibility |  | Signature | Photo |  |  | Comments
1.1 Line marking Conformance Frequency Prior to commencing any activity |  | 721.A05 |  |  | Materials to be used conform with speciﬁcation |  | Method Record Review Records Material sheet |  | IP Contractor Representative WP SWA Representative
1.2 Site preparation Frequency |  | 721.A06 |  |  | Removal of any existing unsound,obsolete or redundant pavement markings |  | Method Visual and photos Records Photos |  | IP Contractor Representative WP SWA Representative
Prior to commencing any activity |  |  |  |  | Removal of any foreign material or debris
Task/Activity Description |  | Speciﬁcati on Reference |  |  | Acceptance Criteria |  | Test/Inspection Method |  | Responsibility |  | Signature | Photo |  |  | Comments
1.3 Set-out of Pavement Markings Frequency Prior to commencing any activity |  | 721.A09 |  |  | Pavement markings to set-out in accordance with IFC Drawings |  | Method Visual and photos Records Photos |  | IP Contractor Representative HP SWA Representative
2. Installation
Task/Activity Description |  | Speciﬁcati on Reference |  |  | Acceptance Criteria |  | Test/Inspection Method |  | Responsibility |  | Signature |  |  | Photo |  |  | Comments
2.1 Line marking Installation Frequency During Construction |  | 721.E01 |  |  | Line marking installed as per IFC Drawings |  | Method Visual and photos Records Photos |  | IP Contractor Representative WP SWA Representative
Task/Activity Description |  | Speciﬁcati on Reference |  |  | Acceptance Criteria |  | Test/Inspection Method |  | Responsibility |  | Signature |  |  | Photo |  |  | Comments
2.2 Glass bead Install Frequency During line marking works |  | 721.E01 |  |  | Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution |  | Method Visual and photos Records Photos |  | IP Contractor Representative WP SWA Representative
3. Compliance
| Task/Activity Description |  | Speciﬁcation Reference |  |  | Acceptance Criteria |  | Test/Inspection Method |  | Responsibility |  |  | Signature |  |  | Photos
| 2.1 Completion Inspection Frequency Upon Construction |  | 721.E01 |  |  | Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects. |  | Method Visual and photos Records Photos |  | IP Contractor Representative WP SWA Representative
Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
Comments
Photo and video
Final Inspection: The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
Subcontractor Team signature Not signed yet.
Photo and video
Project Team Signature - Final Inspection: The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations. Client Team Signature -