## Table 1
Guardrail ITP |  |  |  | Hayden Brett Created Tue, 16 Jan 2024, 3:47 PM (UTC+11)
Subcontractor (If Applicable)
ITP Details:
| Client |  | Construction Process |  |  | Contract Number: |  |  | Speciﬁcations |  |  | Structure / Component |  |  | Prepared By |  |  | Approved By
| Regional Roads Victoria |  | Guardrail Installation | [5 empty] | VicSpeciﬁcations: VicRoads Speciﬁcation Section 708 |  |  | Guardrail
Project Location
Lot No.
Lot details
Lot size/qtys
Date Start: - End: -
Legend: Legend:
1. Preliminary Works
Task/Activity Description |  | Acceptance Criteria |  |  | Reference Documents |  |  | Method & Record of conformity |  |  | Responsibility |  |  | Signature 1 |  |  | Comments
1.1 Check for correct documentation Frequency Prior to commencing any activity |  | Ensure that all employees and subcontractors are: -using the correct and complete set of drawings -all drawings are the latest revision.. |  |  | Design Drawings |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IP Project Manager/ Site Supervisor
1.2 Implementation of all measures and controls Frequency Prior to commencing any activity |  | All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS |  |  | EMP, TMP & SWMS |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IP Project Manager/ Site Supervisor
Task/Activity Description |  | Acceptance Criteria |  |  | Reference Documents |  |  | Method & Record of conformity |  |  | Responsibility |  |  | Signature 1 |  |  | Comments
1.3 Setting Out Frequency Prior to commencing any activity |  | Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg. |  |  | Drawings 708.08 |  |  | Method: Document Review Record: Signed ITP |  |  | IP Project Manager/ Site Supervisor Superintendent
2. Construction works
Task/Activity Description |  | Acceptance Criteria |  |  | Reference Document s |  | Inspection method & Record of conformity |  |  | Responsib ility | Signature |  | Attachments |  |  | Photos |  |  | Comments
2.1 Supply of materials Frequency:Each Delivery |  | All materials are to be on VicRoads current accepted products list and conform with the detailed design |  |  | 708.04 708.05 Detailed design |  | Method: Visual Inspection Record: Signed ITP |  |  | IP Project Manager/ Site Supervisor
Task/Activity Description |  | Acceptance Criteria |  |  | Reference Document s |  | Inspection method & Record of conformity |  |  | Responsib ility | Signature |  | Attachments |  |  | Photos |  |  | Comments
2.2 Installation Frequency:Each lot as required |  | The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100 |  |  | Detailed design 708.08 SD3661 AS4100 |  | Method: Visual Inspection Record: Signed ITP |  |  | IP SWA Engineer Site Supervisor
2.3 End Treatments Frequency:Each lot as required |  | Guardrail end treatments are to be installed to VicRoads speciﬁcations |  |  | Detailed design 708.08 |  | Method: Visual Inspection Record: Signed ITP |  |  | IP SWA Engineer Site Supervisor
2.4 Motorcycle rub rail Frequency:Each lot as required |  | Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail |  |  | Detailed design 708.09 |  | Method: Visual Inspection Record: Signed ITP |  |  | IP SWA Engineer Site Supervisor
Final Inspection Notes Photo and video Project Team signature - Photo and video Final Inspection Notes Client Signature -