## Table 1
General Concrete Paving | [5 empty] | Hayden Brett Created Tue, 16 Jan 2024, 3:47 PM (UTC+11)
Subcontractor (if applicable)
ITP Details:
| Client |  | Construction Process |  | Contract Number: |  |  |  | Speciﬁcations |  |  |  | Structure / Component |  |  | Prepared By |  |  | Approved By
| Regional Roads Victoria |  | General Concrete Paving | [5 empty] | Vicroads Speciﬁcation |  |  |  | Footpaths and other
[9 empty] | Section 173, 175, 204, |  |  |  | surfacing
205, 210, 290, 304, 702
and 720, VR Code of
Practice 500.2
Project Location
Lot Number
Lot Details
Lot size/Qty
Date Start: - End: -
Legend:
1. Preliminary Works
| Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Pictures |  |  | Comments
| 1.1 Check for correct documentation Frequency Prior to commencing any activity |  | Ensure that all employees and subcontractors are: -using the correct and complete set of drawings -all drawings are the latest revision |  | IFC Drawings |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IHP SWA Project Manager
Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Pictures |  |  | Comments
1.2 Implementation of all measures and controls Frequency Prior to commencing any activity |  | All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS. |  | EMP, TMP & SWMS |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IHP SWA Project Manager
2. Construction works
Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Inspection method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Photos |  |  | Comments
2.1 Survey Set-Out Frequency:Prior to commencement of excavation. |  | Area has been set out in accordance with the drawings |  | Work Procedure |  |  | Method: Verify Record: Signed ITP |  |  | IP SWA Project Manager
Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Inspection method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Photos |  |  | Comments
2.2 Excavation Permit Frequency:Each Lot |  | An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation |  | Excavation Permit |  |  | Method: Verify Record: Signed ITP |  |  | IHP SWA Project Manager IP SWA SEQ Adviser
2.3 Formwork Frequency:Each Lot |  | Formwork shall comply with the requirements of AS 3610 |  | AS 3610 |  |  | Method: Site Inspection Record: Signed ITP |  |  | IP SWA Project Manager
2.4 Reinforcement Frequency:Each Lot |  | Steel reinforcement shall comply with the requirements of AS/NZS 4671 Minimum cover of 50mm |  | AS/NZS 4671 |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IP SWA Project Manager
Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Inspection method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Photos |  |  | Comments
2.5 Temporary Drainage Provisions Frequency:Prior to commencing |  | If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority. |  | VcRoads Std Specs 703.15 |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IHP SWA Project Manager
2.6 : Bedding Frequency : Each lot as required |  | · Crushed rock bedding material as per drawings · Bedding trimmed, moistened, and compacted as necessary · Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm |  | VcRoads Std Specs 703.18 IFC Drawings |  |  | Method: Site Inspection/ Document Review Record: Signed ITP |  |  | IHP SWA Project Manager AP RRV Superinten dent
Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Inspection method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Photos |  |  | Comments
2.7 : Concrete Placement Frequency : Each lot as required |  | · Concrete strength as per drawing speciﬁcation · Comply with requirements of AS1379 · Aggregates to comply with Table 703.051 · Extrusion machines cement content ≥ 320kg/m3 · Surface pitting < 5mm diameter · Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre. |  | VicRoads Std Specs 703.04(b) VicRoads Std Specs 703.20 VicRoads Std Specs 703.21 IFC Drawings AS 1379 |  |  | Method: Visual Inspection Record: Signed ITP & Test Reports |  |  | IHP SWA Project Manager AP RRV Superinten dent TP External testing Company representat ive
2.8: Finish Surfaces Frequency : Each lot as required |  | · Footpaths and other Surfacing: Wooden ﬂoat ﬁnish |  | VcRoads Std Specs 703.22 |  |  | Method: Visual Inspection Record: Signed ITP & Test Reports |  |  | IHP SWA Project Manager AP RRV Superinten dent
Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Inspection method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Photos |  |  | Comments
2.9: Tolerances Frequency : Each lot as required |  | · Match existing surfaces ± 5mm · Section dimensions: o Within 5mm and 15mm for width; and o Within ±3mm for dimensions less than 25mm. · Concrete footpath: o 150mm thick o SL72 reinforcement · Concrete Surfacing: o Type 1 100mm o Type 2 150mm |  | VicRoads Std Specs 703.13 IFC Drawings |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IHP SWA Project Manager
2.10: Joints Frequency : Each lot as required |  | · Footpaths and other surfacing: o Expansion joints at 12.5m regular intervals o Control joints at 2.5m regular intervals o 20mm deep and 5mm wide Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material. |  | VicRoads Std Specs 703.23 |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IHP SWA Project Manager
| Task/Activity Description |  | Acceptance Criteria |  | Reference Document s |  |  | Inspection method & Record of conformity |  |  | Responsib ility |  | Signature 1 |  | Reports |  |  | Photos |  |  | Comments
| 2.11: Backﬁlling Frequency : Each lot as required |  | · Topsoil compacted in layers < 150mm · Width ≥ 300mm behind edging to top of edging · Topsoil placed after 3 days of concrete placement |  | VicRoads Std Specs 703.26 |  |  | Method: Visual Inspection Record: Signed ITP |  |  | IHP SWA Project Manager
Final Notes
Photo and video
Final Inspection: The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
Project Team signature -
Final Inspection: The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
Client Signature -