## Table 1
Pre - Construction ITP |  |  |  |  | Hayden Brett Created Tue, 16 Jan 2024, 3:49 PM (UTC+11)
Project/ Site Name and Number Contract Number Description of works Note: Based on the VicRoads contract speciﬁcation and must also be checked for each job against speciﬁc Hold Point to ensure acceptance criteria is correct. 1.0 Pre-Construction Checklist
1.1 Communication:
| External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Community and emergency services
Emergency response plan
1.2 Approved Construction Documentation
| External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
IFC drawings (PDF,hardcop y)·
Digital (CAD) ﬁles (Surveyor)
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Budget / Resource arrangement POs (incl. sub-contract agreements)
Quantities / Speciﬁcations
1.3 Dilapidation Report (records and photographs)
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Residential (ie: structures, access/gate, letterbox, fence)
Hold Point (HP) |  | Business (ie: structures, access/fence/gate, signs/letterbox)
Hold Point (HP) |  | Agricultural (ie: access, livestock, fence/gate)
1.4 Heritage / Cultural listed areas:
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | “No Go Zone”
Hold Point (HP) |  | Tourist attraction
1.5 Protected Environment
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Flora
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
| Hold Point (HP) |  | Fauna
| Hold Point (HP) |  | Water bodies
1.6 Site Pre-start checklist, and supporting documents
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Dial Before You Dig
Excavation Permit
Assess and arrange for Service location
2.0 Pre-Commencement Checklist
2.1 Traﬃc Items
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
VMS boards
TGS/TMP, MoA
2.2 Site marks / references
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Limit of Works
Survey control point
2.3 Services, inspect/identify clash points:
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Sewer, Water
Gas, Electricity
Telecommunication
Drainage (ie: council/shire, Other state authority)
Other- specify:
2.4 Site-Traﬃc Risk Assessment, including:
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
O/H and U/G services ﬂagged “No Go Zone”
Trees(s) marked and approved for trimming or removal
2.5 SWMSs reviewed:
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Site-speciﬁc
Spotter required / arranged
2.6 Site Access (incl. VicRoads pre-commencement - meeting with superintendent)
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Sight and Clearance Distances:
Stop-slow areas, spotter, slips, conﬁned space/work at height
Vehicle access to properties
Proximity to Services: clearance requirements
Proximity to Water: supply point, water- table/dam/river/coast/p ort
Site compound/Plant parking, material stockpile area,” dump- site”
3.0 Construction
3.1 Vegetation Removal
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
| Hold Point (HP) |  | Spotter, Traﬃc Control
| Hold Point (HP) |  | Equipment, Access
| Hold Point (HP) |  | Soil erosion / water contamination
3.2 Contaminated Materials
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Contaminated Materials
3.3 Traﬃc Items
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | External review: Road Safety Audit
Hold Point (HP) |  | Internal review: adjust hold-time (traﬃc lights / traﬃc controller), ﬂow- bias, identify peak-hour period(s) / public transport / rubbish collection
3.4 Trenching works
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Review escape plan (routes)
Review ground / water conditions
Indentify Shoring / Benching requirements
3.5 Drainage Works
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Assess surface-water impact – ﬂow-path / catchment / outlet
Surface drainage (swale drain)
Sub-surface drain pipe and aggregate (agricultural drains / “agi pipe”)
Review conﬁned space entry
Review lifting methods (load / equipment / plant / crane)
Levels
Pit covers / Grates
3.6 Structural Items
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Crown units / culvert
Hold Point (HP) |  | Retaining structure works
Hold Point (HP) |  | Bridge works
3.7 Concrete kerb works:
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Alignment / level
proﬁle / ﬁnish
3.8 Concrete Works
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | (in-situ & pre-cast) - Bedding material / blinding material
Hold Point (HP) |  | (in-situ) - Formwork, duct-work
Hold Point (HP) |  | (pre-cast) Alignment/dimensions
Hold Point (HP) |  | (in-situ) - Rebar layout
Hold Point (HP) |  | (in-situ) - Concrete mix / Compaction / Placement method(s)
Hold Point (HP) |  | (pre-cast) - Lift points / placement method
Hold Point (HP) |  | (in-situ & precast) - Pre-stress works (where applicable)
Hold Point (HP) |  | (in-situ & pre- cast) Finish
3.9 Unsuitable sub-grade / sub-base / Stabilisation treatment
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Require in-situ testing / laboratory report (where required)
Hold Point (HP) |  | Material dockets (ie: Lime / Cement)
Hold Point (HP) |  | Density results
Hold Point (HP) |  | Proof-roll
3.10 Pavement Works
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Density results
Hold Point (HP) |  | Proof-roll / Test Rolling
Hold Point (HP) |  | Dryback results (NB: required prior to sealing works)
Hold Point (HP) |  | Ball Penetration Test
3.11 Utility Services, Traﬃc / Public lights
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Level & Location (ie: clearance requirement)
Approved equipment for installation
Pit and conduit (ie: clearance requirement)
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Audits by relevant authority / hand-over procedure
3.12 Pavement Surface Works
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
| Hold Point (HP) |  | Seal (ie: suitable material, spray-sheet details)
| Hold Point (HP) |  | Asphalt (ie: material dockets)
3.13 Landscape
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Seed / Grass
Hydro-seed / Hydro- mulch
Street furniture
Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
4.0 Practical Completion
4.1 Road Fixtures
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Linemarking & RRPMs
Hold Point (HP) |  | Signs
Hold Point (HP) |  | Guide posts
4.2 Safety Barrier Works
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Guardrail
Hold Point (HP) |  | Wire-rope
Hold Point (HP) |  | Motorcycle-safe ﬁxtures
4.3 Fences and Gates
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Fences and Gates
4.4 Quality Ride Test
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Quality Ride Test
5.1 End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months
External Refrence |  | Activity / Description |  | Yes/No/NA |  |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
Hold Point (HP) |  | Linemarking & RRPMs
Hold Point (HP) |  | Signs, guide posts
| External Refrence |  | Activity / Description |  |  | Yes/No/NA |  | Date |  | Signature |  | Comments |  | Attachments |  | Photos/Video reference
| Hold Point (HP) |  | Seal / Asphalt surface
| Hold Point (HP) |  | Landscape (where applicable)
Final Comments - :
Project Team Signature -
Final Comments - :
SPM Approval Signature -