## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SWA-013 - Pre - Construction | itp |  |  |  |  | SWA-013 - Pre - Construction
section | 1.0 - Pre-Construction Checklist
checkpoint | 1.1 - Communication (1)
label | ACTIVITY / DESCRIPTION: Community and emergency services
date | Date:
checkpoint | 1.1 - Communication (2)
label | ACTIVITY / DESCRIPTION: Emergency response plan
date | Date:
checkpoint | 1.2 - Approved Construction Documentation (1)
label | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
date | Date:
checkpoint | 1.2 - Approved Construction Documentation (2)
label | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
date | Date:
checkpoint | 1.2 - Approved Construction Documentation (3)
label | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
date | Date:
checkpoint | 1.2 - Approved Construction Documentation (4)
label | ACTIVITY / DESCRIPTION: Quantities / Specifications
date | Date:
checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: "No Go Zone"
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Tourist attraction
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Protected Environment (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Flora
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Protected Environment (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Fauna
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Protected Environment (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Water bodies
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
label | ACTIVITY / DESCRIPTION: Dial Before You Dig
date | Date:
checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
label | ACTIVITY / DESCRIPTION: Excavation Permit
date | Date:
checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
label | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
date | Date:
section | 2.0 - Pre-Commencement Checklist
checkpoint | 2.1 - Traffic Items (1)
label | ACTIVITY / DESCRIPTION: VMS boards
date | Date:
checkpoint | 2.1 - Traffic Items (2)
label | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
date | Date:
checkpoint | 2.2 - Site marks / references (1)
label | ACTIVITY / DESCRIPTION: Limit of Works
date | Date:
checkpoint | 2.2 - Site marks / references (2)
label | ACTIVITY / DESCRIPTION: Survey control point
date | Date:
checkpoint | 2.3 - Services, inspect/identify clash points: (1)
label | ACTIVITY / DESCRIPTION: Sewer, Water
date | Date:
checkpoint | 2.3 - Services, inspect/identify clash points: (2)
label | ACTIVITY / DESCRIPTION: Gas, Electricity
date | Date:
checkpoint | 2.3 - Services, inspect/identify clash points: (3)
label | ACTIVITY / DESCRIPTION: Telecommunication
date | Date:
checkpoint | 2.3 - Services, inspect/identify clash points: (4)
label | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
date | Date:
checkpoint | 2.3 - Services, inspect/identify clash points: (5)
textbox | ACTIVITY / DESCRIPTION: Other specify:
date | Date:
checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
date | Date:
checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
date | Date:
checkpoint | 2.5 - SWMSs reviewed: (1)
textbox | ACTIVITY / DESCRIPTION: Site-specific
date | Date:
checkpoint | 2.5 - SWMSs reviewed: (2)
textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
date | Date:
checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
date | Date:
checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
date | Date:
checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
date | Date:
checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
date | Date:
checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
date | Date:
checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
date | Date:
section | 3.0 - Construction
checkpoint | 3.1 - Vegetation Removal (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Vegetation Removal (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Equipment, Access
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Vegetation Removal (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Contaminated Materials
label | ACTIVITY / DESCRIPTION: Contaminated Materials
date | Date:
checkpoint | 3.3 - Traffic Items (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Traffic Items (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Trenching works (1)
label | ACTIVITY / DESCRIPTION: Review escape plan (routes)
date | Date:
checkpoint | 3.4 - Trenching works (2)
label | ACTIVITY / DESCRIPTION: Review ground / water conditions
date | Date:
checkpoint | 3.4 - Trenching works (3)
label | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
date | Date:
checkpoint | 3.5 - Drainage Works (1)
label | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
date | Date:
checkpoint | 3.5 - Drainage Works (2)
label | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
date | Date:
checkpoint | 3.5 - Drainage Works (3)
label | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
date | Date:
checkpoint | 3.5 - Drainage Works (4)
label | ACTIVITY / DESCRIPTION: Review confined space entry
date | Date:
checkpoint | 3.5 - Drainage Works (5)
label | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
date | Date:
checkpoint | 3.5 - Drainage Works (6)
label | ACTIVITY / DESCRIPTION: Levels
date | Date:
checkpoint | 3.5 - Drainage Works (7)
label | ACTIVITY / DESCRIPTION: Pit covers / Grates
date | Date:
checkpoint | 3.6 - Structural Items (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Crown units / culvert
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Structural Items (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Retaining structure works
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Structural Items (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Bridge works
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Concrete kerb works: (1)
label | ACTIVITY / DESCRIPTION: Alignment / level
date | Date:
checkpoint | 3.7 - Concrete kerb works: (2)
label | ACTIVITY / DESCRIPTION: profile / finish
date | Date:
checkpoint | 3.8 - Concrete Works (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION:
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (4)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (5)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (6)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (7)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Works (8)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Density results
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Proof-roll
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Pavement Works (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Density results
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Pavement Works (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Pavement Works (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Pavement Works (4)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Ball Penetration Test
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
label | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
date | Date:
checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
label | ACTIVITY / DESCRIPTION: Approved equipment for installation
date | Date:
checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
label | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
date | Date:
checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
label | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
date | Date:
checkpoint | 3.12 - Pavement Surface Works (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Pavement Surface Works (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Landscape (1)
label | ACTIVITY / DESCRIPTION: Seed / Grass
date | Date:
checkpoint | 3.13 - Landscape (2)
label | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
date | Date:
checkpoint | 3.13 - Landscape (3)
label | ACTIVITY / DESCRIPTION: Street furniture
date | Date:
checkpoint | 3.13 - Landscape (4)
label | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
date | Date:
section | 4.0 - Practical Completion
checkpoint | 4.1 - Road Fixtures (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1 - Road Fixtures (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Signs
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1 - Road Fixtures (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Guide posts
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Safety Barrier Works (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Guardrail
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Safety Barrier Works (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Wire-rope
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Safety Barrier Works (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Fences and Gates
label | ACTIVITY / DESCRIPTION: Fences and Gates
date | Date:
checkpoint | 4.4 - Quality Ride Test
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Quality Ride Test
date | Date:
holdpoint | AUTHORITY HOLDPOINT
section | 5.0
checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Signs, guide posts
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
label | EXTERNAL REFERENCE: Hold Point (HP)
label | ACTIVITY / DESCRIPTION: Landscape (where applicable)
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP