## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-002 - Earthworks | itp |  |  |  |  | ITP-002 - Earthworks
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: IFC Drawings
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
label | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation.
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | METHOD: Verify
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation Permit
label | METHOD: Verify
label | RECORD: Signed ITP
label | IHP/IP
label | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
date | Date Completed:
checkpoint | 2.3 - Sub grade Material Properties
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
label | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
label | METHOD: Site Inspection/Test Report
label | RECORD: Signed ITP & Test Report
label | TP/AP
label | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
date | Date Completed:
checkpoint | 2.4 - Inspection of Subgrade Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.5 - Material Classiﬁed as Silt
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer.
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
label | METHOD: Site Inspection/ Document Review
label | RECORD: Signed ITP
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.7 - Unsuitable Material
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
label | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP & Test Reports
label | IHP/AP/TP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
date | Date Completed:
checkpoint | 2.8 - Groundwater
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP & Test Reports
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.9 - Trimming and level conformity
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
label | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
label | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
label | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
label | METHOD: Survey
label | RECORD: Signed ITP & Survey Report
label | SCP
label | RESPONSIBILITY: SWA Project Manager/External Surveyor
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Test Rolling
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
label | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
label | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP/WP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
label | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
label | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
label | METHOD: Compaction Test
label | RECORD: Signed ITP & Test Reports
label | IHP/AP/TP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
date | Date Completed:
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP