## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004 - Underground Drainage | itp |  |  |  |  | ITP-004 - Underground Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
label | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
label | FREQUENCY: Approval prior to placement of order
label | ACCEPTANCE CRITERIA: Refer to Construction Drawings
label | REFERENCE DOCUMENTS: Vic roads Standard drawings
label | METHOD: Review and approval of documentation, Visual inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
label | REFERENCE DOCUMENTS: Vicroads std sec 701.09
label | METHOD: Construction Drawings
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
label | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: Vicroads std sec 701.09
label | METHOD: Construction Drawings
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.3 - EXCAVATION
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
label | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
label | METHOD: On-site Measurement
label | RECORD: Signed ITP & Drainage Checklist
label | WP
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | ○ 100 mm where D < 1500 mm
label | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
label | METHOD: Site Inspection
label | RECORD: Signed ITP
label | WP
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
checkpoint | 2.5 - PLACEMENT OF FILLING
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
label | (I) Culvert Under Area not to be Paved
label | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
label | METHOD: Site Inspection
label | RECORD: Signed ITP
label | WP
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
label | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
label | METHOD: Visual inspection
label | RECORD: Signed ITP
label | HP/AP
label | RESPONSIBILITY: Project Engineer/Clients Superinten dent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
label | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
label | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
label | REFERENCE DOCUMENTS: NIL
label | METHOD: Visual inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: Project Engineer/Si te Supervisor
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
label | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | (b) Backﬁll
label | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: Vicroads std sec 701.19
label | METHOD: Lab Test
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP