## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-005 - Flexible Pavement Construction | itp |  |  |  |  | ITP-005 - Flexible Pavement Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - SET OUT OF WORKS
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
label | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
label | ○ Refence checking to be conducted with string lines
label | REFERENCE DOCUMENTS: Vicroads std sec 100.6
label | METHOD: Survey set-out
label | RECORD: Signed ITP
label | SCP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
label | REFERENCE DOCUMENTS: Vicroads std sec 204.03
label | METHOD: Survey Report
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
label | REFERENCE DOCUMENTS: Vicroads std sec 304.08
label | METHOD: Visual & Laboratory Report
label | RECORD: Signed ITP
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
label | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
label | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
label | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | REFERENCE DOCUMENTS: Vicroads std sec 304.08
label | METHOD: Laboratory Test Report
label | RECORD: Signed ITP
label | IHP/IP/AP
label | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
date | Date Completed:
checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
label | METHOD: Proof roll
label | RECORD: Signed ITP & Test Report
label | HP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
label | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
label | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
label | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
label | METHOD: Survey report
label | RECORD: Signed ITP
label | IHP/WP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP