## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-006 - Kerb & Channel | itp |  |  |  |  | ITP-006 - Kerb & Channel
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Vicroads std sec 100.6
label | METHOD: Drawing Register
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
label | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Setting Out
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
label | REFERENCE DOCUMENTS: Vicroads std sec 703.13
label | METHOD: Survey Setout
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
label | REFERENCE DOCUMENTS: Vicroads std sec 703.20
label | METHOD: Survey/Site Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Subgrade Inspection
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
label | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.3 - Bedding Preparation
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
label | METHOD: Site Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.4 - Kerb Concrete Mixture/Strength
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
label | METHOD: Delivery Dockets
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.5 - Tolerances on Line, Level & Shape
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.6 - Kerb and Channel Finish
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
checkpoint | 2.7 - Kerb Backﬁll
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Compaction Testing
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
label | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
label | METHOD: Test Point
label | RECORD: Signed ITP
label | TP/HP/AP
label | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
label | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
label | METHOD: Survey Report
label | RECORD: Signed ITP & Test Reports
label | TP/HP/AP
label | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP