## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-008 - Line Marking | itp |  |  |  |  | ITP-008 - Line Marking
section | 1 - Preliminary Works
checkpoint | 1.1 - Line marking Conformance
label | FREQUENCY: Prior to commencing any activity
label | SPECIFICATION REFERENCE: 721.A05
label | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
label | METHOD: Record Review
label | RECORDS: Material sheet
label | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | Date Completed:
checkpoint | 1.2 - Site preparation
label | FREQUENCY: Prior to commencing any activity
label | SPECIFICATION REFERENCE: 721.A06
label | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
label | METHOD: Visual and photos
label | RECORDS: Photos
label | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | Date Completed:
checkpoint | 1.3 - Set-out of Pavement Markings
label | FREQUENCY: Prior to commencing any activity
label | SPECIFICATION REFERENCE: 721.A09
label | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
label | METHOD: Visual and photos
label | RECORDS: Photos
label | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Installation
checkpoint | 2.1 - Line marking Installation
label | FREQUENCY: During Construction
label | SPECIFICATION REFERENCE: 721.E01
label | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
label | METHOD: Visual and photos
label | RECORDS: Photos
label | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | Date Completed:
checkpoint | 2.2 - Glass bead Install
label | FREQUENCY: During line marking works
label | SPECIFICATION REFERENCE: 721.E01
label | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
label | METHOD: Visual and photos
label | RECORDS: Photos
label | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | Date Completed:
section | 3 - Compliance
checkpoint | 3.1 - Completion Inspection
label | FREQUENCY: Upon Construction
label | SPECIFICATION REFERENCE: 721.E01
label | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
label | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
label | METHOD: Visual and photos
label | RECORDS: Photos
label | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | Date Completed:
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP