## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-010 - Guardrail | itp |  |  |  |  | ITP-010 - Guardrail
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision..
label | REFERENCE DOCUMENTS: Design Drawings
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: Project Manager/ Site Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
label | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: Project Manager/ Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Setting Out
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
label | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
label | REFERENCE DOCUMENTS: Drawings 708.08
label | METHOD: Document Review
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Supply of materials
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
label | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: Project Manager/ Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Installation
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
label | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
label | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Engineer/Site Supervisor
date | Date Completed:
checkpoint | 2.3 - End Treatments
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
label | REFERENCE DOCUMENTS: Detailed design 708.08
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Engineer/Site Supervisor
date | Date Completed:
checkpoint | 2.4 - Motorcycle rub rail
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
label | REFERENCE DOCUMENTS: Detailed design 708.09
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Engineer/Site Supervisor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP