## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-045 - General Concrete Paving | itp |  |  |  |  | ITP-045 - General Concrete Paving
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: IFC Drawings
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
label | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation.
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | METHOD: Verify
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation Permit
label | METHOD: Verify
label | RECORD: Signed ITP
label | IHP/IP
label | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
date | Date Completed:
checkpoint | 2.3 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | REFERENCE DOCUMENTS: AS 3610
label | METHOD: Site Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.4 - Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
label | REFERENCE DOCUMENTS: AS/NZS 4671
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.5 - Temporary Drainage Provisions
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.6 - Bedding
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
label | ○ Bedding trimmed, moistened, and compacted as necessary
label | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
label | METHOD: Site Inspection/ Document Review
label | RECORD: Signed ITP
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.7 - Concrete Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
label | ○ Comply with requirements of AS1379
label | ○ Aggregates to comply with Table 703.051
label | ○ Extrusion machines cement content ≥ 320kg/m3
label | ○ Surface pitting < 5mm diameter
label | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
label | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
label | METHOD: Visual Inspection
label | RECORD: Signed ITP & Test Reports
label | IHP/AP/TP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
date | Date Completed:
checkpoint | 2.8 - Finish Surfaces
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
label | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
label | METHOD: Visual Inspection
label | RECORD: Signed ITP & Test Reports
label | IHP/AP
label | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | Date Completed:
checkpoint | 2.9 - Tolerances
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
label | Section dimensions:
label | ○ Within 5mm and 15mm for width; and
label | ○ Within ±3mm for dimensions less than 25mm.
label | Concrete footpath:
label | ○ 150mm thick
label | ○ SL72 reinforcement
label | Concrete Surfacing:
label | ○ Type 1 100mm
label | ○ Type 2 150mm
label | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.10 - Joints
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
label | ○ Expansion joints at 12.5m regular intervals
label | ○ Control joints at 2.5m regular intervals
label | ○ 20mm deep and 5mm wide
label | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 2.11 - Backﬁlling
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
label | ○ Width ≥ 300mm behind edging to top of edging
label | ○ Topsoil placed after 3 days of concrete placement
label | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP