## ITP Cover Page
Northern Access Road & Car Park SW
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-011- 001 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | SP2-011- 001
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Northern access & Car park Stormwater |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STW 0112,0211,212,213,214,402,403,404,405,408,412,416,417 421,422,423,424
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | SM031 project specifications 21.1- 21.7.8
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-02-12 |  | Cordelia Girdler-Brown and Nick Adams |  | 1. Acceptance criteria 3.34 HS2-03*D change to HS2-100mm if D<1500 or 150mm if D>1500 2. Acceptance criteria 3.35 & 3.3.6 HS2-100mm if D<1500 or 150mm if D>1500 change to HS2-03*D |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved | 2024-12-18 |  | Cordelia Girdler-Brown and Nick Adams | [5 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS | [5 empty] | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 2024-02-12 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Northern Access Road & Car Park SW
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-011- 001 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.1 | GENERAL
1.1.1 | Extent of Line Setout | Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings. Identify any clashes before construction. Lot - Markup | As Per Drawings & Markup drawing | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drawings/Data. | M | SE
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.1 | MATERIAL TESTING AP65
2.1.1 | Material grading: Materials (Gap65/AP65) | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | No Particles >200mm Maximum fines 10% passing 75micron sieve | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
2.1.2 | Weathering index: Materials (Gap65/AP65) | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, or CA | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.1.3 | Crushing Resistance: Materials (Gap65/AP65) | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.2 | MATERIAL TESTING AP20
2.2.1 | Material grading: Materials (GAP20/AP20) | Bedding/Side Zone/ Overlay Zone/Embedment Zone | Sieve Size % Passing 19.0mm 100% passing 13.2mm 80-95% passing 9.5mm 64-76% passing 4.75mm 37-58% passing 2.36mm 30-40% passing 1.18mm 18-28% passing 0.600mm 12-22% passing 0.300mm 6-14% passing 0.150mm 2-7% passing 0.075mm 0-3% passing | PS-21.5.7 PS-21.7.2 Table 21.2 | Lab Test Report NZS 4407.2015 Test3.8.1 | 0-400m3 2 Test 400-1500m3 3 Test 1500-4000m3 4 Test >4000 1 Test Additional 1000m3 | HP | ENG
2.2.2 | Weathering index: Materials (AP20) | Bedding/Side Zone/ Overlay Zone/Embedment Zone | AA to CA | PS-21.5.7 PS-21.7.2 Table 21.3 | Lab Test Report NZS 4407.3.11 | Prior to construction - 2 test per source | HP | ENG
2.2.3 | Crushing Resistance: Materials (AP20) | Bedding/Side Zone/ Overlay Zone/Embedment Zone | >100kN | PS-21.5.7 PS-21.7.2 Table 21.4 | Lab Test Report NZS 4407:1991 Test.3.10 | Prior to construction - 2 test per source | HP | ENG
2.3 | MATERIAL DELIVERY
2.3.1 | Pipe and fittings. (Concrete pipe). | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | PS- 21.5.1 PS- 21.5.2 | Delivery Dockets | Each Delivery to site | H | SE
2.3.2 | Stormwater- Structure (SWMH, SDMH, GMH, CP, DCP, CPMH, MP, HW) | Confirm diameter, class & jointing type as shown on the drawings, and that the Structure are correct and in good condition. | Confirm diameter and size as shown on the drawings, and that the Structure are correct and in good condition. | PS- 21.5.4 NZS 3109:1997 | Delivery Dockets | Each Delivery to site | H | SE
2.3.3 | Granular Material (GAP20/AP20, GAP65/AP65) | Confirm Specification and material in good condition. | Confirm Specification and material in good condition. | PS-21.7.2 | Delivery Dockets | Each Delivery to site | H | SE
2.3.4 | Geotextile/Geogrid | TNZ F/7geotextile is to be used in Trench Backfill of Drainage pipe in Wet conditions. | Minimum Strength Class C & Filter Class 1 | PS-21.5.9 | Delivery Dockets | Each Delivery to site | H | SE
SECTION 3 – CONSTRUCTION ACTIVITY
3.1 | STORMWATER MANHOLE INSTALLATION
3.1.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | Appendix V Table 21:11 | Shear vane or Scala test result | 1 Test/Manhole | W | SE
3.1.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 21.5 | Lab Test Report | If Undercut required | HP | ENG
3.1.3 | Undercut Backfill Compliance AP65 | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | PS- 16.5.12 | Lab Test Report | 1 Test per Undercut | H | SE
3.1.4 | Bedding Compaction Testing AP65 | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | PS- 16.5.12 PS- 21.6.11 | Lab Test Report | 1 Test/Manhole | H | SE
3.1.5 | Survey | Inspection of Structure | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm. | PS- 21.7.6 | Survey Data | 1 Test/Manhole | H | SV
3.1.6 | Sidefill Compaction Testing | From the bedding layer to the overlay layer of pipe. | AP20/GAP20 Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal. OR GAP20-Clegg12% CIV | PS- Table 21.12 | Lab Test Report | 4 Density test per layer at Quarter Points around the Structure. | H | SE
3.1.7 | Backfill Compaction Testing | From Overlay layer to the subgrade layer | AP65 Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal. AP65-Clegg28%CIV | PS- 16.5.12 | Lab Test Report | 4 Density test per layer at Quarter Points around the Structure. | H | SE
3.1.8 | Inspection | Inspection of Structure | Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure. | PS- 21.6.11 | Manhole/Catchpit Record | 1 Checksheet per manhole/catchpit | I | SE
3.3 | STORMATER STEEL REINFORCED CONCRETE PIPELINE CONSTRUCTION
3.3.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | Appendix V Table 21:11 | Shear vane or Scala test result | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | W | ENG
3.3.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 21.5 | Lab Test Report | If Undercut required | HP | ENG
3.3.3 | Undercut Backfill Compliance (GAP65/AP65/LRAP65) | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | PS- 16.5.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | H | SE
3.3.4 | Bedding Compaction Testing | On Granular Material | HS2- 100mm if D<1500 or 150mm if D>1500 Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal. Or Clegg 12% CIV | PS- Table 21.6 PS- Table 21.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | H | SE
3.3.5 | Haunch Zone Compaction Testing | On Granular Material | HS2- 0.3xD (outer dia of the pipe) Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal. Or Clegg 12% CIV | PS- Table 21.6 PS- Table 21.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | H | SE
3.3.6 | Side Zone Compaction Testing | On Granular Material | HS2- 0.3xD (outer dia of the pipe) Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal. Or Clegg 12% CIV | PS- Table 21.6 PS- Table 21.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | H | SE
3.3.7 | Survey | Surveyor to Setout | Vertical design Setout: Pipes ≤ 1% grade: +/- 10mm variance Pipes > 1% grade: +/- 20mm variance Horizontal design Setout: +/-30mm variance | PS- 21.7.6 Table 21.15 | Survey Data | Every 100m or at Chambers (whichever distance is the lesser) | H | SV
3.3.8 | Overlay Zone Compaction Testing | On Granular Material | Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal. Or Clegg 12% CIV | PS- Table 21.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | H | SE
3.3.9 | Backfill Compaction Testing | On Granular or Cohesive Material | AP65 Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal. OR Clegg 28% CIV | PS- 16.5.12 | Lab Test Report | One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. 0-5m: 1 Tests 0m-10m: 2 Tests 0m-20m: 3 Tests 0m-50m: 4 Test | H | SE
3.3.10 | Inspection | Inspection of Drainage line | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | PS- 21.7.6 | Drainage line record | Continious 1 per Line | I | SE
3.5 | CCTV
3.5.1 | CCTV Inspection | CCTV stormwater pipes at completion of trench backfill but prior to final surfacing (pavements, etc.) | Every stormwater pipeline 225mm diameter or greater. | PS- 21.7.6 PS- 21.7.8 | CCTV Report | 1 per line | S | SE
SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4.1 | AS-BUILTS
4.1.1 | As-Builts / Redpen markups | Quality Check on New Works based on the tolerances in RITS | Meets spec and thickness requirements as per drawings | Project Specifications | Red pen markup only | Post works completion of a lot | H | SE