## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-011-001 ITP Northern Access Road & Car Park SW | itp |  |  |  |  | DN1210-SP2-011-001 ITP Northern Access Road & Car Park SW Rev 1
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.1.1 - Extent of Line Setout
label | Detail - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings.
label | ○ Identify any clashes before construction.
label | ○ Lot - Markup
label | Acceptance / Conformance Criteria - As Per Drawings & Markup drawing
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction & Every Revision of IFC Drawings/Data.
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.1.1 - Material grading: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - No Particles >200mm
label | ○ Maximum fines 10% passing 75micron sieve
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.2 - Weathering index: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.3 - Crushing Resistance: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.1 - Material grading: Materials (GAP20/AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 19.0mm ¦¦ 100% passing
label | 13.2mm ¦¦ 80-95% passing
label | 9.5mm ¦¦ 64-76% passing
label | 4.75mm ¦¦ 37-58% passing
label | 2.36mm ¦¦ 30-40% passing
label | 1.18mm ¦¦ 18-28% passing
label | 0.600mm ¦¦ 12-22% passing
label | 0.300mm ¦¦ 6-14% passing
label | 0.150mm ¦¦ 2-7% passing
label | 0.075mm ¦¦ 0-3% passing
label | Standard / Specification - PS-21.5.7, PS-21.7.2, Table 21.2
label | Verifying Document - Lab Test Report, NZS 4407.2015, Test3.8.1
label | Testing Quantity Required (based from schedule qtys) - 0-400m3 ¦¦ 2 Test
label | 400-1500m3 ¦¦ 3 Test
label | 1500-4000m3 ¦¦ 4 Test
label | >4000 ¦¦ 1 Test Additional 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.2 - Weathering index: Materials (AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - PS-21.5.7, PS-21.7.2, Table 21.3
label | Verifying Document - Lab Test Report, NZS 4407.3.11
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.3 - Crushing Resistance: Materials (AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - >100kN
label | Standard / Specification - PS-21.5.7, PS-21.7.2, Table 21.4
label | Verifying Document - Lab Test Report, NZS 4407:1991, Test.3.10
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.1 - Pipe and fittings (Concrete pipe)
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Acceptance / Conformance Criteria - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Standard / Specification - PS- 21.5.1, PS- 21.5.2
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 2.3.2 - Stormwater - Structure (SWMH, SDMH, GMH, CP, DCP, CPMH, MP, HW)
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the Structure are correct and in good condition.
label | Acceptance / Conformance Criteria - Confirm diameter and size as shown on the drawings, and that the Structure are correct and in good condition.
label | Standard / Specification - PS- 21.5.4, NZS 3109:1997
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 2.3.3 - Granular Material (GAP20/AP20, GAP65/AP65)
label | Detail - Confirm Specification and material in good condition.
label | Acceptance / Conformance Criteria - Confirm Specification and material in good condition.
label | Standard / Specification - PS-21.7.2
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 2.3.4 - Geotextile/Geogrid
label | Detail - TNZ F/7geotextile is to be used in Trench Backfill of Drainage pipe in Wet conditions.
label | Acceptance / Conformance Criteria - Minimum Strength Class C & Filter Class 1
label | Standard / Specification - PS-21.5.9
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.1.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - Appendix V, Table 21:11
label | Verifying Document - Shear vane or Scala test result
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 21.5
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Undercut Backfill Compliance AP65
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Undercut
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.4 - Bedding Compaction Testing AP65
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12, PS- 21.6.11
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.5 - Survey
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm.
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.1.6 - Sidefill Compaction Testing
label | Detail - From the bedding layer to the overlay layer of pipe.
label | Acceptance / Conformance Criteria - AP20/GAP20
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | OR
label | ○ GAP20-Clegg12% CIV
label | Standard / Specification - PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 4 Density test per layer at Quarter Points around the Structure.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.7 - Backfill Compaction Testing
label | Detail - From Overlay layer to the subgrade layer
label | Acceptance / Conformance Criteria - AP65
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | ○ AP65-Clegg28%CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 4 Density test per layer at Quarter Points around the Structure.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.8 - Inspection
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure.
label | Standard / Specification - PS- 21.6.11
label | Verifying Document - Manhole/Catchpit Record
label | Testing Quantity Required (based from schedule qtys) - 1 Checksheet per manhole/catchpit
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - Appendix V, Table 21:11
label | Verifying Document - Shear vane or Scala test result
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 3.3.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 21.5
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.4 - Bedding Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 100mm if D<1500 or 150mm if D>1500
label | ○ Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.5 - Haunch Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 0.3xD (outer dia of the pipe)
label | ○ Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.6 - Side Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 0.3xD (outer dia of the pipe)
label | ○ Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.7 - Survey
label | Detail - Surveyor to Setout
label | Acceptance / Conformance Criteria - Vertical design Setout:
label | ○ Pipes ≤ 1% grade: +/- 10mm variance
label | ○ Pipes > 1% grade: +/- 20mm variance
label | Horizontal design Setout:
label | ○ +/-30mm variance
label | Standard / Specification - PS- 21.7.6, Table 21.15
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Every 100m or at Chambers (whichever distance is the lesser)
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.3.8 - Overlay Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.9 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - AP65
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | OR
label | ○ Clegg 28% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.10 - Inspection
label | Detail - Inspection of Drainage line
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Drainage line record
label | Testing Quantity Required (based from schedule qtys) - Continious 1 per Line
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.5.1 - CCTV Inspection
label | Detail - CCTV stormwater pipes at completion of trench backfill but prior to final surfacing (pavements, etc.)
label | Acceptance / Conformance Criteria - Every stormwater pipeline 225mm diameter or greater.
label | Standard / Specification - PS- 21.7.6, PS- 21.7.8
label | Verifying Document - CCTV Report
label | Testing Quantity Required (based from schedule qtys) - 1 per line
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.1.1 - As-Builts / Redpen markups
label | Detail - Quality Check on New Works based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - Project Specifications
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature