## Structure (digital map)
First Click/Main area | Second click/Sub area | Checklist Required
Prestart Inspections
| Splashback - JU02 | QA - Splashback Installation
| Splashback - JU13 | QA -Splashback Installation
| Planter - JU13 | QA- Planter box Tiling Installation

## checklists
type | Henkel - 2 Allens Road
checklist | Prestart Inspections
checkpoint | site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Has prior trades QA been signed off by main contractor
checkpoint | Gib compound and sanding cleaned up from rooms
checkpoint | Task Analysis signed onto by tilers and provided to main contractor
checkpoint | Inductions completed
checkpoint | Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current sitesafe - Input number and expiry
checkpoint | Tiler has correct PPE
checkpoint | Correct drawings supplied as per onsite
Checklist | QA - Splashback Installation
section | Splashback Installation
checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Splashback Tiles set out as per drawings
checkpoint | Tiles to walls
checkpoint | Tiling is completed, checked and supervisor to sign onn
checkpoint | siicone nominated is the correct colour and applied evenly and correctly
checkpoint | correct tiles trim is supplied and installed as per drawings
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
Checklist | QA - Planter Box Tiling Installation
section | Planter Box
checkpoint | substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Tiles to planter box
checkpoint | mitre corners completed
checkpoint | Tiling is completed, checked and supervisor to sign onn
checkpoint | siicone nominated is the correct colour and applied evenly and correctly
checkpoint | correct tiles trim is supplied and installed as per drawings (powdercoated)
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed