## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
Scope
Rows
|  | Site QA | dynamic | TAL - Henkel - 2 Allens Road
Columns
|  | Site has been cleaned in advance of our arrival on site |  | Site has been cleaned in advance of our arrival on site
|  | Walls are plumb & level |  | Walls are plumb and level
|  | Tiling works running to programme - prior trades completed |  | Tiling works running to programme - prior trades completed
|  | Has prior trades QA been signed off by main contractor |  | Has prior trades QA been signed off by main contractor
|  | Gib compound & sanding cleaned up from rooms |  | Gib compound and sanding cleaned up from rooms
|  | Task Analysis signed onto by tilers & provided to main contractor |  | Task Analysis signed onto by tilers and provided to main contractor
|  | Inductions completed |  | Inductions completed
|  | Site Inspection checklist has been completed |  | Site Inspection checklist has been completed
|  | All tools tagged & tested |  | All tools tagged and tested - (photo's required)
|  | Tiler has current sitesafe |  | Tiler has current sitesafe - Input number and expiry
|  | Tiler has correct PPE |  | Tiler has correct PPE
|  | Correct drawings supplied as per onsite |  | Correct drawings supplied as per onsite
|  | Wall substrate straight, signed off by MC, & ready for installation |  | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
|  | Splashback Tiles set out as per drawings |  | Splashback Tiles set out as per drawings
|  | Tiles to walls |  | Tiles to walls
|  | Tiling is completed, checked & supervisor to sign onn |  | Tiling is completed, checked and supervisor to sign onn
|  | Siicone nominated is the correct colour & applied evenly & correctly |  | Siicone nominated is the correct colour and applied evenly and correctly
|  | Correct tiles trim is supplied & installed as per drawings |  | Correct tiles trim is supplied and installed as per drawings
|  | Area left clean & tidy |  | Area left clean & tidy
|  | Builders clean completed |  | Builders clean completed
|  | Substrate straight, signed off by MC, & ready for installation |  | Substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
|  | Tiles to planter box |  | Tiles to planter box
|  | Mitre corners completed |  | Mitre corners completed
|  | Correct tiles trim is supplied & installed as per drawings (powdercoated) |  | Correct tiles trim is supplied and installed as per drawings (powdercoated)