## GT4-ITP-014 Electrical
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # GT4-ITP-014
[11 empty] | Revision : 0 | Date: 08/08/2023
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Electrical Works |  | Name: | Susan Smith | Name: | Bruno Vasquez |  | Name:
Contract No: |  | MER-EW-001 |  | Specifications: TDESTD AS/NZS 300
|  |  |  | Structure / Component: Electrical and Communications Cable |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 2023-08-09 | Date : |  |  | Date :
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | QAV | Fulton Hogan | Date
1 | Preliminary Works
1.1 | Define physical bounds of a lot |  | Prior to Commencing Work | Maximum lot size = Single run to the location of field equipoment. Multiple cables can be included in the lot | Lot Map |  | Lot map | HP* | Site Engineer | N/A
1.2 | Site Access available |  | Prior to Commencing Work | Confirm Site access to area with Supervisors. Confirm all safety procedures including car and pedestrian barriers are in place - as required. | current safety requirements of the site | Site inspection | photos | HP* | Site Engineer | N/A
1.3 | Underlying lot(s) conform |  | Prior to Commencing Work | Contractor to verify all underlying lots are closed, or lots open but acceptable to proceed with work. Confirm "Service Trenching & Install CTN-ITP-003" has been completed and signed off. | "Service Trenching & Install CTN-ITP-003" | Site inspection | Previous related ITP completed and signed off | HP* | Site Engineer | N/A
1.4 | Ensure current Termination drawing revisions and cable schedules are available |  | Prior to Commencing Work | Identify and use latest drawing revisions. | latest relevent drawings | Document review & Site inspection | list drawings and version | HP* | Site Engineer | N/A
2 | Subcontractor ITP
2.1 | Receive completed FLE ITP SS107 - Fence and gate installation |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.2 | Receive completed FLE ITP SS108 - Internal road |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.3 | Receive completed FLE ITP SS109 - switchyard surfacing |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.4 | Receive completed FLE ITP SS110 - stormwater Pipe Installation |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.5 | Receive completed FLE ITP SS200 - structural Steel Installation |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.6 | Receive completed FLE ITP SS301- Substation Earth Grid Inspection Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.7 | Receive completed FLE ITP SS302- Current and Voltage Transformer Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.8 | Receive completed FLE ITP SS303- Isolator and Earth Switch Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.9 | Receive completed FLE ITP SS304- Circuit Breaker Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.1 | Receive completed FLE ITP SS305- Post Insulator Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.11 | Receive completed FLE ITP SS306- Bus Bar and Clamps Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.12 | Receive completed FLE ITP SS307- Control Panel Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.13 | Receive completed FLE ITP SS308- Lighting Mast Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.14 | Receive completed FLE ITP SS309- Low Voltage Cable Termination Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.15 | Receive completed FLE ITP SS310- Ductor Test Results (Insulation resistance DLA/DDF) |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.16 | Receive completed FLE ITP SS311- Marshalling Box Installation Checklist |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.17 | Receive completed FLE ITP SS312- HV Cable termination |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.18 | Receive completed FLE ITP SS313- Light and Power in Substation Building |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
2.19 | Receive completed FLE ITP SS314- Field Cable Installation |  | Per ITP | ITP per lot package satisfactorily completed | Signed and completed ITP | verify to TDESTD AS/NZS 300 | Signed ITP | HP* | site engineer | N/A
3 | Final Inspection
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | WP* | Fulton Hogan Witness Point |  | An inspection which must be witnessed by Fulton Hogan Representative