## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-014 - Electrical Works | itp |  |  |  | Yes | GT4-ITP-014 - Electrical Works
section | 1 - Preliminary Works
checkpoint | 1.1 - Define physical bounds of a lot
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Maximum lot size = Single run to the location of field equipoment. Multiple cables can be included in the lot
label | Reference Documents: Lot Map
label | Record of conformity: Lot map
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.2 - Site Access available
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Confirm Site access to area with Supervisors. Confirm all safety procedures including car and pedestrian barriers are in place - as required.
label | Reference Documents: Current safety requirements of the site
label | Inspection / Test Method: Site inspection
label | Record of conformity: Photos
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.3 - Underlying lot(s) conform
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Contractor to verify all underlying lots are closed, or lots open but acceptable to proceed with work. Confirm "Service Trenching & Install CTN-ITP-003" has been completed and signed off.
label | Reference Documents: "Service Trenching & Install CTN-ITP-003"
label | Inspection / Test Method: Site inspection
label | Record of conformity: Previous related ITP completed and signed off
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.4 - Ensure current Termination drawing revisions and cable schedules are available
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Identify and use latest drawing revisions.
label | Reference Documents: latest relevent drawings
label | Inspection / Test Method: Document review & Site inspection
label | Record of conformity: List drawings and version
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Subcontractor ITP
checkpoint | 2.1 - Receive completed FLE ITP SS107 - Fence and gate installation
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.2 - Receive completed FLE ITP SS108 - Internal road
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Receive completed FLE ITP SS109 - Switchyard Surfacing
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.4 - Receive completed FLE ITP SS110 - Stormwater Pipe Installation
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.5 - Receive completed FLE ITP SS200 - Structural Steel Installation
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.6 - Receive completed FLE ITP SS301- Substation Earth Grid Inspection Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.7 - Receive completed FLE ITP SS302 - Current and Voltage Transformer Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.8 - Receive completed FLE ITP SS303 - Isolator and Earth Switch Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.9 - Receive completed FLE ITP SS304 - Circuit Breaker Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.10 - Receive completed FLE ITP SS305 - Post Insulator Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.11 - Receive completed FLE ITP SS306 - Bus Bar and Clamps Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.12 - Receive completed FLE ITP SS307 - Control Panel Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.13 - Receive completed FLE ITP SS308 - Lighting Mast Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.14 - Receive completed FLE ITP SS309 - Low Voltage Cable Termination Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.15 - Receive completed FLE ITP SS310 - Ductor Test Results (Insulation resistance DLA/DDF)
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.16 - Receive completed FLE ITP SS311 - Marshalling Box Installation Checklist
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.17 - Receive completed FLE ITP SS312 - HV Cable termination
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.18 - Receive completed FLE ITP SS313 - Light and Power in Substation Building
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.19 - Receive completed FLE ITP SS314 - Field Cable Installation
label | Frequency: Per ITP
label | Acceptance Criteria: ITP per lot package satisfactorily completed
label | Reference Documents: Signed and completed ITP
label | Inspection / Test Method: Verify to TDESTD AS/NZS 300
label | Record of conformity: Signed ITP
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
section | 3 - Final Inspection
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP