## Breakdown
Contract Construction - Kevin Hickman | [5 empty] | CHECKLIST
Stage 8 - B04
Site QA
Basement
Lift
|  |  |  | Lift Pit base |  | ST - S - Insitu Stitch Joints
|  |  |  | Lift Pit walls |  | ST - S - Insitu Stitch Joints
Floor Slab - Area A
|  |  |  | Site Concrete |  | ST - S - Concrete Pour - Without Reo
|  |  |  | Floor slab Pour |  | ST - S - Concrete Pour
Floor Slab - Area B
|  |  |  | Site Concrete |  | ST - S - Concrete Pour - Without Reo
|  |  |  | Floor slab Pour |  | ST - S - Concrete Pour
Precast Components (Panels/ Stairs/ Precast Beams/Flat slabs)
Check Panel Starters against Panel shop drawings
[5 empty] | Area A | ST - S - Panel Starter bars Installation
[5 empty] | Area B | ST - S - Panel Starter bars Installation
Precast Wall Panel Placement
[5 empty] | Area A | ST - S - Precast Wall Panel Installation
[5 empty] | Area B | ST - S - Precast Wall Panel Installation
Precast Beams Installation
[5 empty] | Area A | ST - S - Precast Beam Installation
[5 empty] | Area B | ST - S - Precast Beam Installation
Insitu Beams Installation
[5 empty] | Area A | ST - S - Insitu Beams Installation
[5 empty] | Area B | ST - S - Insitu Beams Installation
Precast Stair Installation
[5 empty] | Area A | ST - S - Stair Installation
[5 empty] | Area B | ST - S - Stair Installation
Insitu Stitch Joints
|  |  |  | Area A |  | ST - S - Insitu Stitch Joints
|  |  |  | Area B |  | ST - S - Insitu Stitch Joints
Insitu Stitch Columns
|  |  |  | Area A |  | ST - S - Insitu Stitch Joints
|  |  |  | Area B |  | ST - S - Insitu Stitch Joints
Ground Floor
|  |  | Precast Flooring - Area A | Precast Flat Slab Installation |  | ST - S - Precast Flat Slab Installation
|  |  | Precast Flooring - Area B | Precast Flat Slab Installation |  | ST - S - Precast Flat Slab Installation
|  |  | Floor Slab - Area A | Floor slab Pour |  | ST - S - Concrete Pour
|  |  | Floor Slab - Area B | Floor slab Pour |  | ST - S - Concrete Pour
| Compliance Documentation |  |  |  |  | CST - S - Completion Documents

## Checklist
type | name | values
checklist | ST - S - Insitu Stitch Joints
section | Pour Details
checkpoint | Pour Details:
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork
checkpoint | Formwork braced & fixed correctly
checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
section | Reinforcing
checkpoint | Size and type correct to specification
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
signoff | Raise remedial / Request Signoff
checkpoint | All relevant inspections completed and attached
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
button | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
signoff | Raise remedial / Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
type | name | values
checklist | ST - S - Concrete Pour - Without Reo
section | Pour Details
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Pre-Pour Completion (Approval to pour)
checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
button | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
signoff | Raise remedial/ Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
type | name | values
checklist | ST - S - Concrete Pour
section | Pour Details
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Reinforcing
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
text | Supplier Name:
text | Specified concrete strength: | mPA
text | Concrete strength ordered: | mPA
text | Concrete quantity ordered: | m3
button | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
signoff | Raise remedial/ Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
type | name | values
checklist | ST - S - Precast Wall Panel Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint | Installed in correct location
checkpoint | Adequately braced and Braces to be tagged
checkpoint | Grout sleeves correctly grouted
checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
type | name | values
checklist | ST - S - Rib & Infill Installation
section | Pre-commencement
checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint | Grid set-out offset and level correct
checkpoint | Props tagged and fixings as per approved temp works design and temp work approval report attached
checkpoint | All back propping completed, checked and approved as per design
checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
section | Installation
checkpoint | All grids ready for rib installation
checkpoint | All Ribs placed, locations, heights and orientation approved. No damage during install and approval given to install planks
checkpoint | All planks installed correctly (adequate seating etc)
checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (NO GAPS)
checkpoint | Rib & Infill Installation completed correctly (checked location & level) and damage free
type | name | values
checklist | ST - S - Panel Starter bars Installation
checkpoint | Correct drawings referenced and attached
checkpoint | Size and type correct to specificaion
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/ correct
checkpoint | Any additional items installed/ completed (trimmer bars etc.) and excess reinforcing removed
checkpoint | Panel starter bars installed correctly to specifications (location, size, length and apacing) and ready to place the precast panels
type | name | values
checklist | ST - S - Precast Beam Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced and braces are tagged
checkpoint | Precast Beam Installation completed (checked location & level) and no damages
type | name | values
checklist | ST - S - Precast Flat Slab Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced and braces are tagged
checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
type | name | values
checklist | ST - S - Insitu Beams Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced and braces are tagged
checkpoint | Insitu Beams Installation completed (checked location & level) and no damages
type | name | values
checklist | ST - S - Stair Installation
checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint | Grid Set-out offset and level correct
checkpoint | Joints scabbled and acceptable
checkpoint | All setout completed correctly and approved
checkpoint | Temporary support installed and approved
checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
Checklist | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any additional Compliance Documentation (Required under Section C and by consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Sign off