## Master List Templates
Id | Type | Name | Values | Prompting Name
a2a4b8fc-6bfa-596d-a522-b315c0f53c72 | checklist | Add Aluminium Panel Installation Checklist |  | Aluminium Panel -
f5dbbb23-690a-56b7-a918-4f231d98d11c | checkpoint | Wall is waterproofed and hand-over
72a84c6f-d464-5a8a-8dd8-de13ad94e530 | checkpoint | Rail is installed according to panel lay out
601b091f-4377-5088-a46a-3a2f2dc0a78f | checkpoint | Panel install plumb and rigth gap
ea700108-eb08-5978-b7ea-46c5d70746b1 | checkpoint | Gap/joint is sealed
84c3f4af-6948-5640-8a67-e5966d818473 | checkpoint | Defects fixed
ad390dad-a7b1-566c-ace8-81e7000fd2b5 | checkpoint | Trade cleaned
c204f5ef-8ab4-51c2-bfbc-0506306c8769 | checklist | Add Ballustrade Installation Checklist |  | Ballustrade -
732e3a32-1f12-51bb-b8fd-eee4bb0da460 | checkpoint | Waterproofed opening hand-over
3662a2ee-3a47-5418-8e00-b080b07dceb6 | checkpoint | Channel/Chem set-out
2f70ac11-f967-5c96-af53-3da4d2f2a928 | checkpoint | Glazing
67f7eec4-0f33-5467-a49d-732776aac76f | checkpoint | Top rail flashing
f5e55e01-d110-5cf6-8361-cb7d3c3e0db2 | checkpoint | Aluminium capping
87a93059-6816-5f72-b9b5-939b7e4e1eb6 | checkpoint | Seal/Trade clean
d6dc6da6-fa10-57c9-bced-07707ce59260 | checklist | Add Consolidation and Packing Checklist |  | Consolidation and Packing Checklist
4c3c7a21-9e30-55ad-8273-88dde886213c | checkpoint-no-value | Collate manufactured product and package as specified in the Logistics Plan. After closing each case attach a "Contents Schedule" and verify the following as a part of the QA Process
830009c7-68d1-55fc-8477-134f2e6f1543 | checkpoint | Confirm the case is clearly labelled and has "Contents" schedule attached. The contents schedule should identify each product individually to ensure we have full traceability of product
1dcd698f-d077-5beb-adfe-b1d88cccc995 | checkpoint | Confirm the product inside the case has adequate protection to avoid transit damage
5075f3ce-ce07-57aa-a93f-b1f72f94ed49 | checkpoint | Confirm the case is sturdy and will not rack or twist during shipping and movement
59094317-69cf-52cc-a895-ff89cc2fbf44 | checkpoint | Confirm the case is loaded safely and securely inside the shipping container
6b00f3fd-1813-515c-9808-6685344fdffa | checklist | Add Curtain Wall Checklist |  | Curtain Wall QA -
b096d6b0-3c70-589d-96b9-61f47613deda | section | Pre Install QA
eb49fe76-a28b-5a5d-aed8-63eb29aae142 | checkpoint | Opening acceptable and ready for Curtain Wall
ed92aa26-4977-4926-96e8-06d43c428e58 | tickbox | Position of opening relative to grid line
e579dcf9-f116-43f8-b7f4-329342c97202 | tickbox | Height of opening relative to RL
6a6bcbbd-94f5-472a-8b18-226b7481e1d2 | tickbox | Timber sub-frame fully complete
62c675bf-cc5d-4d45-abb7-26ab58aa7ccf | tickbox | All waterproofing elements & flashing tape completed
a8904bc2-28d7-5f16-bd13-bbd4e28468c3 | section | Curtain Wall Install QA
84b04afb-e701-5b94-b924-35a23ab3a70d | checkpoint | All materials are free from damage / exposed aluminium surfaces are covered with protective tape
be9b248d-f5b4-5b1e-b83c-e45b1ba914e5 | checkpoint | Welds cleaned and protective paint applied
026ba4ed-1925-5551-8be9-e9b5a6f40b1b | checkpoint | Brackets lined, leveled and at correct height
745eb5cd-3871-58f4-9cb7-be55d2a55b57 | checkpoint | Packing does not exceed 20mm / packers correctly seated
d4856487-62af-5709-8f8d-2f7ca60e3442 | checkpoint | Panel brackets fully engaged on PFC slab brackets
0ae7c8fb-e48e-5a6e-8cc1-6dbd4694b477 | checkpoint | Panels lines, leveled and at correct height
713bb19d-faf6-5af7-a990-0cda76176629 | checkpoint | Vertical and horizontal panel joint widths correct
df4e44d4-e0b8-5097-8904-bcb5d2904fcf | checkpoint | Soakers correctly positioned, fully sealed and neatly tooled
168846ec-453f-5004-8c18-b1ab19b320b0 | checkpoint | Slab edge smoke stop brackets correctly installed
f65765de-4fcf-5718-aa39-d38e305c78df | checkpoint | Fire safe Rockwool installed and compressed by 25%
ba2a8dea-895a-5e04-b13f-90f43760e81b | checkpoint | Sills lined, leveled and at correct height
b0afad4d-f6bd-5604-b37f-386febd20ab2 | section | Post Install & Handover
999fa7c7-fa92-5543-8fc2-bf6feb6f0f8a | checkpoint | Protective tapes and label removed
e5deae3d-7787-5935-bc60-8522fa1dae26 | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
240e8f34-e361-5ffa-a44a-13db26f7d30c | checkpoint | Glass dry wiped to remove dust and marks
18b2f7f9-32f9-511c-b57a-d67f7153d580 | checkpoint | All surfaces damage free
f38de67d-5387-5de0-89ed-6f57ef63ff11 | checkpoint | Defects review carried out and schedule issued to installation team
12bdd59c-8470-569e-9976-b057d33375c6 | checkpoint | All defect work completed and closed out
4f688fa0-378e-506e-9a1f-ec7dbc047d61 | checkpoint | Final inspection competed & approved
074d88eb-f8fb-50bc-baad-32d1dc3afd31 | checklist | Add Door Install QA |  | Door -
b096d6b0-3c70-589d-96b9-61f47613deda | section | Pre Install QA
d6432546-3207-5459-bfea-edfb7a99c6e1 | checkpoint | Opening Acceptable and ready for door
8899be65-62f8-4754-b8bb-49ac7b511d4d | tickbox | Position of opening relative to grid line
e84fdbbd-c2a6-4552-a2a1-b3320e814c90 | tickbox | Height of opening relative to RL
8c93e877-d4df-4437-9fe8-cbf54805484f | tickbox | Timber sub-frame fully complete
21933b79-503c-43e8-be38-2f61e18551d9 | tickbox | All waterproofing elements & flashing tape completed
cae74d21-640e-5bd6-b2b9-ebcf1bc316b1 | section | Install QA
9c4b6fd0-db9f-5943-ae73-5bec5b714827 | checkpoint | Materials inspected on arrival and damage free
ff5e485f-6051-55bd-985f-5d976f09a642 | checkpoint | Waterproofing membranes correctly seated and fully sealed
016a1fb3-ae60-5095-8e63-3c4b7a68feff | checkpoint | Seismic frame lines, leveled and at correct height
2505b176-fc4f-59e7-bc3c-e649b185e551 | checkpoint | Packing does not exceed 15mm/packers correctly sealed
d0281eca-0d7b-5213-8018-39cbe6070440 | checkpoint | Horizontal and vertical air seals applied/tooled to a smooth, neat finish
1251f13c-3c69-54d8-82d0-7a8016c17744 | checkpoint | Door installed plumb and square within seismic frame
810cd98d-5d69-5b71-aa8d-4bb728b66a7d | checkpoint | Glass toe and healed correctly
0b4e0653-5e77-5e49-bce2-44d3e24cfb7a | checkpoint | Gaskets engaged/corners neatly mitred
520d3553-97f7-5886-bdd5-70803de8edde | checkpoint | Hardware correct installed and functioning
3ca1bde6-583f-5258-a247-722f0137e7d6 | section | Post-Install & Handover
ae7813bc-3126-5ada-ac0a-b0ee5ddc6739 | checkpoint | Protective tapes & labels removed
e5deae3d-7787-5935-bc60-8522fa1dae26 | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
240e8f34-e361-5ffa-a44a-13db26f7d30c | checkpoint | Glass dry wiped to remove dust and marks
18b2f7f9-32f9-511c-b57a-d67f7153d580 | checkpoint | All surfaces damage free
e7f3876d-480e-5bb8-837b-76e4dfc90bc2 | checkpoint | Doors commissioned, hardware functioning correctly
12bdd59c-8470-569e-9976-b057d33375c6 | checkpoint | All defect work completed and closed out
b4b9f31b-3d10-5436-b5e8-1905b11ebac1 | checkpoint | Final inspection completed, reviewed and approved
e8759f69-c7ce-502c-9578-d7583657c6a8 | checklist | Add Receipt of Materials into Fabrication Facility Checklist |  | Receipt of Materials into Fabrication Facility Checklist
d22799a7-8095-5279-a2e6-c3f56009b592 | section | Receipt of Extrusion
3b957f72-1c99-5309-9f77-8c2f1fbe2b92 | checkpoint | Reconcile delivery to order
1953110f-bb85-57ca-8477-111db596e04f | checkpoint | Confirm lengths & dimensions are accurate
12451bf3-3fd8-51e5-9554-6fd1f38291b9 | checkpoint | Confirm extrusion profiles are accurate
39da62f2-5d1a-5943-9dc1-e1e7d303b724 | checkpoint | Confirm no damage or deformation
4bd74330-853f-52cb-8bf9-0d63d32d426b | checkpoint | Confirm surface finish to specification
0d0075f7-c5f6-5fd6-a1af-f015aece97c2 | section | Receipt of Glass
258437c7-579c-5892-a909-e771f609d72f | checkpoint | Reconcile delivery to order checks
0587ccbc-24d3-5310-81e0-39ae9d443629 | checkpoint | Check glass type and thickness
4a345348-e8df-52e7-926b-7b1e2689ae47 | checkpoint | Confirm correct dimensions, holes and any engineering details
14c90a36-2c9e-5eaa-b075-deac0f6b1742 | checkpoint | Visual check of all glass surfaces and edges - damage free
55e2d01c-8a15-5bdc-a1ce-0aa844b4e998 | section | Receipt of Panels
caed6e4e-bffc-42ed-bdf6-ef67baa02b27 | checkpoint | Reconcile delivery to order checks
b164f116-9df4-56c3-9a76-9a2e8aaec5be | checkpoint | Confirm accuracy of dimensions and configuration
109338ac-3ac8-5092-980a-363baa14e384 | checkpoint | Confirm surface finish to specification
7098cdf8-4e12-50eb-b52b-97d0d406af28 | checkpoint | Check surface for damage or scratches
8adbec7f-b029-5bc1-9a7d-3d8e9bcf469d | section | Receipt of Hardware and Fittings
e3e2ae68-55bb-49c1-9730-853bafeadeae | checkpoint | Reconcile delivery to order
643dfa96-b161-54b5-a0fd-c30be1c37dfd | checkpoint | Confirm product is correct to control sample and specification
2ddae513-97f5-538a-a170-b72c306ec0a9 | section | Receipt of Sealant
0943dfd9-7749-42ca-ad0d-7305f31c4a5e | checkpoint | Reconcile delivery to order
4c43c4da-f143-586a-962d-23b36abd1a9e | checkpoint | Confirm product is within shelf life expectations
86ea9799-6680-52e5-905b-81a5b1b421ca | checklist | Add Spandrel QA Checklist |  | Spandrel -
1ff5e525-81c4-5f27-97e4-4a59b3e9a725 | section | Pre-Install QA
13448295-39fd-5027-a9c8-dc8f2293ff9e | checkpoint | Opening acceptable and ready for Spandrel
5823a5d8-86d4-42a0-aea3-03c1ca6746b4 | tickbox | Position of opening relative to grid line
27ed9988-c9e2-44cd-8cb5-cd349416b0b8 | tickbox | Height of opening relative to RL
daaa7dae-e378-4d61-a7b7-a3815743910c | tickbox | Timber sub-frame fully complete
1664f643-d2a0-4d98-9aba-4a8762770138 | tickbox | All waterproofing elements & flashing tape completed
7449874e-b506-52ea-927c-4f89a0df465e | section | Spandrel Install QA
84b04afb-e701-5b94-b924-35a23ab3a70d | checkpoint | All materials are free from damage / exposed aluminium surfaces are covered with protective tape
be9b248d-f5b4-5b1e-b83c-e45b1ba914e5 | checkpoint | Welds cleaned and protective paint applied
026ba4ed-1925-5551-8be9-e9b5a6f40b1b | checkpoint | Brackets lined, leveled and at correct height
01bd721d-6ffc-5963-904f-e607afbda111 | checkpoint | Tie rods lined, leveled and at correct height
745eb5cd-3871-58f4-9cb7-be55d2a55b57 | checkpoint | Packing does not exceed 20mm / packers correctly seated
1667c671-5099-50ab-8c30-b2065801c1f1 | checkpoint | Panel brackets fully engaged on supporting structure
ab8bc810-9fa5-5937-8530-389c1b2e2902 | checkpoint | Panels lined, leveled and at correct height
713bb19d-faf6-5af7-a990-0cda76176629 | checkpoint | Vertical and horizontal panel joint widths correct
df4e44d4-e0b8-5097-8904-bcb5d2904fcf | checkpoint | Soakers correctly positioned, fully sealed and neatly tooled
168846ec-453f-5004-8c18-b1ab19b320b0 | checkpoint | Slab edge smoke stop brackets correctly installed
f65765de-4fcf-5718-aa39-d38e305c78df | checkpoint | Fire safe Rockwool installed and compressed by 25%
3ca1bde6-583f-5258-a247-722f0137e7d6 | section | Post-Install & Handover
cf6cd9ec-d9e5-5459-83c1-f67773c806d8 | checkpoint | Hardware correctly installed and functioning
73fe8e67-3e81-57c0-b0e4-31a3ec05dc5d | checkpoint | Protective tapes & labels
e5deae3d-7787-5935-bc60-8522fa1dae26 | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
240e8f34-e361-5ffa-a44a-13db26f7d30c | checkpoint | Glass dry wiped to remove dust and marks
18b2f7f9-32f9-511c-b57a-d67f7153d580 | checkpoint | All surfaces damage free
e7f3876d-480e-5bb8-837b-76e4dfc90bc2 | checkpoint | Doors commissioned, hardware functioning correctly
12bdd59c-8470-569e-9976-b057d33375c6 | checkpoint | All defect work completed and closed out
b4b9f31b-3d10-5436-b5e8-1905b11ebac1 | checkpoint | Final inspection completed, reviewed and approved
b4a75b5b-866a-5742-bf0b-02b916e7b237 | checklist | Add Transitional Facility and NZ Warehouse Checklist |  | Transitional Facility and NZ Warehouse Checklist
5d3db380-57a0-52b6-b838-176c39fd9fcf | checkpoint-no-value | Receive the shipping containers in NZ and unload, ensuring the following QA Procedures are followed and checked
f70adc64-2130-5bc6-b508-5d9c74c5e7dd | checkpoint | Check that the case is complete and has no visible damage or distortion/breakage
784a2cc0-1155-5c95-b573-6a8b2a2fe043 | checkpoint | Confirm that contents marked on the COntents Schedule are reconciled and logged in as "In Warehouse"
ecf3577c-5b77-5e14-8772-d1eb193b1ace | checkpoint | Unpack and store items appropriately, and carry out a visual check for any transit damage, (rubbing of surfaces etc.)
159e52b8-bcc6-5ea4-8549-d3d3879cc58c | checklist | Add Weekly H&S Checklist |  | H&S Week Starting:
b7d0dee7-466b-5605-a546-e0bb54958c78 | checkpoint | Task Analysis/JSA
fdc4f074-af69-5361-9371-b1d133d6aa19 | checkpoint | Toolbox Minutes
a84f6423-0dab-5305-8174-f63df6ea1a85 | checkpoint | Hot Works Permits/Confined Spaces/Working at heights
d0224e46-6654-59a3-bda5-21697a85d6f9 | checkpoint | Site Safety Inspection Checklists
aea79918-4222-57c5-8e2d-57f32feffef1 | checkpoint | Hazard ID
b28632b0-aa7a-50d0-94be-ff15d347a348 | checkpoint | Accident/Incident/Near Miss Investigation Report
401b396c-6b43-515c-a04f-fd4d0460c668 | checkpoint | Notice/Record of Serious Harm Accident
8f720956-0552-5a22-b456-040b52f8df8a | checkpoint | Additional Heath & Safety Documentation
b179e438-baa8-5369-b467-ec8cd4169f8a | checklist | Add Window Install QA |  | Window -
1ff5e525-81c4-5f27-97e4-4a59b3e9a725 | section | Pre-Install QA
1319bd11-95c6-55f1-8cbd-a86d4603bbb4 | checkpoint | Opening acceptable and ready for window
973f4546-a998-4880-92b8-a7772c54c8af | tickbox | Position of opening relative to grid line
c0cf99a6-180f-4df3-b0b4-dca465726dfc | tickbox | Height of opening relative to RL
c4831ef1-0e90-49f5-980b-9f7fdce052a2 | tickbox | Timber sub-frame fully complete
f352fdd3-321c-4c15-b35c-68f13548ecf7 | tickbox | All waterproofing elements & flashing tape completed
98e5bd8f-20ba-52e9-99bd-830ee93d4603 | section | Window Install QA
84d9ff98-72db-5608-8d90-b02f58db8da3 | checkpoint | Frame delivered on site, checked and damage free
ff5e485f-6051-55bd-985f-5d976f09a642 | checkpoint | Waterproofing membranes correctly seated and fully sealed
7b15c5ee-c55f-5af6-ada3-8720450600fb | checkpoint | Seismic frame lined, leveled and at correct height
c53a1359-02b8-5f95-bf87-41916dfae2d0 | checkpoint | Packing does not exceed 15mm / packers correctly seated
4789e74d-e919-5b5b-84f0-3eeb5a80f732 | checkpoint | Horizontal and vertical air seals applied / tooled to a smooth, neat finish
ce2fcff5-1b83-54fc-8913-8440f20fa239 | checkpoint | Window installed plumb and square within seismic frame
aae80f6e-7cc3-57e5-a17b-8e5e0126f956 | checkpoint | Framing completed checked, correct and approved
48ee6e9e-d1bf-52e9-b2ab-0e3fce635a91 | section | Glazing Install QA
810cd98d-5d69-5b71-aa8d-4bb728b66a7d | checkpoint | Glass toe and healed correctly
d493c02e-ffc4-5986-82dd-350e035953b1 | checkpoint | Gaskets engaged/corner neatly mitred
9f6c8dca-0511-5576-95fa-f6f9be01692f | checkpoint | Glazing completed checked, correct and approved
3ca1bde6-583f-5258-a247-722f0137e7d6 | section | Post-Install & Handover
cf6cd9ec-d9e5-5459-83c1-f67773c806d8 | checkpoint | Hardware correctly installed and functioning
73fe8e67-3e81-57c0-b0e4-31a3ec05dc5d | checkpoint | Protective tapes & labels
e5deae3d-7787-5935-bc60-8522fa1dae26 | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
240e8f34-e361-5ffa-a44a-13db26f7d30c | checkpoint | Glass dry wiped to remove dust and marks
18b2f7f9-32f9-511c-b57a-d67f7153d580 | checkpoint | All surfaces damage free
e7f3876d-480e-5bb8-837b-76e4dfc90bc2 | checkpoint | Doors commissioned, hardware functioning correctly
12bdd59c-8470-569e-9976-b057d33375c6 | checkpoint | All defect work completed and closed out
b4b9f31b-3d10-5436-b5e8-1905b11ebac1 | checkpoint | Final inspection completed, reviewed and approved
8bd5b148-3749-5cc9-9ce5-2077cfeebb72 | checklist | Alum Panels Checklist |  | Alum Panels
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
6a8566ad-2dc5-5803-89ea-1a49878ea119 | section | Alum Panels QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
6fb5fd64-35c2-5ea4-88b7-89a01b556163 | checkpoint | Has waterproof / vapour shield been applied on surface and handed over
1dcd4bfd-520a-5e1e-8a4f-3bbe5e7e4c23 | checkpoint | Is the applied waterproof / vapour shield compatible with silicon
f9973423-5577-5d30-b39d-86c7816fb372 | checkpoint | Grid lines / RL visible and accessible
75419228-b01c-5440-9572-868aa7a3c6aa | checkpoint | Panels / Fins received damaged free from transportation
07ce72e3-3083-5e3a-8685-d5c870bf31fa | checkpoint | Has the omega bracket installed
281b1e53-c4db-5b66-afdc-4557affa8b70 | checkpoint | Has the alum panel Installed and sealed
cfc20872-d123-598a-9038-4e1d062da682 | checkpoint | Has the protection tape been removed
eeba895c-c9b0-567c-bfc7-9e14a23a17d0 | checkpoint | Has the Vertical fins installed to bracket on CW panel
31dcfa09-7847-5ea1-948a-52c991c6b62f | checkpoint | Has all the U channels installed on the vertical fins
e93724be-02da-5438-8362-841a5a46fe3b | checkpoint | Has the Horizontal fin installed
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
bfe8e654-5311-5ca6-bc36-3a92b85e3def | checklist | AWF Handover Checklist |  | AWF Handover
7b24ee9b-431a-5947-8e61-21530e8b99c4 | checkpoint | Has the gutter sill been installed lined and leveled as per approved SD
f4237e4a-89b7-5a70-836d-c786e219c661 | checkpoint | Has the Bracket been Installed lined and leveled as per approved SD
32381a3d-efc1-5e92-ab2b-153b64719a1a | checkpoint | Has the seismic frame been installed lined and leveled as per approved SD
1da2132d-e30a-51ea-9d3b-6484890ed0ed | checkpoint | Has all the jambs been installed and sealed
30a632d2-9b41-5b84-b117-d831968e61fc | checkpoint | Has the CW panels been Installed lined and leveled as per approved SD
2e989096-109d-5931-a787-da473c940060 | checkpoint | Has the BAL panels been Installed lined and leveled as per approved SD
1aea7399-7ec9-54db-9e35-45c59e6ad134 | checkpoint | Has the BLU panels been Installed lined and leveled as per approved SD
f941b9b1-a3da-57be-8896-dba40d090b20 | checkpoint | All end flashing installed with EPDM membrane and sealed
1bec8384-917b-5026-b283-bef3e649d5f9 | checkpoint | Has the rockwool been installed and covered with smoke barrier
459f7bbe-b2f7-5f4e-8f44-38ec8751223b | checkpoint | Has all the bottom window sill been installed.
37212a37-4b2f-54db-bc7c-d2c709b669ca | checkpoint | Has all the protection tapes been removed
c66bde4c-b6ce-5271-a5dd-5660d67abd4b | checkpoint | All the doors and windows handles and locks are working smoothly
50ad2d13-3772-58e4-a858-58f5564dd8f7 | checkpoint | Final handover check sheet issued to Main Contractor with photos
5ed7b8fa-3a1a-5782-bdf3-9b1ad3bea65f | checklist | Balcony Panels Checklist |  | Balcony Panels
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
0d992620-29ea-59a1-8466-5f1f491959d9 | section | Balcony Panels QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
b2e3b29b-dc35-51f4-ac36-936752888453 | checkpoint | Grid lines visible and accessible
0cd3204d-7fb6-526a-a40e-43a8cb916d56 | checkpoint | Panels received damaged free from transportation
4aef7c5c-3523-50ff-a9bf-5d8cec0c8a21 | checkpoint | Panel has all gaskets / Mohair in place and free from wear and tear. No damaged gaskets / Mohair.
2a340e5e-c3a4-522a-bb0a-7db256b8452f | checkpoint | Panel has any missing glass / broken glass
4b1a603e-939b-5609-b5dc-c91af3ddb792 | checkpoint | Has the bracket been installed Line and leveled
2f962726-cec0-546b-aeb6-04db7a595e6d | checkpoint | Has the timber supporting form installed by Main Contractor
884e205f-67e6-5dc2-b5f2-53b774d5d48c | checkpoint | Has the bottom flashing installed and first layer of waterproofing installed
fadc2b8f-4372-541d-81fa-7f19ee26c8ef | checkpoint | Panels installed lined/leveled from GL & RL
4a25b6cf-35c0-592e-a25f-b1d8bf79e0f6 | checkpoint | Has secondary bottom flashing installed above waterproofing
fa53d76f-0789-5d83-b5cd-f54eb5fa25e3 | checkpoint | Has all the top / bottom / side flashing installed and sealed.
68dbb37a-88e3-5752-9b66-e179f6b92657 | checkpoint | Has the BAL-AL panel omega bracket installed and sealed
9eb9f806-d8a3-5a72-810d-48b292141587 | checkpoint | Has the BAL-AL panel Installed and sealed
0d3d9743-8bb5-5346-bbcf-ced8d90146f9 | checkpoint | Has the BLU panel bracket fixed and sealed
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
d2648225-ed40-5f92-9dac-656ca8354f8e | checklist | Balustrade Glass Panels Checklist |  | Balustrade Glass Panels
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
4e00a13e-dc2a-52f5-b94f-5f6bb99a76a4 | section | Balustrade Glass QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
b2e3b29b-dc35-51f4-ac36-936752888453 | checkpoint | Grid lines visible and accessible
9922208f-f209-5175-a133-0dab43ad0829 | checkpoint | Glass received damaged free from transportation
81d5db4b-9282-57ce-9b06-b10959655817 | checkpoint | Has the bracket been installed and all component screwed
fc4dd0b8-0d61-57eb-8181-e9c610967d91 | checkpoint | Are there any missing glass / broken glass
66b949fc-f30f-526d-8d74-5fc1f96fb281 | checkpoint | Glass panels installed lined/leveled from GL & RL
1680f246-8a2a-582d-ad8e-c4c35b4eeba5 | checkpoint | Has the cover flashing (external / internal) been installed
b79ea8df-97b5-59f3-a1d5-2abd1c562575 | checkpoint | Has the capping rail been installed sealed completely.
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
61e1e6e3-af20-5892-9d26-90a3f990ef4d | checklist | Balustrade Panels Checklist |  | Balustrade Panels
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
ceae615a-6514-52b8-b38e-733e433eacca | section | Balustrade QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
b2e3b29b-dc35-51f4-ac36-936752888453 | checkpoint | Grid lines visible and accessible
0cd3204d-7fb6-526a-a40e-43a8cb916d56 | checkpoint | Panels received damaged free from transportation
48827b64-e03b-5928-85f3-d322a3d0ada1 | checkpoint | Panel has all gaskets in place and free from wear and tear. No damaged gaskets.
dcbcc04e-095e-57f5-8392-9081b758f947 | checkpoint | Panel has gutter splice
2a340e5e-c3a4-522a-bb0a-7db256b8452f | checkpoint | Panel has any missing glass / broken glass
88ad493a-6c70-56a8-8364-60406470bba4 | checkpoint | Balcony alum panel installed leveled and sealed
2c648acb-733a-51b7-90de-6d8e12763c2f | checkpoint | Cast-in channel/ bracket installed and inspected.
fadc2b8f-4372-541d-81fa-7f19ee26c8ef | checkpoint | Panels installed lined/leveled from GL & RL
ed753ca1-7979-54e1-9d2c-9b3c01c16d2b | checkpoint | Has the panel alignment screw been installed.
c853173d-65df-50f0-8708-02833921af16 | checkpoint | Has the panel top / bottom cover been installed sealed completely.
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
07424dc0-18e8-52bf-b199-61b7b35d25c5 | checklist | Brackets Checklist |  | Brackets
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
286f2660-fc4a-5104-b871-e193d016b0c3 | section | Brackets QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
cc5b822b-8fd4-53b7-8ff9-f5f00528cb64 | checkpoint | Rebate is smooth and level
c1306333-b314-58e0-8e04-8083e4e91009 | checkpoint | Foam inlay still intact with no concrete inside channel
a5cc8a41-3e3b-4194-af84-8f48f79e8db2 | note | If concrete inside CC need to use expansion/chem set
248639f6-5c80-594a-9ee9-4c2aebae849a | checkpoint | Installation area free from obstructions
9b715fc6-02de-5bcc-abb3-5d73de2d9897 | checkpoint | Bracket installed lined/leveled from GL & RL
ba2fcd15-186d-5183-b0e1-79022739ebf9 | checkpoint | Bracket provided with solid packing/shims
cc498f44-1c68-5025-92e2-eb15708eee0c | checkpoint | Serrated washer engaged correctly and flat washers installed
7910937d-8487-5822-81a4-d8319b9e2085 | checkpoint | Bracket installed with T bolt or expansion bolt
7e29e062-83af-57bc-8965-738a5d81002a | checkpoint | Bolt torqued to 80 NM
4c859ec2-5c97-508f-b778-fa5d16af6851 | checkpoint | Has the steel been holed with 14mmDia
13ccc7a2-c2e3-4e47-bc77-c9a14d07f37b | note | Only fill this for Balustrade brackets
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
d87dc717-7f69-57fe-89c5-37366dc9fcce | checklist | CC Slab Checklist |  | CC Slab
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
4974a07f-7a32-5285-b2df-9c64a5938819 | section | CC Slab QA
01920919-e100-5f45-9c9b-4fe128e40c50 | checkpoint | Access to whole floor
aefa689d-80fa-5927-964e-3b8d55c2477a | checkpoint | Grid Lines and datum levels are visible and accessible
713cef26-7552-501a-9e5f-cdad345ea683 | checkpoint | Handrail and Edge protection fully provided in floor
4b2f1465-baa0-5b2b-a0e1-b06e59577496 | checkpoint | Concrete surface is clear and no obstructions
c5580c88-1bbc-54f3-97c6-54c02daf7a6b | checkpoint | Timber rebate boxes are removed by MC
cc5b822b-8fd4-53b7-8ff9-f5f00528cb64 | checkpoint | Rebate is smooth and level
c1306333-b314-58e0-8e04-8083e4e91009 | checkpoint | Foam inlay still intact with no concrete inside channel
42915d5e-01e7-5393-9a1e-d7ad980ef056 | checkpoint | Cast in Channel installed lined/leveled from GL/RL
787f6117-bee4-5504-91db-898a1423968d | checkpoint | Power DB box and sufficient lighting provided at this floor
7c4964ae-9668-56d9-b135-a63ba6607c2c | checkpoint | Any location at this floor not handed over
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
0486dc6a-818e-550d-a923-aee03057bab1 | checklist | Corner Facade Installation Checklist - Int |  | Corner Facade Installation -
ea9176f4-ce4b-5ae5-a84f-fc3bc2d5551b | section | Prestart QA
a4966c99-b46d-5073-b718-054bfcd309db | checkpoint | Handover of openings from DCL to AWF
44acc3a8-43e0-5f85-aa95-b545a414c185 | checkpoint | AWF QA of openings following handover from DCL
8f8a4dcb-716a-5d6f-ba7f-6c61d3f0e58c | section | Corner Facade Installation QA
da1bfaaf-3ba2-5bf4-9557-fe7109021f80 | checkpoint | AWF QA Water proofing to columns
ca77937a-11c5-5659-b0a1-a830c1c6d33d | checkpoint | DCL QA of water proofing
c799a10d-3c93-5d4a-bd22-15fed86496c7 | checkpoint | AWF install glazing complete
15142235-39b3-5984-bd01-4ea00ac9bcca | section | Completion/Inspection & Handover
d9628d25-024d-5ae2-9549-a928ef82fdc3 | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
37bd99ac-d03a-5f98-8598-292947cd3851 | signoff | Request DCL Signoff
566d8d90-722e-52f0-8fb2-26271d36349d | checklist | Curtain Wall Panels Checklist |  | Curtain Wall Panels
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
fba5333a-63df-52af-8f81-a08b29e58661 | section | Curtain Walls QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
b2e3b29b-dc35-51f4-ac36-936752888453 | checkpoint | Grid lines visible and accessible
0cd3204d-7fb6-526a-a40e-43a8cb916d56 | checkpoint | Panels received damaged free from transportation
99116812-6940-55bc-a1d3-c42e03951770 | checkpoint | Panel gutter chamber has suitable weep holes for drainage
8b25750a-17e8-41c4-ada3-0f1b3d16e6bc | checkpoint | Panel gutter chamber has suitable weep holes for drainage
48827b64-e03b-5928-85f3-d322a3d0ada1 | checkpoint | Panel has all gaskets in place and free from wear and tear. No damaged gaskets.
dcbcc04e-095e-57f5-8392-9081b758f947 | checkpoint | Panel has gutter splice
2a340e5e-c3a4-522a-bb0a-7db256b8452f | checkpoint | Panel has any missing glass / broken glass
00ed2789-358e-53d8-b3e8-9f690dcc374f | checkpoint | Has the starter gutter been installed lined and leveled.
3b0ee03f-cac2-4538-b063-3a2a70d9e608 | note | Only at starting point of UCW. GF or Level 1
bbb8608d-c334-5226-9c08-e53a09ada036 | checkpoint | Panel gutter provided with close cell form
49718684-4255-5533-910a-19762e7c5d9c | checkpoint | Panel gutter splice sealed top/ bottom and sides.
fadc2b8f-4372-541d-81fa-7f19ee26c8ef | checkpoint | Panels installed lined/leveled from GL & RL
01755ee8-8cca-568c-8548-6b8844253ae2 | checkpoint | Has the panel alignment screw been installed
62e1ee64-e2e6-5616-881c-8f5b5c476ba3 | checkpoint | Has the sealing on joint between CW panel completed
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
cd40cbc9-06e0-5b57-a852-33093790bac3 | checklist | Exo Installation Checklist - Int |  | Exo Installation Installation -
ea9176f4-ce4b-5ae5-a84f-fc3bc2d5551b | section | Prestart QA
a4966c99-b46d-5073-b718-054bfcd309db | checkpoint | Handover of openings from DCL to AWF
44acc3a8-43e0-5f85-aa95-b545a414c185 | checkpoint | AWF QA of openings following handover from DCL
6cedb00f-d197-5b1f-93f8-9b5adb085991 | section | Exo Installation QA
f21736e0-2a8d-5159-b5c3-7ec8feb56aeb | checkpoint | Set out completed and accurate
f1565444-3b85-540a-96e2-c5f12a9fc94e | checkpoint | Bolt and fix brackets to nodes
3ad76b35-94d1-54e7-8e82-b86f78c87a7d | checkpoint | Install and adjust struts and bolts fix to node brackets
d293085b-6f59-5f6e-9d4e-572770388d94 | checkpoint | Check isolation disks are installed
7384b72b-71a7-57fe-9699-2db0ebf99fb3 | checkpoint | Install rear cover
8802cc68-cb0d-5a6a-a552-4082f71322ad | checkpoint | install internal cover
c1013c6d-8ac6-5a92-9170-63f1f58f3933 | checkpoint | Adjust covers
15142235-39b3-5984-bd01-4ea00ac9bcca | section | Completion/Inspection & Handover
d9628d25-024d-5ae2-9549-a928ef82fdc3 | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
37bd99ac-d03a-5f98-8598-292947cd3851 | signoff | Request DCL Signoff
197d4f9a-0d46-5f46-bc29-71a86bacf90c | checklist | Floors Checklist |  | Floors
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
0a90552c-d7df-5cd4-a8f1-317afb968f16 | section | Floor QA
01920919-e100-5f45-9c9b-4fe128e40c50 | checkpoint | Access to whole floor
aefa689d-80fa-5927-964e-3b8d55c2477a | checkpoint | Grid Lines and datum levels are visible and accessible
713cef26-7552-501a-9e5f-cdad345ea683 | checkpoint | Handrail and Edge protection fully provided in floor
4b2f1465-baa0-5b2b-a0e1-b06e59577496 | checkpoint | Concrete surface is clear and no obstructions
a4b5c6ff-f4a7-5743-97a3-98a7b613b75a | checkpoint | Concrete floor surface preparation completed with Waterproofing or vapour shied
21400ef2-69f2-50a2-a3c2-363ded4697cf | checkpoint | Surface preparation at floor structure is compatible for sealant application
787f6117-bee4-5504-91db-898a1423968d | checkpoint | Power DB box and sufficient lighting provided at this floor
7c4964ae-9668-56d9-b135-a63ba6607c2c | checkpoint | Any location at this floor not handed over
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
94335571-e7d1-569e-8a2e-9de8c84763d0 | checklist | Glass Balustrade Installation Checklist - Int |  | Glass Balustrade Installation -
ea9176f4-ce4b-5ae5-a84f-fc3bc2d5551b | section | Prestart QA
fbbebeeb-e954-5331-9aa6-24e672702d1a | checkpoint | Glass Balustrade area and item ready for install
e6415529-58d9-554d-a326-8d7810eba1e9 | section | Glass Balustrade Installation QA
b909b362-5a5b-58a1-9cfa-dabc8651bac7 | checkpoint | Install channel and bolted connections
073beb16-6964-5aef-a3f1-ddc5457c2133 | checkpoint | Install glass
e084c763-9448-5a16-8fda-66dfdf310a97 | checkpoint | Install top channel
15142235-39b3-5984-bd01-4ea00ac9bcca | section | Completion/Inspection & Handover
90954897-3058-5def-92b6-e9db78d986cb | checkpoint | Trade Clean Completed
d9628d25-024d-5ae2-9549-a928ef82fdc3 | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
37bd99ac-d03a-5f98-8598-292947cd3851 | signoff | Request DCL Signoff
a58752e9-8f90-55e7-bb84-3771a7c29a88 | checklist | Gutters Checklist |  | Gutters
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
431163b7-789e-5367-9a91-e23f7c12409a | section | Gutters QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
b2e3b29b-dc35-51f4-ac36-936752888453 | checkpoint | Grid lines visible and accessible
4b1dbcc4-7646-5472-a8f8-0876fe76edcb | checkpoint | Structure slab floor surface prepration completed with Waterproofing or vapour shied
884aad93-8e84-5884-a2d9-f76eb22e9cd8 | checkpoint | Floor structure is compatible for sealant application
14ae68e5-e1ee-5760-8ba1-1e576ed12a36 | checkpoint | Gutters received damaged free from transportation
88575636-151f-5e30-8527-60ea540223e3 | checkpoint | Gutter has suitable weep holes for drainage
3eef095d-d1f2-5331-8ae4-f759c551de8f | checkpoint | Gutter installed lined/leveled from GL & RL
8186fffd-8f3a-5325-982d-753369d64425 | checkpoint | Gutter provided with solid packing
22956c14-3ff8-5f42-b8ad-229a5804f82f | checkpoint | Gutter installed with suitable chem bolt
7e29e062-83af-57bc-8965-738a5d81002a | checkpoint | Bolt torqued to 80 NM
3a085412-e3eb-574a-a23f-495600546160 | checkpoint | Has all the mechanical fixings been sealed properly
fea478a7-bc00-5b9b-978f-13418385f203 | checkpoint | Has gutter been sealed for water bund test.
a40dcf68-c61b-593c-8294-5f5b16b5a39a | checkpoint | Gutter water test conducted and witnessed
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
466f3333-690a-5ac4-8829-cb261f048a16 | checklist | Internal Sliding Door Installation Checklist - Int |  | Internal Sliding Door Installation -
ea9176f4-ce4b-5ae5-a84f-fc3bc2d5551b | section | Prestart QA
a4966c99-b46d-5073-b718-054bfcd309db | checkpoint | Handover of openings from DCL to AWF
0cfaf3c3-e463-57a1-a710-89c38b6a8512 | section | Internal Sliding Door Installation QA
4fcabc1f-3a15-550a-a22a-2259368e9b29 | checkpoint | Install tracking and level
5c880f56-3776-53d9-bd92-400c1e6d96d8 | checkpoint | Glaze openings
15142235-39b3-5984-bd01-4ea00ac9bcca | section | Completion/Inspection & Handover
90954897-3058-5def-92b6-e9db78d986cb | checkpoint | Trade Clean Completed
d9628d25-024d-5ae2-9549-a928ef82fdc3 | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
37bd99ac-d03a-5f98-8598-292947cd3851 | signoff | Request DCL Signoff
ba693582-6ae6-509a-81fb-51ab812aae41 | checklist | Jambs Checklist |  | Jambs
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
431163b7-789e-5367-9a91-e23f7c12409a | section | Gutters QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
b2e3b29b-dc35-51f4-ac36-936752888453 | checkpoint | Grid lines visible and accessible
a9560031-7b72-5326-92ff-6e711ec7ed24 | checkpoint | Jambs received damaged free from transportation
172c0f23-9c91-5b87-9154-82f0804802bf | checkpoint | Structure surface prepration completed with Waterproofing or vapour shied
ffe77d58-571d-56ca-a291-e4b9b9b428fd | checkpoint | Structure is compatible for seleant application
67a4c906-6e80-5ed8-8fc6-d2df5060d037 | checkpoint | Jambs installed lined/leveled from GL & RL
ac9fc328-e240-5c5f-9b1b-3a9e8b2ac0ef | checkpoint | Jambs provided with solid packing
c4e406dd-9a58-56ac-bf32-d8feb34d22ac | checkpoint | EPDM Membrane fixed without wear / tear where applicable
86a42f71-4489-5a61-adf3-74d171ad1c99 | checkpoint | EPDM Membrane mechanically fixed and sealed where applicable
78fed1b0-f199-5154-a61b-4c63937f9d82 | checkpoint | Jambs installed with suitable fixings
95fdb668-ba88-53ed-93ad-c69ef2578b88 | checkpoint | Has the side L angle flashing been fixed
3a085412-e3eb-574a-a23f-495600546160 | checkpoint | Has all the mechanical fixings been sealed properly
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
1052b03b-7667-5768-a6fd-91e8f76f9b43 | checklist | Seismic Frame Checklist |  | Seismic Frame
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
059b9dbb-9e5b-5dc0-8c88-428f5b969cdf | section | Seismic Frame QA
cb0ea141-a2a6-5059-971b-4c0690e6cf0e | checkpoint | Received Handover from Main Contractor
0c3cf49e-da1d-5c32-9d15-5dc60a133efa | checkpoint | Has the water proof completed top / bottom and handed over
884aad93-8e84-5884-a2d9-f76eb22e9cd8 | checkpoint | Floor structure is compatible for sealant application
fbbf8258-38b2-5ccb-8a6e-092b7c35383e | checkpoint | Nib/ Upstand is smooth and level
e89d5b21-1129-5f3e-8f8d-ec46d7cf6896 | checkpoint | Frame installed lined/leveled from GL & RL
8f286fff-3b25-5148-bd32-df1fcfb7afb8 | checkpoint | Splice been installed to the frame and sealed all around
9119c69e-efa9-5cd9-8952-eaa13733ca71 | checkpoint | Frame provided with solid packing and top/bottom gap is within tolerance (15mm)
198d8763-7043-5bca-b4cd-f563d9b2da15 | checkpoint | Has all the screws heads been sealed
a312e099-05d1-5f83-8836-7de9833bba80 | checkpoint | Has the side and head flashing been fitted in front of seismic frame and sealed top and bottom.
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
cd5b4355-ede3-55f8-8b10-adbd6b5bf3ba | checklist | Sliding Door Checklist |  | Sliding Door
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
d35adef7-ff2a-565f-ab70-d3c64c8d544c | section | Sliding Door QA
02bdf0a0-5d10-5651-ba1a-57b02094d684 | checkpoint | Seismic Frame / door slider installed.
746a269b-b082-584f-9eb4-1bae20c2d562 | checkpoint | Panels / frames received damaged free from transportation
ee7afe1f-d399-5ffd-ab1c-2b88de408dee | checkpoint | Panel has all gaskets/ mohair in place and free from wear and tear. No damaged gaskets.
2a340e5e-c3a4-522a-bb0a-7db256b8452f | checkpoint | Panel has any missing glass / broken glass
5ecc4cff-e9ae-551b-b134-3035742a4192 | checkpoint | Sliding door has handles / locks and free from damages.
703c2c42-f10f-553c-ab7a-74a88fd54ebf | checkpoint | Has the door lock catcher been installed on the frame.
8aa14f3d-a626-5596-92dd-06017860a67c | checkpoint | Doors installed leveled and closing smoothly.
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible
bc5e343f-f43e-58cf-b7c5-cad1d1519b1d | checklist | Spandrel Install Checklist - Int |  | Spandrel Install -
ea9176f4-ce4b-5ae5-a84f-fc3bc2d5551b | section | Prestart QA
a4966c99-b46d-5073-b718-054bfcd309db | checkpoint | Handover of openings from DCL to AWF
44acc3a8-43e0-5f85-aa95-b545a414c185 | checkpoint | AWF QA of openings following handover from DCL
7449874e-b506-52ea-927c-4f89a0df465e | section | Spandrel Install QA
804b8d9f-0bc6-5b73-a1e2-bbb9c0d3dacf | checkpoint | Inspect water proofing wrap AWF QA
13091e57-ecb4-5012-91c1-950729834082 | checkpoint | Inspect aluminium back pan, insulation and seal
1843c63f-3006-5c3c-9269-733b7327135a | checkpoint | Install ducts (by others)
7c5499f8-3683-521f-ab31-26b5e1895a2a | checkpoint | Air seal ducts (by AWF)
8da15772-91ad-5d40-a2bf-31a73ab2fed4 | checkpoint | Install air seals to perimeter of EXO nodes
1c45d8cf-f107-5c57-9515-f1a8d419d7b8 | checkpoint | DCL QA of air sealed penetrations to spandrel
47942fa7-e270-5462-89bd-59f82bc3f3b1 | checkpoint | Hang Panels
473c7e49-9d08-5316-9a09-5c0d4596ac1b | checkpoint | Seal Panels
15142235-39b3-5984-bd01-4ea00ac9bcca | section | Completion/Inspection & Handover
8133b3a8-cc56-5785-972c-b7c7722bb25c | checkpoint | Trade clean completed
d9628d25-024d-5ae2-9549-a928ef82fdc3 | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
37bd99ac-d03a-5f98-8598-292947cd3851 | signoff | Request DCL Signoff
b8bb2661-65be-59d0-b3c6-93a25a31bb86 | checklist | Steel Post/Water Proofing/External Sliding Door/Base Nodes Checklist |  | Steel Post/Water Proofing/External Sliding Door/Base Nodes Checklist -
ea9176f4-ce4b-5ae5-a84f-fc3bc2d5551b | section | Prestart QA
a4966c99-b46d-5073-b718-054bfcd309db | checkpoint | Handover of openings from DCL to AWF
44acc3a8-43e0-5f85-aa95-b545a414c185 | checkpoint | AWF QA of openings following handover from DCL
79d18c08-5b98-5374-829a-6fd760c7c0ef | section | Steel Post/Water Proofing/External Sliding Doors/Base Nodes QA
038008e6-7b4b-5444-8948-4cd613830c83 | checkpoint | Install steel posts and check for level
0bca08e9-988e-5a79-b2d0-01d12aaaad88 | checkpoint | Install water proofing
46abb989-6f98-5d39-98e9-0eb2301b9376 | checkpoint | AWF QA of installed water proofing
9a5f1776-a020-5554-a8fe-02a249e118f5 | signoff | Request DCL Approval/Signoff
01d50a68-e069-56e1-ae4b-ed739abdc785 | checkpoint | Install perimeter frames
24bfa4fa-5150-5d6d-ab28-3daf0c249a92 | checkpoint | AWF QA of perimeter frames
414f20e2-4540-5018-9b50-a3cf96e65180 | checkpoint | AWF/DCL QA flood test cills and report
21dd537a-291a-5265-9a66-d9c93e2a13fc | checkpoint | Air seal internal perimeter
476b7c16-f3c8-501e-8499-829a8943ba00 | checkpoint | AWF/DC QA air seal lines
28a553e9-1147-5b32-af40-4d84738448f5 | signoff | Request Signoff
d41244ea-9b13-5b54-b6b3-4f788d5bae8a | checkpoint | Adjust rollers
7c47b914-87ee-593a-a053-cff089d01f75 | checkpoint | Install door stops
f861194c-ca1d-5e89-ab86-465438cbaaf6 | checkpoint | Install threshold trims
fe780b3a-cd75-5f5f-8ccf-333b49f38b76 | checkpoint | Adjust locks
fa566ba8-c60d-55f9-a080-19f4443b4e76 | checkpoint | Install external sliding doors and fixed panles
4c9de862-24fb-5582-9fa6-6c9a039289e3 | checkpoint | Install base nodes within +-10mm
be435934-280b-5032-9a89-fab0f46cf322 | checkpoint | DCL water test
15142235-39b3-5984-bd01-4ea00ac9bcca | section | Completion/Inspection & Handover
8133b3a8-cc56-5785-972c-b7c7722bb25c | checkpoint | Trade clean completed
788a2a6e-166e-5db0-b658-abb9ce62e658 | checkpoint | Handover AWF to DCL as complete - All Items inspected, approved and functioning
a2f642e8-5ae9-59fa-9031-ed9b7ea43760 | signoff | Request DCL Signoff
15f61275-60d7-5c2c-9250-1366eda2320c | checklist | Swing Door Checklist |  | Swing Door
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
8f73d1a8-1063-5ccc-8a44-521348675d88 | checkpoint | Area tidy and accessible
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
6629c820-b007-5bdc-9bbd-e49dc1327182 | section | Swing Door QA
468d96cd-3cdc-52c9-a15f-c6bfdcc4bce4 | checkpoint | Door received damaged free from transportation
14e7502c-2095-5513-88e1-41e5c809aa6b | checkpoint | All four hinges are installed on frame or door
9e2d65ba-94ff-5a8c-ae78-cd2055045ce6 | checkpoint | Has the handle been installed to the door
3d8d5618-d88f-5389-b120-cc7d96aa75d4 | checkpoint | Door has all gaskets/ mohair in place and no damaged found on gaskets/mohair.
2c1e27c5-429a-546d-b9e4-a31b13682f90 | checkpoint | Has all the door lock and keys are functioning
8aa14f3d-a626-5596-92dd-06017860a67c | checkpoint | Doors installed leveled and closing smoothly.
83b7c407-d41d-5fcd-a104-12a0605e6bee | checkpoint | Check sheet send to Main Contractor with photos
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
c9935c25-5e49-5f01-b989-a24949905791 | checkpoint | Area left tidy and accessible

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
bfa2f150-896a-58b8-9170-311b9dcd1b02 | checklist | Awning Window |  | Awning Window
727f1b26-44ab-541a-a3f5-d256e574e23c | section | Pre-Installation QA Check
4f86e110-28e7-58d4-8b5c-366049436e40 | checkpoint | Handover QA check sheet received from maincon
46ef5c63-9da6-57f6-87fa-33ccc242eef3 | checkpoint | Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the sealant joint around?
fd243c96-43d4-5c28-95c3-463ad0ccc6f0 | checkpoint | Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant.
8d1a68a6-d186-535d-bd2e-44ede1bbc2b9 | note | Record of Peel Adhesion Test Required
15d2f857-1302-5359-84b5-45df114e763f | checkpoint | Sub-sill flashing installed (by other trades)
44a78c03-d45a-5ea3-a70f-1cb045b175a5 | checkpoint | Alum. frame and sash received in good condition with protection tape applied.
4df93a41-92a0-5e51-a902-960161df9740 | checkpoint | Timber liners complete & securely fixed.
a91f0a7b-2d76-54b2-849b-f7d1dd1959a7 | checkpoint | Sufficient drain holes & hood applied.
248aadf2-1a14-535c-a7fa-643a5f9305d2 | checkpoint | Condensation holes & cover applied
7d967831-0d42-595e-9aa5-bde65e5573ac | checkpoint | Condensation tray installed at locations.
24bbb6a3-b2ee-570d-a82d-f608ea641490 | checkpoint | Corner soakers applied & sealed
48432b4b-a058-51d0-a698-2368f58862d3 | checkpoint | Mitre joints applied with Galva-seal
932100fc-28f9-57f6-8c2c-1d7ef6e8dc8a | checkpoint | Ironmongery/Trickle vent/Gaskets installed properly.
0d8637a7-fe0d-5955-9ae0-521b165dfefc | section | Installation QA Check
689d4054-c65e-55dc-82cf-ae11a1600b10 | checkpoint | Window frame installed plumb, level and square.
5c4db787-63da-52ac-93e9-2cb615309ddf | checkpoint | HD packers/shims are not expose with allowance for silicon as per detail.
8e342474-162c-5857-b830-357130d8c4f9 | checkpoint | All the screws over-sealed as per detail
9994e727-8d11-518e-8c61-273b36b0778f | checkpoint | Sealant neatly applied at external/internal as per detail & ratio
e67255cf-8ded-5ef3-8241-9d45baf16839 | checkpoint | Omega head flashing installed as per drawing
3a47f7a9-e6ac-5040-a3cc-7b65f94af207 | checkpoint | Sash operating (open/close) & locking properly.
0944f9ce-8763-5114-867a-9ddac38ed1b8 | checkpoint | Restrictor stays installed to 100mm max. opening
f579279e-49b3-5c8f-bab5-eb043faa8608 | checkpoint | Glazing beads & rubbers installed properly.
9af75bd8-5ed5-59af-b257-d8e39f92d0df | checkpoint | Glass free from any defect/scratch.
cac2dad8-877e-5c74-9fe0-b659313e282e | checkpoint | Removal of protection tape & trade clean done.
fc478d29-266f-5a0a-b833-570e99542b2b | checkpoint | Final QA checks completed & no defects found.
ad1f7cec-222a-557b-a7bf-41f7ef68b477 | checkpoint | Window handed over by Allwin to Main Contractor.
bf9cdd66-77a6-5769-8355-9e51d8941aab/2 | checklist | Full Ht. PW |  | Full Ht. PW
727f1b26-44ab-541a-a3f5-d256e574e23c | section | Pre-Installation QA Check
adab9e7d-73c9-59ad-bc37-d97249746e72 | checkpoint | Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the silicon joint around?
fd243c96-43d4-5c28-95c3-463ad0ccc6f0 | checkpoint | Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant.
106a3fce-4bd8-5345-a87d-5c4ec7ecff4f | note | Record of Peel Adhesion Test Required
6d855eb2-8f14-5551-979d-15fc978e8547 | checkpoint | Wind beam installed at correct level.
c00caa89-499e-5fa2-9855-790fe94f6ca2 | checkpoint | Alum. Frames/sashes received in good condition with protection tape applied.
340bb492-4285-5a77-9c44-215ff1b89a6d | checkpoint | Sufficient drain holes & caps applied.
d8085f5f-a907-5c94-95ff-16026a5aca43 | checkpoint | Ironmongery/Gaskets installed properly.
0d8637a7-fe0d-5955-9ae0-521b165dfefc | section | Installation QA Check
35b6c7a8-32a5-5ccd-b097-387616743806 | checkpoint | Wanz support bar installed as per dwg.
98496eac-443d-4cff-a3f8-f3d5943ce7a2 | checkpoint | Window frame installed plumb, level and square.
5c4db787-63da-52ac-93e9-2cb615309ddf | checkpoint | HD packers/shims are not expose with allowance for silicon as per detail.
0a7eccfd-0c35-49d4-945f-1fb43fc1bb37 | checkpoint | All the screws over-sealed as per detail
169f5108-19ae-5eb3-85b6-73d06f0c772f | checkpoint | Sealant neatly applied at external/internal as per detail.
c893cadb-4da0-48e9-9b93-e44cc99ac7f9 | checkpoint | Omega head flashing installed.
6fd2cc82-d931-54dd-888b-a8414d1e9e6e | checkpoint | Door panel aligned, leveled & plumbed.
1d2804a6-e74d-4559-8e4a-5ce629a78d9d | checkpoint | Door hardware installed and working e.g. handle/lock
14441ccc-ce5c-5803-9122-12bef08a1295 | checkpoint | Door opening & closing smoothly without scratching the floor or sill.
b72c2ba3-6bff-42fa-95f4-f14121061127 | checkpoint | Door closer installed and functioning
f579279e-49b3-5c8f-bab5-eb043faa8608 | checkpoint | Glazing beads & rubbers installed properly.
4de5b621-50c2-4687-a1ab-ba24b34608d8 | checkpoint | Glass free from any defect/scratch.
d46ed639-9f80-5f0a-9365-c7583b741f17 | checkpoint | Awning sashes installed as per drawing
d3c1aa78-3cbc-4f0f-8bc1-1a7317d81ff3 | checkpoint | Window sash open/close properly
0944f9ce-8763-5114-867a-9ddac38ed1b8 | checkpoint | Restrictor stays installed to 100mm max. opening
5ad6d7f0-c2b2-4e93-a3ce-d910e6676722 | checkpoint | Timber liners complete & securely fixed.
cac2dad8-877e-5c74-9fe0-b659313e282e | checkpoint | Removal of protection tape & trade clean done.
67843e30-4bbf-4409-b391-5da267271945 | checkpoint | Final QA checks completed & no defects found.
ad1f7cec-222a-557b-a7bf-41f7ef68b477 | checkpoint | Window handed over by Allwin to Main Contractor.
affcdd1b-f5e1-5d2d-9f39-c8ee1d802c50 | checklist | Hinge Door |  | Hinge Door
727f1b26-44ab-541a-a3f5-d256e574e23c | section | Pre-Installation QA Check
4f86e110-28e7-58d4-8b5c-366049436e40 | checkpoint | Handover QA check sheet received from maincon
46ef5c63-9da6-57f6-87fa-33ccc242eef3 | checkpoint | Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the sealant joint around?
fd243c96-43d4-5c28-95c3-463ad0ccc6f0 | checkpoint | Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant.
b49646ea-a7f0-5071-a589-8a3798e5ca0f | checkpoint | Record of Peel Adhesion Test Required
bb61bdfe-e624-5ec2-8764-b978bd32d3f8 | checkpoint | Concrete rebate as per dwg & waterproofing applied
dabc5232-71f7-597e-b354-adc6d270f5e4 | checkpoint | Alum. frame and panel received in good condition with protection tape applied.
4df93a41-92a0-5e51-a902-960161df9740 | checkpoint | Timber liners complete & securely fixed.
340bb492-4285-5a77-9c44-215ff1b89a6d | checkpoint | Sufficient drain holes & caps applied.
5ac88d83-cab0-517e-a3f5-80fe1ac942a6 | checkpoint | Ironmongery/Trickle vent/gaskets/mohair complete and secured in place. Replace "IF ANY" gasket or mohair ran short.
0d8637a7-fe0d-5955-9ae0-521b165dfefc | section | Installation QA Check
35b6c7a8-32a5-5ccd-b097-387616743806 | checkpoint | Wanz support bar installed as per dwg.
40698977-4bca-5d2f-8ec8-7ece6ff1ecbd | checkpoint | Door frame installed (plumb/level)
e9e45b97-5327-5d48-b894-075f2c724f50 | checkpoint | Mechanical fixings complete as per schedule
828b9466-0ae0-578a-bf6f-7bd1bcae51e4 | checkpoint | HD packers applied at fixing points
a9bc6d83-1f02-5b09-9b14-179c6db495f7 | checkpoint | Screws over-sealed as per detail
9994e727-8d11-518e-8c61-273b36b0778f | checkpoint | Sealant neatly applied at external/internal as per detail & ratio
6fd2cc82-d931-54dd-888b-a8414d1e9e6e | checkpoint | Door panel aligned, leveled & plumbed.
7e238a06-453d-5585-a088-48476ee001bc | checkpoint | Door hardware installed and working e.g. handle / lock
3b47e770-0051-5ff5-a085-26f0d18baa55 | checkpoint | Door opening & closing smoothly not touching the floor or threshold.
8bb403eb-a284-5e96-b4a8-da6f8efb32fd | checkpoint | Door closer installed and functioning
f579279e-49b3-5c8f-bab5-eb043faa8608 | checkpoint | Glazing beads & rubbers installed properly.
9af75bd8-5ed5-59af-b257-d8e39f92d0df | checkpoint | Glass free from any defect/scratch.
cac2dad8-877e-5c74-9fe0-b659313e282e | checkpoint | Removal of protection tape & trade clean done.
fc478d29-266f-5a0a-b833-570e99542b2b | checkpoint | Final QA checks completed & no defects found.
ad1f7cec-222a-557b-a7bf-41f7ef68b477 | checkpoint | Window handed over by Allwin to Main Contractor.
86b2b661-8a8f-5976-ae5d-fc6c0854f3f7 | checklist | MC Handover |  | MC Handover
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
fa8e86da-eb37-5cdc-97fb-736fb8def052 | checkpoint | QA check sheet/marked up plan or elev. drawing received from Main Contractor for the whole floor.
c222cc8d-e2e7-5a1f-96a2-9ab43e52f726 | checkpoint | Grid-lines (minimum 3-lines per work face) clearly marked on floor by maincon.
759bc8bc-60e9-5ae7-894c-27030b8f6f78 | checkpoint | RLs to be provided at two (2) locations on each level.
c1c69da3-ac4e-5d68-86ab-e2c9c3d15ce8 | checkpoint | Structural opening within tolerance (as per standard)
4bad0d91-eba4-57b0-852c-99bcf6468aca | checkpoint | Gap for sealant joints within tolerance as shown in shop dwgs.
7eeb0983-478c-5245-848a-df71364a2060 | checkpoint | All substrates compatible with Sika AT Façade sealant.
ecc8f04e-28b8-578b-b73c-ac1fe6a452a9 | note | IF NOT - Separation tape must be applied by Maincon
2feb87ea-1146-5889-97a1-06ed7f1fc955 | checkpoint | Concrete rebates made as per approved dwg.
47c81841-a2aa-595a-b2ea-21ffb5e6036b | checkpoint | Waterproofing / membrane applied as per approved dwg.
72ce6dc1-c239-56a3-b180-acfa3b76803a | checkpoint | All timber framing completed & weather-proofed
237f323d-aee0-58c6-91d0-925d4259da82 | checkpoint | Flashing tapes applied as per approved dwg.
585de5fe-eb6c-5d12-a333-7b90caf247de | checkpoint | Sill flashing installed (by other trades)
e18cdeb9-5f50-5ff3-8a47-6951e5a3f321 | checkpoint | Wall face aligned at head-sill-jambs as per approved drawing setout.
283faadb-0987-5eb1-a167-e287b5ec8e09 | checkpoint | Work face is clean, accessible and free from any obstructions.
39e0e74d-b37c-54f2-bb93-fbdfa092c056 | checkpoint | Has Allwin team checked and accepted
189b1e1b-8e4f-55fe-9b29-59f181b66af6 | checklist | Punch Window |  | Punch Window
727f1b26-44ab-541a-a3f5-d256e574e23c | section | Pre-Installation QA Check
adab9e7d-73c9-59ad-bc37-d97249746e72 | checkpoint | Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the silicon joint around?
fd243c96-43d4-5c28-95c3-463ad0ccc6f0 | checkpoint | Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant.
9074b590-46e1-5c76-a398-b8c603da0ebe | note | Record of Peel Adhesion Test Required
15d2f857-1302-5359-84b5-45df114e763f | checkpoint | Sub-sill flashing installed (by other trades)
74421c12-b350-5f10-9ed7-118e60b4df1f | checkpoint | Alum. frame received in good condition with protection tape applied.
4df93a41-92a0-5e51-a902-960161df9740 | checkpoint | Timber liners complete & securely fixed.
a91f0a7b-2d76-54b2-849b-f7d1dd1959a7 | checkpoint | Sufficient drain holes & hood applied.
248aadf2-1a14-535c-a7fa-643a5f9305d2 | checkpoint | Condensation holes & cover applied
7d967831-0d42-595e-9aa5-bde65e5573ac | checkpoint | Condensation tray installed at locations.
24bbb6a3-b2ee-570d-a82d-f608ea641490 | checkpoint | Corner soakers applied & sealed
48432b4b-a058-51d0-a698-2368f58862d3 | checkpoint | Mitre joints applied with Galva-seal
932100fc-28f9-57f6-8c2c-1d7ef6e8dc8a | checkpoint | Ironmongery/Trickle vent/Gaskets installed properly.
0d8637a7-fe0d-5955-9ae0-521b165dfefc | section | Installation QA Check
689d4054-c65e-55dc-82cf-ae11a1600b10 | checkpoint | Window frame installed plumb, level and square.
5c4db787-63da-52ac-93e9-2cb615309ddf | checkpoint | HD packers/shims are not expose with allowance for silicon as per detail.
8e342474-162c-5857-b830-357130d8c4f9 | checkpoint | All the screws over-sealed as per detail
169f5108-19ae-5eb3-85b6-73d06f0c772f | checkpoint | Sealant neatly applied at external/internal as per detail.
e47bf398-62dd-5b3d-b930-02be09830cae | checkpoint | Omega head flashing installed.
f579279e-49b3-5c8f-bab5-eb043faa8608 | checkpoint | Glazing beads & rubbers installed properly.
9af75bd8-5ed5-59af-b257-d8e39f92d0df | checkpoint | Glass free from any defect/scratch.
cac2dad8-877e-5c74-9fe0-b659313e282e | checkpoint | Removal of protection tape & trade clean done.
fc478d29-266f-5a0a-b833-570e99542b2b | checkpoint | Final QA checks completed & no defects found.
ad1f7cec-222a-557b-a7bf-41f7ef68b477 | checkpoint | Window handed over by Allwin to Main Contractor.
746f7319-4a73-5ef3-a11d-d6eaab5b005f | checklist | Sliding Door |  | Sliding Door
727f1b26-44ab-541a-a3f5-d256e574e23c | section | Pre-Installation QA Check
4f86e110-28e7-58d4-8b5c-366049436e40 | checkpoint | Handover QA check sheet received from maincon
46ef5c63-9da6-57f6-87fa-33ccc242eef3 | checkpoint | Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the sealant joint around?
fd243c96-43d4-5c28-95c3-463ad0ccc6f0 | checkpoint | Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant.
87bc4ab2-2bb3-5ec7-953c-781022725c86 | note | Record of Peel Adhesion Test Required
bb61bdfe-e624-5ec2-8764-b978bd32d3f8 | checkpoint | Concrete rebate as per dwg & waterproofing applied
dabc5232-71f7-597e-b354-adc6d270f5e4 | checkpoint | Alum. frame and panel received in good condition with protection tape applied.
4df93a41-92a0-5e51-a902-960161df9740 | checkpoint | Timber liners complete & securely fixed.
340bb492-4285-5a77-9c44-215ff1b89a6d | checkpoint | Sufficient drain holes & caps applied.
f579279e-49b3-5c8f-bab5-eb043faa8608 | checkpoint | Glazing beads & rubbers installed properly.
9af75bd8-5ed5-59af-b257-d8e39f92d0df | checkpoint | Glass free from any defect/scratch.
5ac88d83-cab0-517e-a3f5-80fe1ac942a6 | checkpoint | Ironmongery/Trickle vent/gaskets/mohair complete and secured in place. Replace "IF ANY" gasket or mohair ran short.
0d8637a7-fe0d-5955-9ae0-521b165dfefc | section | Installation QA Check
82220694-9bba-5066-80bc-5215db0c3036 | checkpoint | Slider frame/track installed (align/level)
e9e45b97-5327-5d48-b894-075f2c724f50 | checkpoint | Mechanical fixings complete as per schedule
828b9466-0ae0-578a-bf6f-7bd1bcae51e4 | checkpoint | HD packers applied at fixing points
8e342474-162c-5857-b830-357130d8c4f9 | checkpoint | All the screws over-sealed as per detail
9994e727-8d11-518e-8c61-273b36b0778f | checkpoint | Sealant neatly applied at external/internal as per detail & ratio
3ab6f19d-5828-581a-bd94-a78b061a3a4d | checkpoint | Door panel installed as per drawing
fb206cf8-3030-5d31-9b90-3f54bea85ad5 | checkpoint | Sliding panel aligned, leveled, run smoothly.
a3a3a7a4-c9b1-5554-8b1b-63cf56257ea8 | checkpoint | Pull handle installed/open/close properly
d46ed639-9f80-5f0a-9365-c7583b741f17 | checkpoint | Awning sashes installed as per drawing
491ef136-8b45-5409-80f2-2a95752a40d3 | checkpoint | Sash aligned with the frame
3a47f7a9-e6ac-5040-a3cc-7b65f94af207 | checkpoint | Sash operating (open/close) & locking properly.
0944f9ce-8763-5114-867a-9ddac38ed1b8 | checkpoint | Restrictor stays installed to 100mm max. opening
f9781abb-5829-59e6-9990-8dfa0252ee5a | checkpoint | Wedge rubber / hole caps / been installed to the frame
b862b67d-6d1f-53e2-b1f9-b5fb618d6a37 | checkpoint | Door stop installed as per detail
f71e9f87-1622-55ca-994a-83d5837ce2d0 | checkpoint | Interlocker end cap installed
e67255cf-8ded-5ef3-8241-9d45baf16839 | checkpoint | Omega head flashing installed as per drawing
cac2dad8-877e-5c74-9fe0-b659313e282e | checkpoint | Removal of protection tape & trade clean done.
fc478d29-266f-5a0a-b833-570e99542b2b | checkpoint | Final QA checks completed & no defects found.
ad1f7cec-222a-557b-a7bf-41f7ef68b477 | checkpoint | Window handed over by Allwin to Main Contractor.