## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b3a6cd26-05a5-4ad5-bdca-3e0b6be8e4e8 | checklist | Miscellaneous/Attach Drawings |  | Miscellaneous/Attach Drawings
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1c625852-8607-4a67-b7d6-8697d8946d9c | checkpoint | Document Attached
1f8ae48f-0779-47bd-8d73-d9a25142096a | checklist | QA - Interior Painting |  | QA - Interior Painting
02ff8d15-8ad8-4a45-865b-d82de892b427 | section | Pre-Commencement
01dac54c-a2ed-4ef6-99b1-dae05f7da404 | checkpoint | Handover from stoppers
dcbba17b-45a9-4b22-b91d-9454c5aeeb27 | checkpoint | Work area clean & tidy
8e6f228e-d59c-4939-8349-6d9d209d4702 | section | Sealer Coat
5c58748a-2342-4c2b-b75b-2da2da2e3b58 | checkpoint | Apply sealer coat to walls
37d179a4-dcca-4aa1-9ac6-e429986ab430 | checkpoint | Handover to stoppers for 1st QA light check for defects
d452b55b-ab1e-4602-985a-e1d3e81b553e | checkpoint | Handed back from stoppers defect free
164aef3e-29dc-4955-ae32-8a03a696ece7 | section | First Coat
8ebfbd50-3eb1-47ba-b92c-3570394c92b4 | checkpoint | Apply first coat of colour to walls
938aaffb-ae9c-4ccf-8fe8-03501835e9cd | checkpoint | Surfaces free of defects - signed off by site team
84771cc5-42e4-443b-b558-c2331c01d727 | section | Second Coat
deece584-f6b8-462e-bb14-975303be4914 | checkpoint | All surfaces free of damage & ready for painting
bd70b8b4-c6f6-4c38-9bf5-262ffbdc4277 | checkpoint | Apply final coat to walls
e616a741-13b3-4d95-a35a-a8866cefcefa | checkpoint | Signage in place notifying final coats have been applied
f4606171-cf94-4d6a-b8a7-530ab413ade7 | checklist | QA - Intumescent Paint |  | Intumescent for Area:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
73d3f1bd-c7ff-4e7b-8ac3-b3253319e324 | checkpoint | Specification & mark-up received & reviewed
b7590295-5ebf-44a5-a619-686467de5269 | checkpoint | Q.A. from steel fabricator received & reviewed
56b8541f-cf2c-4f46-afe1-ccc073ef9f4c | checkpoint | Cleaning/washing of substrate
956ded6a-4921-4b90-9dc0-3ccf126263c5 | checkpoint | Substrate acceptable
3e85708e-40a2-4271-9802-1f841021df03 | checkpoint | Base DFT readings on primers
0058b69c-a2df-48a3-b2be-bcfe10ac2d54 | checkpoint | Intumescent applied
9e7f5fc8-d965-44a2-af32-23f98cfe92c2 | checkpoint | Dry film inspection completed
aa8692b2-ddf7-49eb-bae4-b6cba705d467 | checkpoint | Topcoats applied in accordance with specification
594ac9f0-c405-4b6f-a8de-256bebd26ffd | checklist | QA - Stopping |  | QA - Stopping
e356d482-e38d-4fa5-bf61-9efded9cf8fa | section | GIB fixes QA handover
69403e33-9741-4c84-8bb1-e23f5c045eab | checkpoint | Handover from GIB fixes
ff9c4126-a4aa-40f6-8364-80b0e9c03d93 | checkpoint | Screws acceptable
668e5f2d-6104-46ff-bf69-11897aa4856b | checkpoint | Negative details sorted
6d13a679-2692-4e32-8a46-076beb4a21da | checkpoint | Hatches installed
ae95f620-c62a-46ce-b806-db8e89da241e | checkpoint | Joints acceptable
29442201-adb3-4185-9e68-00a8087bdd68 | checkpoint | Bruised/Broken sheets or corners
33d19ae6-739d-4a11-a11f-a77b0f0e3fe8 | checkpoint | Room clean & tidy
39f9ca77-bb4f-4f0d-b006-a7eeb5428ad1 | section | Stopping Completion
5c3640f4-abaa-4864-b329-f7f2e0db461f | checkpoint | 1st coat complete & sanded
1b6acecb-e4fd-4110-9a11-e0e249f2622f | checkpoint | 2nd coat complete & sanded
26f3209a-6317-4d1f-9178-105569a643fa | checkpoint | 3rd coat complete & sanded
fe9f4905-c037-4061-a32f-b040cfe97275 | checkpoint | Ready for sealer coat & 1st light check
dd3f2e14-78ab-4b9b-bca2-310af0a2a088 | checklist | Variation # |  | Variation #
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
cf50e155-6423-439f-ab06-f00bbcc56e30 | checkpoint | Variation completed with photos of work
925806c4-b4cf-5c7a-9e24-33669f4c117a | textbox | Details (Level/Unit/Area)
3d7554eb-6c5e-5869-b380-7774ef2ff50b | textbox | Hours/Minutes