## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC - Concrete Pour Record | [5 empty] | ITC - Concrete Pour Record
section | Preliminaries
checkpoint | 1 - Survey
label | Acceptance Criteria - Sufficient survey set out information is available.
checkpoint | 2 - Survey
label | Acceptance Criteria - Correct line and level for placement of concrete
checkpoint | 3 - Material Delivery
label | Acceptance Criteria - Items conform with the applicable Australian Standard/s
label | Comments / Records - Delivery Docket, Supplier’s Certificate of Compliance
checkpoint | 4 - Material Delivery
label | Acceptance Criteria - Items delivered with no visible signs of damage
label | Comments / Records - Delivery Docket, Supplier’s Certificate of Compliance
section | Pre-Pour Check (to be completed by Engineer or Supervisor)
checkpoint | 1 - Confirm Dimensions
label | Acceptance Criteria - Visual Check and Measure dimensions are correct for trench width or Thrust Block dimensions
checkpoint | 2 - Initial pour against ground
label | Acceptance Criteria - Surface free of water and soft spots
checkpoint | 3 - Initial pour against ground
label | Acceptance Criteria - Hardstand/ ground suitable for concrete pump location
checkpoint | 4 - Initial pour against ground
label | Acceptance Criteria - 50mm blinding UNO
checkpoint | 5 - Initial pour against ground
label | Acceptance Criteria - If for Thrust Block no loose Material
checkpoint | 6 - Construction joints & surfaces
label | Acceptance Criteria - Clean and free of laitance, scabble where required.
checkpoint | 7 - Reinforcement
label | Acceptance Criteria - Installed as per IFC drawings
label | ○ Type, size, position, chairs, cover all as specified & within tolerance; laps and splices as specified
label | ○ Extra tie wire on splice bars around construction joints and wedges fixed to support splice bars in stop end formwork
label | Comments / Records - Cover (mm):
bool | 50mm above obvert
bool | 75mm ground clearance
label | Reo Count:
bool | Reo Count
checkpoint | 8 - Cast-in items, block outs and hold down bolts
label | Acceptance Criteria - Type, quantity and location as per design.
checkpoint | 9 - Final inspection
label | Acceptance Criteria - Pour arrangements agreed and equipment adequate
checkpoint | 10 - Final inspection
label | Acceptance Criteria - Surface free of water, dust, debris and stains.
section | Concrete Pour (to be completed by Engineer or Supervisor)
checkpoint | 1 - Correct Batch / Grade of Concrete
label | Acceptance Criteria - Visual Acceptance of the docket prior to pouring
checkpoint | 2 - Concrete quality
label | Acceptance Criteria - Visual assessment of quality - note details of any loads rejected
checkpoint | 3 - Concrete Testing (Vertical Crest Thrust Block)
label | Acceptance Criteria - 3 sample Cylinder taken (7day and 2 X 28 day tests)
checkpoint | 4 - Concrete Testing (All Other Concrete Pours)
label | Acceptance Criteria - 3 sample Cylinder taken (7day and 2 X 28 day tests)
checkpoint-no-status | 5 - Compaction Method
bool | Pencil vibrators
textbox | No:
section | Post Pour Check (to be completed by Engineer or Supervisor)
checkpoint | 1 - Curing of exposed surfaces
label | Acceptance Criteria - Exposed surfaces cured
bool | Polyethylene sheeting (edges / laps sealed, 300mm min laps)
bool | Curing compound
bool | Water curing (continuous spraying, ponding, wet Hessian)
checkpoint-no-status | 2 - Location of embedment, hold down bolts and penetrations
label | Acceptance Criteria - All embedded items, hold down bolts and penetration located in accordance with drawings
label | Refer defects list below
checkpoint | 3 - Details of defects – cracking in slab pours and inspection of repairs
label | Acceptance Criteria - Finish concrete surfaces inspected by Supervisor. Within specification tolerances (≤ 0.2mm)
label | ○ All defects repaired
bool | Cracks requiring repairs observed
bool | Refer to attached location plan
textbox | RFI
bool | Repairs in accordance with approved specification.
textbox | Comments / Records - Type of surface finish:
checkpoint | Signed:
textbox | FH Engineer (initial):
textbox | FH Supervisor (initial):
label | Details of other defects:
button | Defects listed and NCR raised | Yes,No
textbox | NCR #
button | As Built survey complete | Yes,No
checkpoint | Final Inspection
note | All work completed accordance with applicable procedures, drawings, specifications and approved changes
textbox | Close out - Engineer:
date | Date:
signoff | Sign:
checklist | Concrete Pour Record | [5 empty] | Add Concrete Pour Record
section | Details
checkpoint-no-status | Concrete Pour Record
textbox | CH Location:
textbox | Mix (MPA):
date | Date:
dropdown | Concrete Pour Type: | Thrust Block,Encasement
textbox | Truck Rego/ No.
textbox | Docket No.
textbox | Quantity (m3) - Truck
textbox | Quantity (m3) - Cum.
textbox | Batch Time
textbox | Finish Time
textbox | Discharge Time within 90mins
textbox | Measured Slump (mm) - 1
textbox | Measured Slump (mm) - 2
textbox | Cylinder Test No
checkpoint | Sign off
textbox | Engineer (initial):
textbox | Supervisor (initial):
date | Date: