## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
01f0dcfb-3bfa-4507-83e5-7d0c249f124b | checklist | DTM-ITP-015- Asphalt Placement Rev1 | itp | DTM-ITP-015- Asphalt Placement
b7d5a63c-d42c-4c36-8dab-38d43ad7b48c | section | 1 - Preliminary Works
e6584f21-8731-4375-b19b-9fe56481a4cd | checkpoint | 1.1 - Mix Design approval
f1461c80-f27c-5adc-8813-86415046a32b | note | FREQUENCY: Prior to commencing paving
7a602ad8-d4fd-59d3-b847-f6737462bae3 | note | ACCEPTANCE CRITERIA: Mix design to be used has been approved by project superintendent, prior to use
31cf87a0-c6f3-578e-85cc-4de893bdb707 | note | REFERENCE DOCUMENTS: 407.09 Mix Design Registration
1af4be20-4910-538b-81c1-b714743d1b25 | note | INSPECTION/TEST METHOD: Approval Correspondence
93a4a562-042b-5f3e-b087-36e64fb30068 | note | RECORD OF CONFORMITY: Supply of registration certificate
1101f2cb-7b9a-51ee-b6c0-89198e18a81d | note | HP
6211b1e1-f994-5bc4-bb57-dff70385459f | note | RESPONSIBILITY: Engineer
bebdbe30-b1cc-57ea-9ecd-4fb97b46c79e | date | Date Completed:
9a4e309b-9606-41d8-9a79-71987d8cb80c | signoff | AUTHORITY HOLDPOINT
59dd2a18-8997-4347-bf44-1cc6a9abce56 | checkpoint | 1.2 - Site Inspection and Base Condition
96f4832b-b759-50c6-881c-906922f6eb7e | note | FREQUENCY: Prior to commencing paving
a985246a-31d0-5f25-a1f1-58b98bec1be9 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
848a3803-1ee9-5d20-9504-596fdbb36a15 | note | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
f38e5cb1-d231-582f-978d-5973e316aa1c | note | INSPECTION/TEST METHOD: Visual Inspection
728d7655-bcbf-5731-baa3-096fa4362348 | note | RECORD OF CONFORMITY: Completed ITP Photograph
5a7c5d0f-8682-550f-ad16-b1401689cddb | note | WP
b641356d-c44b-52e1-8a06-835d5de3b165 | note | RESPONSIBILITY: Asphalt Supervisor
8187c94e-4422-55f8-be8f-9504e12dd2e3 | date | Date Completed:
2b9d6932-2dc8-4dd6-9d53-8c6bde0d9558 | checkpoint | 1.3 - Ambient Conditions for Placing
996e10c0-17f8-5855-b1c9-7c331f434736 | note | FREQUENCY: Prior to commencing paving
1d964590-dcdc-56aa-8968-d84ebec423da | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
eb2b2c59-81c7-53d5-b1b5-9a6b94ff01b2 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
5ee2f21e-9b5a-5e48-b56a-eada17f2a13e | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
2a342779-4232-51a6-86ed-6e533f6f2137 | note | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
d4fab6cf-753d-5d83-a2f8-95f19025cb27 | note | REFERENCE DOCUMENTS: 407.17
19de2d53-dec5-5f44-bf13-7d0107887169 | note | INSPECTION/TEST METHOD: Infrared Thermometer
61d50a3a-a7a9-56c7-8d3c-54842c513899 | note | RECORD OF CONFORMITY: Completed ITP Weather forecast Thermometer reading
6bcc2cca-f9df-5af9-864c-ada15faf1020 | note | IP
e0ca07c0-972d-57a8-b04a-45b7cad39259 | note | RESPONSIBILITY: Asphalt Supervisor or Foreman
f244d6f6-0f64-51bf-8882-d3362723b3f2 | date | Date Completed:
d63baa61-8211-477c-ad2b-d527ac61c0b0 | checkpoint | 1.4 - Planning of Joints
7dbeb188-8d88-5165-bd53-ca36c6977758 | note | FREQUENCY: Prior to commencing paving
4059daa3-4ead-5810-be26-07a02607749c | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines
de34daf6-0f7f-5535-9ef9-a21c63dd690f | note | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines
9f944b8f-4c15-5fd8-8ecc-c3dd78ca3802 | note | REFERENCE DOCUMENTS: 407.21
163303f2-0168-55b6-8c6d-414ceb5a7185 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
d3837549-2912-5a7f-9346-0f0b3c3d21ae | note | RECORD OF CONFORMITY: Preliminary join plan submission & photograph on site
d62996d6-27b5-5ad9-ae18-dccb87490db7 | note | WP
d09300a3-81bc-5e4b-aeba-179fe0243651 | note | RESPONSIBILITY: Engineer / Supervisor / Asphalt Foreman
f63b9ba0-5054-524d-90e9-35d87af98dec | date | Date Completed:
b89f67e2-09f1-46c2-9838-78a66a5765fe | checkpoint | 1.5 - Tack Coat
ccd0202a-bae9-54d4-908c-f9bf51ecfa79 | note | FREQUENCY: Prior to Commencing paving
2eb0c982-66c1-5c69-9956-9f2b9c03861b | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure .
fe5702cc-7ad2-5432-9c05-b1820b7a06b5 | note | ○ NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces
26b129c5-97d8-5b97-ba4c-0739d7f79fe5 | note | ○ Photographical evidence must be obtained (with an identifiable landmark)
e26c5b9e-7d24-5451-948b-d10e31f34232 | note | ○ *from 1st July 2023, "trackless Tack Coat" must be used
cbbd2774-192c-5aec-84d1-fbcea2fe0a17 | note | REFERENCE DOCUMENTS: 407.19, AS2150 11
7808549d-78c8-5c99-a420-73463caf1071 | note | INSPECTION/TEST METHOD: Spray area and inspect
43f60b1c-733b-52b6-9ef5-6ce7b09fa973 | note | RECORD OF CONFORMITY: Completed ITP Photograph
796d2751-29ad-5249-b4ba-bc034ddabb43 | note | IP
bbaa6055-38cb-5cbb-a531-d84e987629fa | note | RESPONSIBILITY: Asphalt Foreman
62101368-3248-59db-8e1d-cfa9e2fa9a48 | date | Date Completed:
b646a67a-6db4-41e9-bff2-e6038d501376 | checkpoint | 1.6 - Selection of compaction equipment to satisfy clause 160
568e3502-f50e-5458-920e-be6d5b85614b | note | FREQUENCY: Prior to commencing paving
7efb8d22-12ff-58ad-8dd6-47e637311544 | note | ACCEPTANCE CRITERIA: An oscilating roller will be used if available or static rolling will be conducted on site. Number of rollers and appropriate rolling paterns will be determined prior to the works to achieve the required compaction of the mix. This will be assessed by compaction testing.
4b5246a7-8652-56e4-89f0-f32c5ecae86c | note | REFERENCE DOCUMENTS: 401.04 & 160
690cbdfc-851f-58c9-81c8-d2dc780f1282 | note | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
0af7119f-dbf6-55da-b4d2-d1685f40feed | note | RECORD OF CONFORMITY: Completed ITP, Compaction reports
1dbd02fc-f9da-51da-885f-36607ed01d1a | note | AP
4f8ed472-d65f-58e0-8a6e-39b92362bf80 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
5c215c3b-7a51-5653-a13f-e207fcbac0c6 | date | Date Completed:
cc57a0af-f4f7-4771-a141-7911fbf34b92 | section | 2 - Asphalt Placement works
8182c62d-efe3-4b72-b816-5dd329b6b9e9 | checkpoint | 2.1 - Commencement of Placing
36ed56fd-8ff5-5d8d-9d6a-ba39a5ff2971 | note | FREQUENCY: Prior to Commencing paving
804a1e9f-763f-55cb-a9a1-cbe135fda258 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
a4db787c-c958-5fc5-b7fa-db72407b184e | note | REFERENCE DOCUMENTS: 407.23
b1125a32-de26-5ee2-84c4-554ee92d684d | note | INSPECTION/TEST METHOD: Visual Inspection
c38d54e7-1dc4-59b6-b121-4fe447620bc7 | note | RECORD OF CONFORMITY: Completed ITP Email corresponance
a45e27b0-f34c-5f8e-af81-13b1e773a719 | note | HP
6b61b01c-0c4f-53f4-8e3e-08031991686f | note | RESPONSIBILITY: Asphalt Supervisor / Superintendent
aec74d4e-19f2-5965-8bd9-9d429076a929 | date | Date Completed:
87e3a2c0-65ba-4d12-acf1-9acc3c0da91e | signoff | AUTHORITY HOLDPOINT
1cabd8de-91c1-471e-ae5e-5e36e47990f7 | checkpoint | 2.2 - Delivery of Mix
0681d9ff-d4ca-52d1-bd95-4d49d2e16687 | note | FREQUENCY: Each lot
3dc08e2c-9c04-55a5-ae0a-4ef96175a964 | note | ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design.
fb832523-304c-514d-8daa-fcd4047265b0 | note | REFERENCE DOCUMENTS: Pavement Design Details 407.20
31d2dabd-d307-59c2-ab2d-02c4b7a2f6c6 | note | INSPECTION/TEST METHOD: Check asphalt delivery docket
fac5a3e9-660c-54a0-ab1c-4d952cd0d0d1 | note | RECORD OF CONFORMITY: Traceability sheet
d3729402-ec22-58af-a5d4-43596ad4bafe | note | IP
2fccec77-4af9-5deb-afd3-d096306cee4e | note | RESPONSIBILITY: Asphalt Foreman
61df111c-e47d-5367-add1-39d142b06e43 | date | Date Completed:
cacbe3f7-2f18-42b4-802f-a609e7370f0e | checkpoint | 2.3 - Delivery of Mix
95bddeab-f226-5af2-af14-71a98f518a5c | note | FREQUENCY: Each load
1e79ec97-02e1-572b-bb86-5097eacaf4f3 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
d9596093-88d8-5f5d-8498-81ec39811190 | note | REFERENCE DOCUMENTS: 407.11 Table 407.111
4e869d4f-7e58-574e-a50e-b3f24230fe19 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
d9a1d438-e829-54e4-bc21-ef71025ebfa8 | note | RECORD OF CONFORMITY: Traceability sheet
c1b072c2-1ae1-5731-91c1-117b59ead1c7 | note | WP
18104e52-90fd-5a58-a25c-99d40b866460 | note | RESPONSIBILITY: Asphalt Foreman
6bad2f16-a6d8-5c2d-b49d-cd400ed98c9e | date | Date Completed:
7be16ef5-82d2-49a9-82da-75d3ef1aa99b | checkpoint | 2.4 - Traceability
45b16292-9b81-55b9-8323-0274243dd7d6 | note | FREQUENCY: Each lot
d767e35a-3910-550c-97c6-53d3e56e2a3b | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
4ceecc96-ef27-5348-a934-28dd2c30e9bc | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
15724847-a4fb-53d0-aab4-9f0ac249b5bd | note | INSPECTION/TEST METHOD: Measure and Record on Daily Lot Record
b54fef0e-754c-5d32-abc1-835b636e2432 | note | RECORD OF CONFORMITY: Traceability sheet
ad622faa-d5cf-50d5-a270-002f9afcb839 | note | IP
c9b00581-d6e0-566b-9441-a2d24d99b353 | note | RESPONSIBILITY: Fulton Hogan Foreman/ Engineer
11ce75d7-e682-54a4-a587-222bc595fdb8 | date | Date Completed:
998c32a1-5641-4902-9b72-2fef3836a9fa | checkpoint | 2.5 - Layer Thickness and Level Control
86183d6a-f38f-5e3d-8d2b-995a333d9261 | note | FREQUENCY: Regularly during paving
e65a3ebb-7bae-5633-8e3d-7718b0844031 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
851c9ded-8450-547e-86e9-7335293b69de | note | REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b)
6df7e944-659d-53fb-9f54-045c7637f14b | note | INSPECTION/TEST METHOD: Dips using ruler or dip stick
c81a3602-11dd-5d92-b0a2-177aa691c945 | note | RECORD OF CONFORMITY: Level and stringline record
c6c5e97f-9920-59b1-bbdc-fcf860e96818 | note | WP
4990afc7-5a46-591c-bf32-94cd1cccd1a6 | note | RESPONSIBILITY: Asphalt Foreman
a5bfacf9-a50a-5f81-a290-e74755de1041 | date | Date Completed:
c82e3e23-7a00-4050-995d-64505ff8f2d1 | checkpoint | 2.6 - Paver Stoppages
2f7a8f86-b71a-5b63-9f6e-3c472a894f82 | note | FREQUENCY: If paver stops
e7615f5b-9ef2-528e-8864-946b3e224486 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
5ab58eb5-958c-5572-93e0-dbe214a011eb | note | REFERENCE DOCUMENTS: 407.25 (c)
1c17aca5-e59f-53ed-8dcb-2c6b1a71cd60 | note | INSPECTION/TEST METHOD: Thermometer
593ac53c-17d2-5af1-8c6f-7552ddf9d6d7 | note | RECORD OF CONFORMITY: Traceability sheet
e94ac733-8882-5537-9e43-18789ca7c8d3 | note | WP
a43b1327-c158-5582-b9c9-8c7b298a0521 | note | RESPONSIBILITY: Asphalt Foreman
8a99df12-07eb-5628-9af7-f97c3bbb7768 | date | Date Completed:
7e3165ee-105d-415b-abf9-071837858eef | checkpoint | 2.7 - Surface Finish of Wearing Course
ef44fc55-3477-51c8-90c3-16780796d045 | note | FREQUENCY: During paving and after final roll
cf857460-7870-5694-953a-e015b912aa61 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
94f0e32f-83e7-5967-97fe-9a683e287d45 | note | REFERENCE DOCUMENTS: 407.25 (c)
7c4acf53-583b-5b98-a49d-37313d8a75d5 | note | INSPECTION/TEST METHOD: Visual Inspection & straightedge
b64154bf-a529-5f32-9190-baac478b56f3 | note | RECORD OF CONFORMITY: Completed ITP or photograph
04b8f84d-9bc7-5d76-be17-1fbad0942b5e | note | WP
0180e968-180d-5645-a980-500bc1ef00ca | note | RESPONSIBILITY: Asphalt Foreman
f6ead3c9-3f6f-5ef6-8d49-da960dcf0672 | date | Date Completed:
12b32dcb-625a-4205-9238-5cc5db6f956b | checkpoint | 2.8 - Kerb and Channel
068e5c27-51a3-5b5f-b37c-0dc24aee5ac1 | note | FREQUENCY: During paving and after final roll
53e40956-a8cc-599c-a66f-be5033e5b837 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
a6a7482e-7bac-5f42-b0c6-fd1ae9ac5534 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
c712f562-5c43-591c-ac9c-c878951ee4ae | note | INSPECTION/TEST METHOD: Visual Inspection & Measurement
638b5bfb-7483-5b26-ad10-de3db086a3c2 | note | RECORD OF CONFORMITY: Completed ITP or photograph
5baaa019-dc1d-5de2-8513-bb2de90ee73b | note | WP
4ac9ad79-a519-5f32-b1f6-11b2b9d6b93f | note | RESPONSIBILITY: Asphalt Foreman
04331480-fa9a-5ee6-948d-cb18f86d95f8 | date | Date Completed:
e642238e-7797-4230-bb9c-8b178017134c | checkpoint | 2.9 - Trafficking pavement after placement
797d2de2-301a-5cb8-935a-abf8d3da4edc | note | FREQUENCY: After final roll
822e7e29-077d-5ead-a1c4-bf1b5ee62532 | note | ACCEPTANCE CRITERIA: Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling. Where trafficking of SF asphalt results in deformation, further trafficking shall cease until such time that the type SF asphalt has adequately cooled to allow works to continue without further damage.
8d03325d-ea19-5a76-b75b-b8eb8f2b0a38 | note | ○ For Stone Mastic Asphalt, this must be 40°C
5a45696f-724e-55b8-824f-9bdbe2bb59ce | note | REFERENCE DOCUMENTS: 407.28, 404.14
762b6f5c-c39b-59c1-8d0a-7fc4de5f35ec | note | INSPECTION/TEST METHOD: Visual Inspection & Thermometer
ee6579a5-0158-5830-9eaa-124d14297250 | note | RECORD OF CONFORMITY: Completed ITP & thermometer reading
4c4c0a23-25a7-558a-90c0-3ca809c5019e | note | HP
295c3c13-9808-53d0-bec7-126eab279005 | note | RESPONSIBILITY: Asphalt Foreman
06259743-9928-5874-bf6c-28849d386d0a | date | Date Completed:
4c08df8c-9ccc-4082-b852-aaef98a56727 | signoff | AUTHORITY HOLDPOINT
5d53ee20-3a2d-4f15-bb42-62927612cfc9 | section | 3 - Testing
f2229942-9e19-4e1b-a215-a4c4d268fdd0 | checkpoint | 3.3 - Compaction Testing (Dense Graded Asphalt)
e43578f9-0a80-5889-b155-6fbf7141a88d | note | FREQUENCY: Per Lot
c354355a-4703-5f5e-b3ab-42e2f1fd81ba | note | ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
a305df5e-9585-5e30-81e9-1dd7f33b8ae6 | note | — >50mm layer depth = 96.0%
95f532e2-32da-58c5-8610-abd1cab25df8 | note | — <50mm layer depth = 95.0%
ca36683e-7258-57b5-93db-a0cf6fec4646 | note | ○ Additional Test must be undertaken on the longitudinal joints for wearing courses
19c79b79-84ee-56f7-a47c-2e51e88027c7 | note | ○ Test Lots 50m2-500m2, may be treated as a small area, in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
d3629042-14bc-5f02-b1a8-1d54db67b7c2 | note | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
0d898531-eaca-52a1-af4e-005b20d4fc98 | note | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
817b310e-1aaf-555f-9d88-b31cb76cf000 | note | REFERENCE DOCUMENTS: Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
88992777-206e-58ca-94c8-e4cda70cff71 | note | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
8b3c9fe3-df59-54ce-8c1a-794f89e5a7dc | note | RECORD OF CONFORMITY: Completed ITP, Compaction reports
75ee6485-75b7-5f73-93f8-82fbad5f5d21 | note | TP
b070e86a-ce15-528c-b09a-14e29ebda1f5 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
68a1f51a-ebdc-5a4b-a5c8-73ddf1eef463 | date | Date Completed:
00602149-8718-4f06-afdd-39921c529412 | checkpoint | 3.4 - Level Conformance
bed1e19c-f501-5dd7-923f-5eee9f178c54 | note | FREQUENCY: Each Lot
5866edb8-17c0-5f62-a306-07e44b05102e | note | ACCEPTANCE CRITERIA: The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
afcc579a-f646-5dea-8ef1-4f3f661c5612 | note | ○ Scale A: +/- 5mm Range, +/- 8mm standard deviation
d7c9d096-98e5-5671-874c-530b05ad65e9 | note | REFERENCE DOCUMENTS: 407.30, 407.29
5ce3f110-55b6-5b8a-9732-ff2f55503eb8 | note | INSPECTION/TEST METHOD: Survey Results
c7f64e24-696a-57a4-a1e3-e929105631d1 | note | RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results
028f05cf-dad0-5ea8-9ee3-cdff28f55dc3 | note | WP
e350a470-c7f1-5b1d-81b9-61dea6cf5a2f | note | RESPONSIBILITY: Surveyor / Superintendent
6bb4e7db-1387-50ba-bb40-db131430ef0f | date | Date Completed:
06886c9b-b0c0-4950-9fd2-2e2084e61cf8 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f3037c11-ea1a-572a-ac9f-daa2d3ab4509 | textbox | Fulton Hogan - Print Name:
44657c40-fa17-5446-bc12-52bfe78922b0 | textbox | Fulton Hogan - Position:
c801164e-48d4-5ce7-aaea-bb7b2e1337d4 | date | Work Completed On:
bd9f5a9e-b48c-4e1c-9e4d-2fa811816d01 | signoff | Add Signature