## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
209638ce-b303-4260-8a99-c55798fa3acd | checklist | Commercial/Domestic |  | Commercial/Domestic
04aba37b-6387-4ffc-9173-76efe1a7440c | section | Details
e567b819-58d8-4775-af37-5ccd1d97d2fb | checkpoint | Opening Wrapped & Prepared Correctly
83d794f8-3873-47e1-b1af-54950a748ea7 | checkpoint | Installed / Fixed As Per Shop Drawings
529b78d2-d60f-4511-a850-75d5e1ca791d | checkpoint | External Flashings / Weather Seals As Per Shop Drawing
dd17610c-bfe1-4a6a-b453-367b5617e9a7 | checkpoint | Airseals Completed (photo)
bb572e09-dea4-4d91-a5e8-dd8c44b558e1 | checkpoint | Glass - Frame Glazed
0c7f7b0e-4573-4c17-b0a7-5f350e07bfe2 | checkpoint | Glass - Glazing Rubbered and Complete
9e90c4dd-cd8d-4eb6-89fe-0865e4efadcd | checkpoint | Trade Clean & Sign off
11195645-3468-4b29-b4db-3fb0af0ce026 | checkpoint | Wights - Sign Off
84357850-c961-4456-9e9c-b1919322aefa | checklist | Seismic Suite (Curtain Wall) |  | Seismic Suite (Curtain Wall)
f11ca812-a2db-49a0-a459-1cb848ed9066 | section | Details
303150cf-c534-4581-a591-1ce2c96f727d | checkpoint | Opening Prepared By Main Contractor
50d78dce-68e2-4fcd-ad2a-88d433737484 | checkpoint | Setout/Grids/Datum Lines
c78e2a54-2860-4a1f-854e-d4670955c0c4 | checkpoint | Seismic Installed As Per Shop Drawings
85969ef3-a8e2-45f6-bb56-04fafe3f676c | checkpoint | DL Brackets Fitted & Welded correct location
038ce9c2-ab6b-4243-a03c-4b86f2956dd2 | checkpoint | Panel Fitted & Locked Off
62ae4e15-7677-4a83-a099-7c36e23dff77 | checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
d7ce7c0d-feb6-47a3-bc4b-e3b3a6fd5af5 | checkpoint | Airseal and Internal Flashings (photo)
0ccef7d7-e680-4f6a-9191-f3d3a21bef20 | checkpoint | Smoke Seal Complete (photo)
54d99f3e-d9b3-4bee-bc4a-89486a2b1fa0 | checkpoint | External Flashings / Weather Seals/Drainage
09d148dc-4fae-4e7b-9d4d-b8c73fb08941 | checkpoint | Glass - Frame Glazed
bf8559bf-5be5-479e-9281-5197941453dd | checkpoint | Glass - Glazing Rubbered and Complete
ef381242-69ce-48cc-89f1-2b5b0c0072ba | checkpoint | Trade Clean & Sign Off
1d96f304-57d7-4be0-8069-14b778598234 | checkpoint | Wights - Sign Off
d9e96b10-837d-48f7-aa39-63d3745da57a | checklist | Seismic Suite (non curtain wall) |  | Seismic Suite (non curtain wall)
9e7e5f6b-d0ac-44ac-978b-b4faa0d913d8 | section | Details
5e65abe7-2ec0-47ed-926b-17fba23c4bf8 | checkpoint | Opening Prepared, Wrapped & Datums
8b35b543-e735-4dce-9b07-76690fc84277 | checkpoint | Seismic Installed As Per Shop Drawings
ca5d519e-c7c7-42b5-8c05-41e2383897b6 | checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
a763dc39-6ef4-40af-a9dc-1919b739db32 | checkpoint | Panel Fitted & Locked Off
76f7d66d-c3e3-4ed9-89ec-167b2c5d4283 | checkpoint | Airseal and Internal Flashings (Photo)
7c0fd547-0da1-44d7-8352-8076a7cb5b21 | checkpoint | External Flashings / Weather Seals / Drainage
6567074e-3d22-4c3c-822f-ed41ad12f954 | checkpoint | Glass - Frame Glazed
27f179a3-5039-44bc-9cee-ff5550704f3e | checkpoint | Glass - Glazing Rubbered and Complete
49f2e064-fcc2-48d0-8709-029cc8a1ee65 | checkpoint | Trade Clean
b76c6d30-f759-429c-bca5-948f45fa66a6 | checkpoint | Wights - Sign Off
d8f5d319-71b0-4e9b-a46b-76f1bdebd89d | checklist | Seismic Suite (Structurally Glazed Curtain Wall) |  | Seismic Suite (Structurally Glazed Curtain Wall)
6ab22afc-968f-4533-a868-273b8bb68a3c | section | Details
2e5ebf1a-4046-47fc-99e6-f4f41ea95001 | checkpoint | Opening Prepared By Main Contractor
067cf8c8-7c60-48ef-8873-00f3f0a94b6f | checkpoint | Setout/Grids/Datum Lines
cbf8804a-d6d8-4c82-b101-38f257644a96 | checkpoint | Seismic Installed As Per Shop Drawings
fc0f0834-83f0-43a5-a462-30b184e2aee7 | checkpoint | DL Brackets Fitted & Installed correct location
d270fced-32ad-4cf3-a66a-ea962dc93dd8 | checkpoint | Panel Fitted & Locked Off
2a698402-2705-4f13-8628-28b30ca5a1fc | checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
1ecb7a02-89e5-40b4-869e-7a52a410f3a6 | checkpoint | Airseal and Internal Flashings (photo)
a770622c-8b78-44bc-9ad7-7dd05ce15a05 | checkpoint | Smoke Seal Complete (photo)
9efd9950-434e-4492-9312-f0d5e757630c | checkpoint | External Flashings / Weather Seals/Drainage
05dbea94-b622-4165-b256-bbe4b814919c | checkpoint | Trade Clean & Sign Off
9802940b-eb26-4bd4-84f0-9debe489dd24 | checkpoint | Wights - Sign Off
65c65751-2bfd-466f-be1c-65633b9e7a20 | checklist | Skylights |  | Skylights
bc254c4a-97d6-4170-97f5-11f2ba92ecdf | section | Details
45b72486-708c-4d2d-b1ba-f744b5e70565 | checkpoint | Opening Wrapped & Prepared Correctly By Main Contractor
43f821da-0704-4581-8ca9-03b98be89132 | checkpoint | Roof frame Installed / Fixed As Per Shop Drawings
e4dcf4e3-4eff-423f-9b21-2cc4cbc98602 | checkpoint | Airseal and Internal Flashings (photo)
09c6cbac-6602-4f33-a3a3-f86ffe0af314 | checkpoint | External Flashings / Weather Seals (provide photo reference)
aac225bb-ec47-48ca-b58e-2bace3b228ee | checkpoint | Glass - Frame Glazed
71dac788-bfe9-4efc-99c8-e42352d6b8da | checkpoint | Glass - Glazing Rubbered and Complete
44c92c27-faa6-445f-8b62-0dbc8df5857b | checkpoint | Wights - Sign Off