## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Brick Install for Area: |  |  |  |  | Yes | QA - Brick Install | 11a736f8-6fc7-4792-981d-aa2e28675213
checkpoint-status |  |  | checkpoint | Epoxy mortar installed at ground level
checkpoint-status |  |  | checkpoint | Brick support angle installed
checkpoint-status |  |  | checkpoint | Awining brackets installed
checkpoint-status |  |  | checkpoint | Cavity fire bat installed
checkpoint-status |  |  | checkpoint | Brick ties installed at correct centers
checkpoint-status |  |  | checkpoint | Correct brick tie type installed
checkpoint-status |  |  | checkpoint | Corner reinforcing installed
checkpoint-status |  |  | checkpoint | Weep holes
checkpoint-status |  |  | checkpoint | Silion installed
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checklist-flat |  |  | checklist | QA - Backfill Checklist |  |  |  |  | Yes | QA - Backfill Checklist | 15971650-3189-46f1-96f3-7beb6b442421
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closeout
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct - desired compaction achieved
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | QA - Concrete Suspended slab |  |  |  |  | Yes | QA - Concrete Suspended slab | 21c2b717-0f5c-4908-b39a-8029504ecf40
checkpoint-status |  |  | checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint-status |  |  | checkpoint | flat slab RL correct
checkpoint-status |  |  | checkpoint | Formwork in place.
checkpoint-status |  |  | checkpoint | Reinforcing steel – mesh/reinforcing size and lap.
checkpoint-status |  |  | checkpoint | Starter bars in correct position and size.
checkpoint-status |  |  | checkpoint | Floor thickness in place (random slab check areas).
checkpoint-status |  |  | checkpoint | Cover to reinforcing correct.
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Levels of finish confirmed.
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.
checkpoint-status |  |  | checkpoint | Control joints / saw-cuts and depth.
checklist-sectioned |  |  | checklist | QA - Structural Steel Checklist |  |  |  |  | Yes | QA - Structural Steel Checklist | 25aa0005-f357-44dc-881d-c8aa93762d23
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Structural steel items checked
label | ba8571a8-7142-58fb-83d0-e2342462090e |  | note | Type/Size Checked
label | 170710a1-5efc-5f56-97d0-5ce5d97279b5 |  | note | Finishing checked (ie. Painted, Galvanised, etc)
checkpoint-status |  |  | checkpoint | Cast in/anchor bolts and plates installed
checkpoint-status |  |  | checkpoint | Welding complete and QA recieved
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels checked/correct
checkpoint-status |  |  | checkpoint | All dry packing completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Structural steel work completed within tolerance in respective area
checkpoint-status |  |  | checkpoint | Paint remedials complete and at the correct thickness
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checklist-flat |  |  | checklist | QA - Pile Caps |  |  |  |  | Yes | QA - Pile Caps | 36ebc884-f727-48a4-b561-031be3a36f49
checkpoint-status |  |  | checkpoint | Approved Handover CAN received from engineers
checkpoint-status |  |  | checkpoint | Pile broken into correct height
checkpoint-status |  |  | checkpoint | Top of pile is scabbled
checkpoint-status |  |  | checkpoint | Formwork dimensional check
checkpoint-status |  |  | checkpoint | Drawings photo with location
checkpoint-status |  |  | checkpoint | Photos
checkpoint-status |  |  | checkpoint | Minimum site concrete achieved
checkpoint-status |  |  | checkpoint | Waterproofing
checkpoint-status |  |  | checkpoint | Reinforcing cover achieved
checkpoint-status |  |  | checkpoint | Reinforcing bars correct size annd grade
checkpoint-status |  |  | checkpoint | lap bars through pile cage installed
checkpoint-status |  |  | checkpoint | IBMS terminators installed well within cover
checkpoint-status |  |  | checkpoint | Electrical grounding installed
checkpoint-status |  |  | checkpoint | Structural engineer's inspection completed and site report received and closed out.
checkpoint-status |  |  | checkpoint | Pour
checklist-flat |  |  | checklist | Balcony Timber Framing for Area: |  |  |  |  | Yes | QA - Balcony Timber Framing | 527b7124-a4a2-4f50-a453-df795fac6926
checkpoint-status |  |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | frame install at correct RL
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | Deflection head
checkpoint-status |  |  | checkpoint | Correct fixings used
checkpoint-status |  |  | checkpoint | Fixings installed at correct centers
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checklist-sectioned |  |  | checklist | QA - Precast Walls Checklist |  |  |  |  | Yes | QA - Precast Walls Checklist | 63a37f3c-2e2e-4953-ba31-672e233be1d8
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast walls manufacturing completed and transported safely to the site
boolean | bcab2810-823b-5995-938a-3479266b4aef |  | tickbox | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Site Setout completed and template followed
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the panel checked/correct
checkpoint-status |  |  | checkpoint | Panel propping checked
checkpoint-status |  |  | checkpoint | Checked rebar requirements for any insitu stich joints
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Panel grouted and QA completed
checklist-sectioned |  |  | checklist | External Envelope |  |  |  |  | Yes | External Envelope | 65e3d9e8-35cf-42e6-be2e-86a1c0fef553
checkpoint-group |  |  | section | Waterproofing balconies
checkpoint-status |  |  | checkpoint | Substrate correct
checkpoint-status |  |  | checkpoint | Outlets and Overflow installed
checkpoint-status |  |  | checkpoint | Correct laps and upstands
checkpoint-status |  |  | checkpoint | 2nd layer install at bricks
checkpoint-status |  |  | checkpoint | Terminations bars installed
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checkpoint-group |  |  | section | External Timber Framing
checkpoint-status |  |  | checkpoint | Setout from Grid lines
checkpoint-status |  |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | Correct fixings used
checkpoint-status |  |  | checkpoint | Fixings installed at correct centers
checkpoint-status |  |  | checkpoint | All openings are in correct location and correct size
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checkpoint-group |  |  | section | Weather line
checkpoint-status |  |  | checkpoint | Correct fixing installed
checkpoint-status |  |  | checkpoint | Fixing installed at correct centers
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checkpoint-group |  |  | section | Reveal Shield
checkpoint-status |  |  | checkpoint | Correct laps installed -150mm
checkpoint-status |  |  | checkpoint | joint at internal and external corners installed correctly
checkpoint-status |  |  | checkpoint | All services/penetrations liqui-flashed
checkpoint-status |  |  | checkpoint | openings Liqui-flashed
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checkpoint-group |  |  | section | Joinery install
checkpoint-status |  |  | checkpoint | Correct packing 6-18mm
checkpoint-status |  |  | checkpoint | fixings installed and over sealed
checkpoint-status |  |  | checkpoint | Airseal completed 6-18mm
checkpoint-status |  |  | checkpoint | Cavity closer installed
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Glazing installed and rubbered off
checkpoint-status |  |  | checkpoint | Protection installed
checkpoint-status |  |  | checkpoint | Windows and Doors Operational
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checkpoint-group |  |  | section | Rockwool Insulation
checkpoint-status |  |  | checkpoint | Correct fixings used
checkpoint-status |  |  | checkpoint | Fixing installed at correct centers
checkpoint-status |  |  | checkpoint | Insulation installed snug
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checkpoint-group |  |  | section | Brick Install
checkpoint-status |  |  | checkpoint | Epoxy mortar installed at ground level
checkpoint-status |  |  | checkpoint | Brick support angle installed
checkpoint-status |  |  | checkpoint | Awining brackets installed
checkpoint-status |  |  | checkpoint | Cavity fire bat installed
checkpoint-status |  |  | checkpoint | Brick ties installed at correct centers
checkpoint-status |  |  | checkpoint | Correct brick tie type installed
checkpoint-status |  |  | checkpoint | Corner reinforcing installed
checkpoint-status |  |  | checkpoint | Weep holes
checkpoint-status |  |  | checkpoint | Silion installed
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checkpoint-group |  |  | section | Balcony Timber Framing
checkpoint-status |  |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | frame install at correct RL
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | Deflection head
checkpoint-status |  |  | checkpoint | Correct fixings used
checkpoint-status |  |  | checkpoint | Fixings installed at correct centers
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checklist-flat |  |  | checklist | Waterproofing for Area: |  |  |  |  | Yes | QA - Waterproofing Balconies | 7cb8d007-f9e3-4b5b-9f67-5fc93129a44a
checkpoint-status |  |  | checkpoint | Substrate correct
checkpoint-status |  |  | checkpoint | Outlets and Overflow installed
checkpoint-status |  |  | checkpoint | Correct laps and upstands
checkpoint-status |  |  | checkpoint | 2nd layer install at bricks
checkpoint-status |  |  | checkpoint | Terminations bars installed
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checklist-flat |  |  | checklist | QA - Underslab Services |  |  |  |  | Yes | QA - Underslab Services | 90e9c331-41f5-464f-aaec-830efa34e884
checkpoint-status |  |  | checkpoint | ELECTRICAL services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | HYDRAULIC services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | GAS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Subsoil drain installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | MECHANICAL services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | DATA/COMMS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Any other services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Underslab Services completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | QA - Detailed Excavation Checklist |  |  |  |  | Yes | QA - Detailed Excavation Checklist | 9880b60b-4d8a-4167-98af-07666bcb119d
checkpoint-status |  |  | checkpoint | General Photos / Comments / Observations during excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
checkpoint-status |  |  | checkpoint | Sump pit excavated
boolean | 5bc44793-2967-5a9e-afca-0414d96bfa10 |  | tickbox | Location accurate
boolean | 79ccd762-3d1c-50e0-87bd-c37183978ebf |  | tickbox | Depth correct (allow for site concrete if required)
boolean | 1edc2d4b-0f27-5a32-9bbe-623cd69add0f |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
checkpoint-status |  |  | checkpoint | Excess Material Cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Weather line for Area: |  |  |  |  | Yes | QA - Weather line Installation | 9fea2b42-1b9b-4d72-a454-938b88452545
checkpoint-status |  |  | checkpoint | Correct fixing installed
checkpoint-status |  |  | checkpoint | Fixing installed at correct centers
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checklist-flat |  |  | checklist | QA - Waterproofing Checklist |  |  |  |  | Yes | QA - Waterproofing Checklist | be66ac6a-145d-4520-a92e-66a1388599b4
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status |  |  | checkpoint | Sufficient lap installed at transition
checkpoint-status |  |  | checkpoint | General photos/comments during install
checkpoint-status |  |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status |  |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Joinery for Area: |  |  |  |  | Yes | QA - Joinery install | c40b429f-7975-49bc-b85f-e2d44805382f
checkpoint-status |  |  | checkpoint | Correct packing 6-18mm
checkpoint-status |  |  | checkpoint | Fixings installed and over sealed
checkpoint-status |  |  | checkpoint | Airseal completed 6-18mm
checkpoint-status |  |  | checkpoint | Cavity closer installed
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Glazing installed and rubbered off
checkpoint-status |  |  | checkpoint | Protection installed
checkpoint-status |  |  | checkpoint | Windows and Doors Operational
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checklist-flat |  |  | checklist | Reveal Shield for Area: |  |  |  |  | Yes | QA - Reveal Shield | c531ffb5-2d64-4f1e-be02-bcdd9ce4aad4
checkpoint-status |  |  | checkpoint | Correct laps installed -150mm
checkpoint-status |  |  | checkpoint | Joint at internal and external corners installed correctly
checkpoint-status |  |  | checkpoint | All services/penetrations liqui-flashed
checkpoint-status |  |  | checkpoint | Openings Liqui-flashed
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checklist-flat |  |  | checklist | External Timber Framing for Area: |  |  |  |  | Yes | QA - External Timber Framing | ca5cb4e8-25c7-433e-9914-8055e1fdb9a5
checkpoint-status |  |  | checkpoint | Setout from Grid lines
checkpoint-status |  |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | Correct fixings used
checkpoint-status |  |  | checkpoint | Fixings installed at correct centers
checkpoint-status |  |  | checkpoint | All openings are in correct location and correct size
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed
checklist-flat |  |  | checklist | Rockwool Insulation for Area: |  |  |  |  | Yes | QA - Rockwool Insulation | d838ff23-92fb-4c5c-a0fa-206b640d053c
checkpoint-status |  |  | checkpoint | Correct fixings used
checkpoint-status |  |  | checkpoint | Fixing installed at correct centers
checkpoint-status |  |  | checkpoint | Insulation installed snug
checkpoint-status |  |  | checkpoint | Remedial(s) Raised & Completed
holdpoint |  |  | signoff | Inspections completed
checklist-flat |  |  | checklist | QA - Retaining lagging and drainage |  |  |  |  | Yes | QA - Retaining lagging and drainage | da659c00-0467-4e4d-8a32-b45085536ebf
checkpoint-status |  |  | checkpoint | Boards bolted and straight
checkpoint-status |  |  | checkpoint | Correct fixing centres
checkpoint-status |  |  | checkpoint | Maxi flow installed
checkpoint-status |  |  | checkpoint | Backfill complete
checkpoint-status |  |  | checkpoint | Wall clean and pencil marks removed
checklist-flat |  |  | checklist | QA - Concrete Slab on Grade |  |  |  |  | Yes | QA - Concrete Slab on Grade | e524c973-98c3-4664-9f43-978050199827
checkpoint-status |  |  | checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint-status |  |  | checkpoint | Slab on grade – top of metal RL.
checkpoint-status |  |  | checkpoint | Formwork in place.
checkpoint-status |  |  | checkpoint | Reinforcing steel – mesh size and lap.
checkpoint-status |  |  | checkpoint | Starter bars in correct position and size.
checkpoint-status |  |  | checkpoint | Holding bolts in place.
checkpoint-status |  |  | checkpoint | Floor thickness in place (random slab check areas).
checkpoint-status |  |  | checkpoint | Cover to reinforcing correct.
checkpoint-status |  |  | checkpoint | Construction joints installed
checkpoint-status |  |  | checkpoint | Column control joints installed
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Levels of finish confirmed.
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.
checkpoint-status |  |  | checkpoint | Control joints / saw-cuts and depth.
checklist-sectioned |  |  | checklist | QA - Concrete Pour Checklist |  |  |  |  | Yes | QA - Concrete Pour Checklist | fc6742a9-cbbf-47bc-84dd-20c5b803655e
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | b7f5ab55-5778-5174-a036-b66bb7c969e5 | DataPoint is missing 'button' values | button | Size and type correct to specification
boolean | ab4251a8-7472-5b8d-bb79-472c8b171930 |  | tickbox | Reinforcing spacing and location correct | Yes, N/A
boolean | f7c2d451-fc13-5a38-80b0-1db88a3e3973 |  | tickbox | Specified covers checked/correct | Yes, N/A
boolean | 3e9ba6c0-4121-57fb-b4a1-9b048f40bf74 |  | tickbox | Splice laps checked/correct | Yes, N/A
boolean | 94ffccfd-c271-5945-a251-3186b7781029 |  | tickbox | Any starter bars are installed correctly (location, size and spacing ) | Yes, N/A
boolean | 63d4ad3d-3f76-5c5e-97bc-781079b3e3c1 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed | Yes, N/A
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | bc07041b-42c8-5c41-80b4-e1b5c62e9816 |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | 2849b9fa-ef4e-56a1-987d-21b3505f0e2f |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable