## Sheet1
Type | Name | Values
Waterproofing balconies
Checklist | Substrate correct
Checklist | Outlets and Overflow installed
Checklist | Correct laps and upstands
Checklist | 2nd layer install at bricks
Checklist | Terminations bars installed
checkpoint | Remedial(s) Raised & Completed
holdpoint | Raise Remedial / Request Signoff
checkpoint | Inspections completed
checklist | External Timber Framing Checklist
checkpoint | Setout from Grid lines
checkpoint | Dimensions / locations of walls checked and correct
checkpoint | DPM installed where required
checkpoint | All frames are square & plumb
checkpoint | Correct fixings used
checkpoint | Fixings installed at correct centers
checkpoint | All openings are in correct location and correct size
checkpoint | Remedial(s) Raised & Completed
holdpoint | Raise Remedial / Request Signoff
checkpoint | Inspections completed
Type | Name | Values
checklist | Weather line Installation Checklist
checkpoint | Correct fixing installed
checkpoint | Fixing installed at correct centers
checkpoint | Remedial(s) Raised & Completed
holdpoint | Raise Remedial / Request Signoff
checkpoint | Inspections completed
Type | Name | Values
checklist | Reveal Shield Checklist
checkpoint | Correct laps installed -150mm
checkpoint | joint at internal and external corners installed correctly
checkpoint | All services/penetrations liqui-flashed
checkpoint | openings Liqui-flashed
checkpoint | Remedial(s) Raised & Completed
holdpoint | Inspections completed
Type | Name | Values
checklist | Joinery install
checkpoint | Correct packing 6-18mm
Checkpoint | fixings installed and over sealed
checkpoint | Airseal completed 6-18mm
Checkpoint | Cavity closer installed
checkpoint | Flashings installed
checkpoint | Glazing installed and rubbered off
checkpoint | Protection installed
Checkpoint | Windows and Doors Operational
checkpoint | Remedial(s) Raised & Completed
holdpoint | Inspections completed
Type | Name | Values
checklist | Internal Fit-out #1
checkpoint | Install bottom plates
Checkpoint | Core drilling
checkpoint | Intumescent
Checkpoint | Carpentry works
checkpoint | Steel stud
checkpoint | Install nogs
checkpoint | First fix - PVC underslung
checkpoint | First fix - Mech
checkpoint | First fix - Electrical
checkpoint | First fix - Sprinkler
checkpoint | First fix - Pex
checkpoint | First fix - Alarms
checkpoint | First fix - Security
holdpoint | Inspections completed
Type | Name | Values
checklist | Internal fit-out #2
checkpoint | Passive fire install - Inside walls
checkpoint | Install insulation - walls
holdpoint | Inspections completed
Type | Name | Values
checklist | Internal fit-out #3
checkpoint | Install Gib - walls
checkpoint | Passive fire install - all soffits
checkpoint | Install ceiling grid
checkpoint | Install insulation - ceiling
checkpoint | Install Gib - ceiling
checkpoint | 2nd fix - drill Gib services holes
checkpoint | Install doors & skirting
checkpoint | Gib stopping
checkpoint | Gib Painting
checkpoint | Install kitchen including bench top
checkpoint | Vinyl install
checkpoint | Install kitchen splash back
checkpoint | Appliances
checkpoint | 2nd fix - Mech
checkpoint | 2nd fix - Sprinkler
checkpoint | 2nd fix - Electrical
checkpoint | 2nd fix - Pex
checkpoint | 2nd fix - Alram/Security
checkpoint | Install hardware
checkpoint | Install flooring carpet
checkpoint | Install wardrobe doors & organisers
holdpoint | Inspections completed final sign off