## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | dcf94ffa-9174-4a93-8b67-b495933c1e40 |  | checklist | ITP-01-007 - Hot Mix Asphalt | itp |  |  |  | Yes | ITP-01-007 - Hot Mix Asphalt | 14d89e74-1cb0-447b-8168-d6ae719c3c98
checkpoint-group | 8901406d-349c-4d1b-9174-bf4c289f2751 |  | section | 1 - Construction Works
checkpoint-status | c366929a-b219-4219-b346-5c37e455ef33 |  | checkpoint | 1.1 Submission of Mix Design
label | 5d517c03-5fa8-5b97-a8ff-31ce9792160f |  | note | FREQUENCY: Prior to commencing paving
label | e15bf9cf-3207-5040-8698-8dfcaca4a5a5 |  | note | – – – – – – – – –
label | fe604b8c-61be-5f17-9079-540e9151cb25 |  | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | a5ec1df0-eea0-560c-8766-841d638e1a92 |  | note | – – – – – – – – –
label | 1a8ea927-ab8a-5c76-879c-2f67333552d7 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | 14acac6b-6a74-5441-b884-b8287cf00ef9 |  | note | – – – – – – – – –
label | 1939f3b3-fdaa-5c2b-ac13-c8bc5712121e |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | 84fd11f8-d9e6-51d2-b907-918eaf99ee4a |  | note | – – – – – – – – –
label | f2412eca-5eb5-5419-8c48-6b8a9463dfa3 |  | note | RECORD OF CONFORMITY: VR approval, Completed ITP
label | b4de5da9-759e-5e20-9f2a-1202830c8cac |  | note | – – – – – – – – –
label | abafebc2-b788-51a6-8dce-09dfcddcd3aa |  | note | HP
label | 176a0b83-f55c-54fb-b2ff-f115256d346e |  | note | – – – – – – – – –
label | fd233a74-b572-53dc-a6fd-9ece56ca0031 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
label | 77c60406-cd88-54de-b9fc-6ffd40305cc4 |  | note | – – – – – – – – –
text | c620b830-99d3-52fd-b877-36abc9c4686b |  | textbox | DATE:
holdpoint | 76361e82-4645-47f1-bc8a-add18a180210 |  | signoff | HOLD POINT AUTHORITY
checkpoint-status | c24ff299-88e4-499f-a546-985ace107e12 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 3b033468-4f22-5a08-8039-e1eb4e7d3ee6 |  | note | FREQUENCY: Prior to commencing any activity
label | 03aa0ef3-4b64-5947-80ca-c669d138dad0 |  | note | – – – – – – – – –
label | 341d3a9f-d36d-50f2-b3b0-d59eb1f0d50a |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | f83ce86a-cac9-5063-a17e-951f4ac441ca |  | note | – – – – – – – – –
label | 9dd1a5ba-0dd6-51f1-acec-ef890b22bf53 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | fed7fb50-380f-5356-878b-88b838fc8475 |  | note | – – – – – – – – –
label | 9b37f230-5a84-530b-8cb9-803ce5a24369 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7b0edc44-dd17-56d1-bb84-5f1319c484fd |  | note | – – – – – – – – –
label | 7096833c-37d0-5e1d-9e41-b18f10ebfa7c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | dc7434e8-1258-5153-bf4a-9293a10f0a3e |  | note | – – – – – – – – –
label | 3cfe8dcd-7dfb-5c35-9222-37583c4723c9 |  | note | HP*
label | 5eebb63c-4c40-56ff-87ad-9ae27f07674d |  | note | – – – – – – – – –
label | 3b52c257-46bb-597c-b3b0-1ff25f990498 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | e7e892fa-fa31-53c3-84dc-0cb32546de05 |  | note | – – – – – – – – –
text | 8b95670c-6a0c-53be-8497-66ab4b1086ae |  | textbox | DATE:
checkpoint-status | 2baa6521-1bf4-4f30-a6e2-9b17e2c78332 |  | checkpoint | 1.3 Site Inspection and Base Condition
label | 453fdc0d-10be-5438-962a-73d124b42f95 |  | note | FREQUENCY: Prior to commencing paving
label | 0dd0e333-4c10-56bb-bcf2-ae7d8b3c0f87 |  | note | – – – – – – – – –
label | d07b4f4f-c7ef-5fdc-9b39-d0c3f5a3a28b |  | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | 395b21ae-51bb-5756-b6fa-054b1902290b |  | note | – – – – – – – – –
label | 5ec9cf67-0f94-5c0a-8ceb-5b11e11f863f |  | note | REFERENCE DOCUMENTS:
label | bc215544-a6f4-5b8d-befa-addadd5e0bda |  | note | • 407.14
label | 8088077f-2b81-5dd4-8961-fe1ff5393c27 |  | note | • AS2150 10.1
label | 9b429438-aed0-5ccd-84b9-59b2bef3b974 |  | note | • AS2150 10.3
label | 88923fbd-33ff-5dc2-b38d-5247f27fcd6d |  | note | – – – – – – – – –
label | 85babfbc-f19b-54b5-8687-7b7b79a9424d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e32df529-850c-5f43-aa30-7e8f5a9e7a46 |  | note | – – – – – – – – –
label | fa6cc303-e7bc-5b3d-a1ed-ca3241303b7e |  | note | RECORD OF CONFORMITY: ITP Signed
label | 6c5bb57a-e102-569f-978e-b0d135b4eaf9 |  | note | – – – – – – – – –
label | 0eb146eb-7506-575c-a8ca-3af32b613815 |  | note | WP
label | 76a5dc00-c67a-511e-b8ab-bc207a15c6e6 |  | note | – – – – – – – – –
label | e0c48a80-c6d4-5837-b5e8-a913785c78f4 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | ab854c4d-1ee5-5659-a0cb-b31e50054582 |  | note | – – – – – – – – –
text | a282921e-7d7d-5b10-b7db-563ec84be646 |  | textbox | DATE:
checkpoint-status | b47e7572-d75c-473c-9f55-41cb7607b5ca |  | checkpoint | 1.4 Ambient Conditions for Placing
label | f83728e0-de2d-55ef-9fef-33c5de0694f7 |  | note | FREQUENCY: Prior to commencing paving
label | 08283cc2-a5cf-5e03-93dc-6820a00a2ac1 |  | note | – – – – – – – – –
label | 27b8d534-28df-5c65-909f-64af751951ad |  | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | a88f2fd0-b975-5b8e-a4d3-2853b62c07bb |  | note | • Base & Intermediate Courses: 5°C for conventional binders or
label | 4e2a9775-973a-57e9-8451-df297c436496 |  | note | • 10°C for PMBs & Class 600
label | 2b7f4d65-8456-51e2-b3a4-f94d20ad3b35 |  | note | • Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | 17349e5c-4ed9-5cd1-9dff-0e1b9c0421b8 |  | note | – – – – – – – – –
label | 18af2ea3-6f4f-50b5-9478-5c1848155e03 |  | note | REFERENCE DOCUMENTS: 407.13
label | 6453672b-025f-5866-acee-8bb0ee3d321a |  | note | – – – – – – – – –
label | d4a59a77-f26b-506a-b7e6-701b1db639cc |  | note | INSPECTION/TEST METHOD: Verify
label | 391c4f46-dae1-5354-91cb-911b786ce075 |  | note | – – – – – – – – –
label | 669a5ad2-6191-595b-a3c0-0bda2cfcbd84 |  | note | RECORD OF CONFORMITY: Thermometer
label | 541cebb9-46a2-5f27-abd2-6017ad7fa678 |  | note | – – – – – – – – –
label | cb96a2ff-8008-522b-b26e-c53d611e504c |  | note | IP
label | d7b45ee2-8aee-5bc0-a275-3a3fa4a358f1 |  | note | – – – – – – – – –
label | 52ca3628-4a8a-5e89-970b-1075eee107f9 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 7975ffc2-6997-50e7-b005-f7750c14c930 |  | note | – – – – – – – – –
text | ae0b27d8-da0e-59f8-82f4-a5a196af2b6f |  | textbox | DATE:
checkpoint-status | 23644472-a7c1-427e-a4a5-d8f48c2f1718 |  | checkpoint | 1.5 Planning of Joints
label | 025106c0-7ba9-5adf-8f2b-e4cc86185f8e |  | note | FREQUENCY: Prior to commencing paving
label | efdab6c3-fe09-55aa-85a6-7a66a73bffb2 |  | note | – – – – – – – – –
label | 6ca229f9-7e57-5abc-a9fb-c47e5a7d001f |  | note | ACCEPTANCE CRITERIA:
label | 973bc94c-71ea-5af5-aef6-3022ae687f17 |  | note | • Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | fa64c680-876c-57ac-9d92-b7cb4e619e93 |  | note | • Transverse Joints Offset from layer to layer by at least 2m
label | fa7c57ee-6b4b-595a-a153-51c52fb7454b |  | note | • Longitudinal Joints Offset from layer to layer by at least
label | 7da5c09b-4b88-55b8-8a3f-6698d5d48246 |  | note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | 68077064-ba5d-5ef9-a89b-41c839d6e1dd |  | note | – – – – – – – – –
label | 982858d9-0c77-516b-88e2-c91e4d391096 |  | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
label | 66f5ad0c-264d-5f41-af2c-88cdea9a7ed4 |  | note | – – – – – – – – –
label | c4d22a84-d86d-5268-be81-adeb6a94661b |  | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | e5f6c710-3bb6-55e7-af7f-77958aa16f6d |  | note | – – – – – – – – –
label | 7b634c1b-a4d1-55ef-b352-b9d8a3ff154b |  | note | RECORD OF CONFORMITY: Paving Plan
label | 7a5de942-bbdd-563f-9679-0b70c7c71e13 |  | note | – – – – – – – – –
label | b91d9e0e-67fa-56b0-8f46-52c432e71841 |  | note | WP
label | 87a5df42-0911-5151-96ba-b06734a1c15b |  | note | – – – – – – – – –
label | 3d23947c-f004-5a2a-8296-43d1a2c4acb9 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
label | 3ff805cf-b566-5de6-801d-f6b85e3397f7 |  | note | – – – – – – – – –
text | e4a21092-4293-5187-bc93-7b1825c86ed9 |  | textbox | DATE:
checkpoint-status | 55afb1dc-cbc6-4e78-bb78-930f9f28986c |  | checkpoint | 1.6 Longitudinal Joints with existing Pavement
label | 5907383c-4021-5c17-9f8b-0f74b18271f3 |  | note | FREQUENCY: Prior to commencing paving
label | c41e3b2e-4673-5852-8096-def7e1f9f776 |  | note | – – – – – – – – –
label | 2f784a34-f845-5b36-a1fd-f5f39d298b1e |  | note | ACCEPTANCE CRITERIA:
label | ef917d78-98e9-5522-973a-ac924acd3fb5 |  | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | e84d4f78-5923-55b0-9c32-eff1d30e738c |  | note | • Depth of step to be cut to the full depth of each indiviual layer.
label | f36007f5-1fc5-52a3-9037-adced40e749b |  | note | – – – – – – – – –
label | 40eb9598-0bdd-574f-80a8-c890ca25da90 |  | note | REFERENCE DOCUMENTS: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
label | b78613bb-5742-5a89-8ab6-bce01214e03f |  | note | – – – – – – – – –
label | b16628ab-23b8-595d-81fd-6b3101349e62 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9a1edba9-7b5c-54ae-b2d0-bbe26c717fe8 |  | note | – – – – – – – – –
label | 7ef271ae-ec5c-54e7-988a-0a4078dbefee |  | note | RECORD OF CONFORMITY: ITP Signed
label | fbbcfe7e-244b-51e8-8914-73d978753e89 |  | note | – – – – – – – – –
label | 7e8a234c-dde4-55d9-ad4a-7fc942d7488d |  | note | WP
label | 35f4f232-6636-5b3d-9822-6f8413decccf |  | note | – – – – – – – – –
label | 7f57a5ec-3608-54c8-9340-04a3b17b0db3 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
label | b7f41081-2bfc-5c93-97be-f9800436ff74 |  | note | – – – – – – – – –
text | 4105936b-f499-5c8f-8d69-8056afe9e018 |  | textbox | DATE:
checkpoint-group | c024dba1-d580-49aa-80bc-2586bc72d38a |  | section | 2 - Asphalt Placement works
checkpoint-status | 957106e0-b934-44d0-8bea-2aafa7cb59ae |  | checkpoint | 2.1 Tack Coat
label | 779bd18e-7bcf-50cd-95f8-73de464366c5 |  | note | FREQUENCY: Prior to commencing paving
label | f184073e-6ab9-5787-bb8d-8a47fed2ca68 |  | note | – – – – – – – – –
label | 9ce27624-3e9f-5bda-b0f7-53ce3a44092f |  | note | ACCEPTANCE CRITERIA:
label | 1e266ad6-eed0-5e8b-964d-e8632068a181 |  | note | • Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content).
label | 8f5735dd-7ea2-56a6-8bb6-685aa3243927 |  | note | • This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving.
label | fdad1bc2-0e7b-51bd-9d83-faa8d024b9e0 |  | note | NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | e3cb0914-6353-5180-84fc-fdbdf42eecd8 |  | note | – – – – – – – – –
label | 58993c48-5de9-50d4-ad5d-c06240b1599e |  | note | REFERENCE DOCUMENTS: 407.15 AS2150 11
label | 0b273aec-6f22-5e92-a285-7a83ecf0a6b1 |  | note | – – – – – – – – –
label | d3e869a6-3363-53ea-b188-2665a5540b14 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 5176cb87-ea44-5a83-b892-407a80eb3e7f |  | note | – – – – – – – – –
label | 463ec368-10b7-51ae-8643-9d263fafc5b3 |  | note | RECORD OF CONFORMITY: Spray area
label | c8f91230-df0a-5400-8a6e-824533707524 |  | note | – – – – – – – – –
label | 886fe91a-b5fb-54ae-bd83-7b6e6cc2a28f |  | note | WP
label | 10c25fcc-c2fd-59d4-ad4f-63978418c041 |  | note | – – – – – – – – –
label | cc16b8f1-cd6a-58f2-a1a0-016f4c0d7b45 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 297da023-663d-5d73-ac44-dcd920f3da4e |  | note | – – – – – – – – –
text | b20ecb99-b6fb-53c3-97f1-a9723424fcb6 |  | textbox | DATE:
checkpoint-status | 223176e3-ad39-4441-be74-49153452795a |  | checkpoint | 2.2 Commencement of Placing
label | 9b3cd1ab-67b6-5171-ad03-713e9e733d19 |  | note | FREQUENCY: Prior to commencing Paving
label | 86f41def-d3d4-5e01-a822-8f83eb77ce64 |  | note | – – – – – – – – –
label | 2dc22a51-675a-5d23-ae7d-11e3193404b6 |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | 714e39fc-034b-5a5d-8733-cf2d5b7f9980 |  | note | – – – – – – – – –
label | d965c3e2-bf78-57ad-8557-7f68c8efbc75 |  | note | REFERENCE DOCUMENTS: 407.18
label | 9c67184e-2e6d-505b-8347-a1318dae575b |  | note | – – – – – – – – –
label | e7bd7cd0-0cda-5d99-9921-be43e5095c98 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 5c4d37c1-c071-5df0-b090-39ec8b0a0422 |  | note | – – – – – – – – –
label | dd94c88c-2be2-5c69-a83f-0b9f2d61e6fa |  | note | RECORD OF CONFORMITY: ITP Signed
label | 3d64d100-662b-50c0-a344-855622fbfa3a |  | note | – – – – – – – – –
label | 3235fce3-aed3-521a-9993-11b744d6c7b5 |  | note | HP
label | 4dab1753-6bc0-55e9-8b00-2e261d0bfbdb |  | note | – – – – – – – – –
label | 9624ae95-b0ea-571b-b8e9-abead4af574d |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
label | c859d9ab-6848-57f3-b5cc-70816111d853 |  | note | – – – – – – – – –
text | 28205231-7e8e-55e9-8c82-7298872aa3bc |  | textbox | DATE:
holdpoint | b35cd4cb-ad41-4210-9340-e9b5a053364e |  | signoff | HOLD POINT AUTHORITY
checkpoint-status | ad8eaf99-bb5e-46de-abc8-91ef6a0bb886 |  | checkpoint | 2.3 Mix Design Confirmation
label | 0976523b-c6ea-5ad2-bb5b-29b1e7ef6b0e |  | note | FREQUENCY: Each lot
label | b226d133-2a59-5151-8466-f5fc35199cbe |  | note | – – – – – – – – –
label | f74666ec-9f79-52a8-89fe-476cd81e5e47 |  | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | b04eee73-9ebe-5299-8e0d-fbd2b98090b2 |  | note | – – – – – – – – –
label | e3049c21-5af6-57a2-93b3-26fe2f4080db |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | 4da740ab-b523-5532-82c6-474575e9abc9 |  | note | – – – – – – – – –
label | 92225e2f-8061-5b0f-ad1e-64c6de23b07e |  | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | 6b0bd756-b996-5ffb-8a78-1aeff2a22b28 |  | note | – – – – – – – – –
label | 5811f9d0-5af8-588d-a06a-b3f746531e68 |  | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
label | 65dc0d65-28c2-5ac6-a20e-a6268e4949ab |  | note | – – – – – – – – –
label | fb9e3037-ec07-5a2f-b34c-b32896d96a07 |  | note | HP*
label | c4eada17-3fd0-5959-afdd-b5788f506257 |  | note | – – – – – – – – –
label | 197579d9-3d49-538f-8926-482655abbde4 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 5d0be62e-1290-593f-94bd-47ea6394f331 |  | note | – – – – – – – – –
text | 33d116b8-12cc-5789-845c-57a586e6327f |  | textbox | DATE:
checkpoint-status | 81cebd3f-1d7c-4433-971e-775ef3e8bfbc |  | checkpoint | 2.4 Delivery of Mix
label | be3d0820-16c4-5bc9-8f02-0121e37117f5 |  | note | FREQUENCY: Each load
label | ba3381f6-74cc-542e-8381-a5ace4190dae |  | note | – – – – – – – – –
label | a988cda1-438a-5a32-9826-92a14ed01abe |  | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | d3745a1e-4f46-5266-9535-ef9781183cbc |  | note | – – – – – – – – –
label | eccb0d7a-f328-5850-9a89-117231cee5ee |  | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
label | 8f3d2411-9315-5691-a554-576e93e8329c |  | note | – – – – – – – – –
label | 258ac48d-288d-59f3-9c3d-2dfad2b5fd8c |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8be5dee2-d505-513f-972b-df0902fbe0a5 |  | note | – – – – – – – – –
label | 6cc0f1e8-ec80-5daa-b69c-b0cea81230e3 |  | note | RECORD OF CONFORMITY: Delivery Docket
label | d5bb139d-0bfe-5270-82ed-8c45d7d9f761 |  | note | – – – – – – – – –
label | b225273a-7884-50d8-8b1d-3e3c0591ca53 |  | note | WP
label | 0f9d0e78-5d8f-544b-8b2c-87d94cf39572 |  | note | – – – – – – – – –
label | 03fd04a0-3c0d-5f6e-929d-52fcbfeb3257 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 33a75d36-bc62-5cf4-8761-291adc131c52 |  | note | – – – – – – – – –
text | 056750be-3bac-5ce2-ac3a-9548c0a1eb48 |  | textbox | DATE:
checkpoint-status | f281e1c2-a388-4c01-a479-5e26d591adf6 |  | checkpoint | 2.5 Traceability
label | 19992a32-c931-5f1f-80af-90f87af87e5e |  | note | FREQUENCY: Each lot
label | 555348a7-59fd-564f-a54a-888720b7ae80 |  | note | – – – – – – – – –
label | 5e779c0c-9abf-580f-8848-4b2896a3827a |  | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | 9f362d13-e73e-5953-8690-4377d479dd1d |  | note | – – – – – – – – –
label | 6d4d3aa7-1316-5e11-853f-cc5dd31870dc |  | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | 4d4086ef-d47d-5dc4-83e2-c8a23b77212a |  | note | – – – – – – – – –
label | dd61a01d-74a0-56fb-b875-6e053bb8c5ab |  | note | INSPECTION/TEST METHOD: Verify
label | 67772c46-6e46-5de4-b553-6ba7e476b74b |  | note | – – – – – – – – –
label | d8b59d9a-2cc3-5333-a651-211a41888dcb |  | note | RECORD OF CONFORMITY: Daily Lot Record
label | b37116ee-3ba7-517f-ba26-3f542550e5b8 |  | note | – – – – – – – – –
label | 58f87004-fbce-504d-ab9b-62b076aaf39e |  | note | IP
label | c91795d3-3f71-5aa3-9a76-5c0b8d8a756b |  | note | – – – – – – – – –
label | 45b1e1a8-58a3-5079-b394-5c2a9b557974 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | f9751fda-b837-55e0-80db-319a9c043a4d |  | note | – – – – – – – – –
text | 523a1acb-faa7-5a90-a109-25abf1b7fe00 |  | textbox | DATE:
checkpoint-status | 79746bd4-154a-4981-b504-35958e9a6d3d |  | checkpoint | 2.6 Layer Thickness and Level Control
label | 02bb80b9-140e-5c03-af66-70c8ffb0ce40 |  | note | FREQUENCY: Regularly during paving
label | 867ec6c2-7d9d-5c67-8e3c-8e2e69090d10 |  | note | – – – – – – – – –
label | a76eee70-2387-50e9-aba0-732ef4f0134d |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | de474018-e2f4-5bbc-b581-0c4fdba07db6 |  | note | – – – – – – – – –
label | e069483d-501c-55cd-a8c2-63be268f82a8 |  | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | 72aecb52-f507-50a7-9098-a7691e8734e1 |  | note | – – – – – – – – –
label | 1defec72-91b6-5be1-9fc4-df2d54c837a2 |  | note | INSPECTION/TEST METHOD: Verify
label | 1409307f-68d4-5a31-a644-09d62b37c503 |  | note | – – – – – – – – –
label | dcba5261-bb8a-594f-93db-e98d83a4cadd |  | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | 8c91218d-8457-565c-8aeb-e5ddf1eda0b2 |  | note | – – – – – – – – –
label | 65a9ea68-9cda-5c54-aae2-e1fa0c33c75b |  | note | WP
label | cf8f5638-36bd-54c5-996b-3f77fa72d6c5 |  | note | – – – – – – – – –
label | ae96a1e2-831e-5f87-bc2e-2adb1ae94d19 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | e1b64802-3937-5784-b6ef-75150daf9f52 |  | note | – – – – – – – – –
text | 7f9d5d06-5742-53a9-9fde-c05bec63fc9e |  | textbox | DATE:
checkpoint-status | b062d004-90a1-49d6-8324-6c620c1ea8bc |  | checkpoint | 2.7 Paver Stoppages
label | bd8f3832-f714-5805-881c-276c1a887b62 |  | note | FREQUENCY: If paver stops
label | 545be8e7-fcc2-5e99-9649-27335f895364 |  | note | – – – – – – – – –
label | a669dc2c-7e9d-5a37-a6cb-3de78dedcc04 |  | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | ce0c19ea-a30d-53a4-9729-e8dd6781893e |  | note | – – – – – – – – –
label | ba68c9b1-8e91-58d8-872a-57479fb654b9 |  | note | REFERENCE DOCUMENTS: 407.20 (c)
label | 7ecdc3e8-5e03-5745-b647-8761d718640e |  | note | – – – – – – – – –
label | 872e3538-7d5f-5359-ad69-fdda33d7187c |  | note | INSPECTION/TEST METHOD: Verify
label | b84c8f84-c571-5d55-a374-8e5367bb8ab7 |  | note | – – – – – – – – –
label | d6a9263d-3ce2-5165-a6bb-ad2da5448d08 |  | note | RECORD OF CONFORMITY: Thermometer
label | a96b9b2b-1157-5e65-905b-73203a5a9849 |  | note | – – – – – – – – –
label | 1b4998a7-a5fb-594b-bac3-f97c82ad68ae |  | note | WP
label | 7415c02c-e267-5c37-8e3a-615847e7707d |  | note | – – – – – – – – –
label | 24196f28-fe3f-554b-9e29-a5d0d8d8fe0e |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 5f522948-69ce-577f-a0f1-258454ecd101 |  | note | – – – – – – – – –
text | baee7d6b-d77f-5860-bb39-fb2d0ff7c2bf |  | textbox | DATE:
checkpoint-status | 00d23668-8553-4497-8fe6-4daabd2fa01f |  | checkpoint | 2.8 Surface Finish of Wearing Course
label | f377f5ae-cbb3-563d-9631-878d3771ae03 |  | note | FREQUENCY: During paving and after final roll
label | 6dffe214-31e7-5e38-a243-b45990a30471 |  | note | – – – – – – – – –
label | 584a6035-b813-53f0-9d0e-319a772332fa |  | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | c8f0f3ea-f2ef-5185-94f1-cd8f85a3a175 |  | note | – – – – – – – – –
label | f0bcc155-3719-5ac9-93c1-7294adf1d3d0 |  | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
label | 483b9161-b828-523f-b5cd-15f6d059c37b |  | note | – – – – – – – – –
label | c280e987-05e6-5247-b8df-4b5e37dffa8e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c70ad976-a24e-5541-9916-27f3f97347c6 |  | note | – – – – – – – – –
label | 57f31820-7c32-5b17-8d26-be94d84b6a69 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 1be0619b-ac26-59c9-80c0-b538611a9903 |  | note | – – – – – – – – –
label | ae28dd6b-bdb2-5052-90b9-35d17bff755e |  | note | WP
label | 1145f59c-c908-502e-a0ad-6d9ae8e75aa3 |  | note | – – – – – – – – –
label | b65864fb-afb4-5ca0-81ef-ef7382ba193a |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | b688d989-49d4-5b58-b045-0a4b90e7b6a6 |  | note | – – – – – – – – –
text | bf9a2e50-c297-5f51-ae55-07ca9d4ce6a2 |  | textbox | DATE:
checkpoint-status | d6051a7d-072f-47d5-87f8-f069075c45a9 |  | checkpoint | 2.9 Kerb and Channel
label | 65508891-0b10-5070-8d0a-1bde413ba6f4 |  | note | FREQUENCY: During paving and after final roll
label | d6df1b87-182f-5a21-85be-1c1d0c14bb33 |  | note | – – – – – – – – –
label | fdc9c71d-98d4-5e4a-a782-5b9109c82a60 |  | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | 57a71570-2e35-5d9f-9924-18bb48fef380 |  | note | – – – – – – – – –
label | 331bf954-22f2-5b64-914b-e1abd4371d5e |  | note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
label | 3cccf7ad-8386-564c-9d3e-37f713339d1a |  | note | – – – – – – – – –
label | b7b38db5-8770-5e20-8366-0e8d9e357656 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 82b4a942-872e-5c4c-8a56-2bfcf6f806f7 |  | note | – – – – – – – – –
label | 6d0dd7e1-d82b-5082-86f9-64ce50b6eb3a |  | note | RECORD OF CONFORMITY: ITP Signed
label | cccd05d2-7a46-59ec-a2da-6bb91704a07c |  | note | – – – – – – – – –
label | 537ad69f-6e6c-5f1f-9e41-a8334b273f93 |  | note | WP
label | 06ee9a59-b011-58ea-85e4-2655dbc16982 |  | note | – – – – – – – – –
label | 37026608-7b19-50be-9eea-b2beca566cd7 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 801a2630-a5f2-57b7-b60f-c2ce4f1bc607 |  | note | – – – – – – – – –
text | 797c10ae-0130-592b-87a0-6998809f538e |  | textbox | DATE:
checkpoint-status | ef44ddd6-cf52-4e00-b925-e33412a6ee29 |  | checkpoint | 2.10 Alignment of layers not placed against concrete edge
label | 055b1370-27bf-530a-a391-68593762d94d |  | note | FREQUENCY: During paving and at completion of work
label | d80e7b33-8063-5517-b699-fa6df2086509 |  | note | – – – – – – – – –
label | 9c868d6d-4ed9-554a-b9fc-c0c0ff9e1a7d |  | note | ACCEPTANCE CRITERIA:
label | b34f9dc3-d522-5f1c-a9e3-785dafff10fb |  | note | • The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | b99add74-d360-5934-9a0f-10b8b21102bd |  | note | • The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | 702d8bf6-73b3-536e-a6f2-dfe65574c19c |  | note | – – – – – – – – –
label | f5848a49-4c55-5f67-8114-c04254702301 |  | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
label | 3128691c-d618-535b-82f2-c0f1c3a38df7 |  | note | – – – – – – – – –
label | f87b372f-eb39-5200-9d48-a8ee462c74ab |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | aaea8a13-7709-502f-af6c-135b6bed9fa7 |  | note | – – – – – – – – –
label | 7fbd5000-8f37-51c6-909b-59eb807c2525 |  | note | RECORD OF CONFORMITY: ITP Signed
label | ec9de723-e665-5403-a650-d22ea76e6429 |  | note | – – – – – – – – –
label | c780ba70-b5a4-538a-9681-eeb3fc00588f |  | note | IP
label | 23b567f9-4d4d-5c72-aab7-a57defc5f8f3 |  | note | – – – – – – – – –
label | 09d785a6-fc2a-5e9f-9775-4e42054de461 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 3da43786-c8ba-546c-95e4-20570b4aa615 |  | note | – – – – – – – – –
text | ec623902-a3ef-5e9e-964f-f32d43f358f5 |  | textbox | DATE:
checkpoint-status | ed2a4590-9b6f-4174-9a14-dc18a54701dc |  | checkpoint | 2.11 Width of layers not placed against concrete edge
label | 819164bb-c8cd-5b0b-b9ad-d235b0a883a8 |  | note | FREQUENCY: During paving and at completion of work
label | a1419fc2-c204-5b77-a398-2529d29c96d3 |  | note | – – – – – – – – –
label | d281ed5e-02f2-5355-9919-1fc62b514d5b |  | note | ACCEPTANCE CRITERIA:
label | ea65ea4b-3dcf-53e0-8333-7417820bd8cc |  | note | • The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
label | 17716a24-afca-5a07-a9ec-d7c7ee1dde3e |  | note | • The average width over any 300m shall not be less than the design or specified width
label | 13a10a8e-3d25-5c81-8fe5-98eecb08d38d |  | note | – – – – – – – – –
label | 7fd59364-63af-57af-bcac-24e5a30d077a |  | note | REFERENCE DOCUMENTS: 407.23 (a)(v)
label | ead1a923-b237-50e9-ad29-169034b81e97 |  | note | – – – – – – – – –
label | d77abb07-1212-5768-aa49-cdb6eee6ab33 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e6697d6d-9ef7-59fb-97cc-18da975cc173 |  | note | – – – – – – – – –
label | b176eb20-6ed1-5209-bb53-174789fb9df8 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 52493fbe-02ed-56d5-98a4-045330e69fb4 |  | note | – – – – – – – – –
label | 7ca9615a-cdd8-524b-9c6a-716a0da4b0d8 |  | note | IP
label | 0ea35d23-0ef1-5f09-9f6d-7272502a7f9e |  | note | – – – – – – – – –
label | af60cdcd-9a6d-5dc6-bb8a-d07a38a67ca7 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 20743ddc-22ab-5608-9704-c11c895278d4 |  | note | – – – – – – – – –
text | 30be64ac-b44c-57d9-b022-95784b397526 |  | textbox | DATE:
checkpoint-group | 8b58fdf8-a9da-419e-a42f-6e29123d7af3 |  | section | 3 - Testing
checkpoint-status | ef76033e-6302-47f9-9248-ac76937c9bdd |  | checkpoint | 3.1 Compaction
label | dae41ed9-0c87-521d-9921-6f456fba0217 |  | note | FREQUENCY: Per Lot
label | 7740e221-806b-5581-9b32-66a78ccedbc7 |  | note | – – – – – – – – –
label | f9f92dad-9f02-54b8-bece-cab808836ed4 |  | note | ACCEPTANCE CRITERIA:
label | b1d94cf0-b9d7-5380-acc4-98779f2aa3f8 |  | note | ○ For layers <50mm, if characteristic density ratio is:
label | d285bbef-af06-5440-b376-2f8e7aa754d6 |  | note | • 94.0% or greater Accept lot
label | e2c17801-d8df-5e7f-b5f9-386023208f12 |  | note | • 91.0% to 93.9% Lot may be accepted at reduced rate
label | 6a61f6d3-e4ec-5293-9b02-a93e4bdb9815 |  | note | ○ For layers ≥50mm, if characteristic thickness is:
label | 21e701e0-0270-5ac2-aec2-7a62dcea8f94 |  | note | • 96.0% or greater Accept lot
label | 821a65e9-5030-5dff-a695-48f9e9d22377 |  | note | • 91.0% to 95.9% Lot may be accepted at reduced rate
label | 2d01c96e-f2b4-5fd8-a006-000d97730a39 |  | note | – – – – – – – – –
label | 77cee935-12f0-5b24-a909-71b8c8915bb6 |  | note | REFERENCE DOCUMENTS: Table 407.221
label | 15ffba85-4255-5e08-a5ef-f096dc2c054c |  | note | – – – – – – – – –
label | f8406b37-7e30-51a5-bddd-a84ba8fe30ee |  | note | INSPECTION/TEST METHOD: Verify
label | 61b80674-44be-5b50-9d05-bb87e57db70e |  | note | – – – – – – – – –
label | 9621eb95-6902-5ff2-9088-6b7b27f70376 |  | note | RECORD OF CONFORMITY: Test Report
label | 82f2b99d-d0c5-58a7-82aa-0e353022a060 |  | note | – – – – – – – – –
label | 89b23c0a-af84-5377-b296-895aa725031d |  | note | TP
label | 5bdb9e0f-d40c-5acc-b92d-439dd83eac77 |  | note | – – – – – – – – –
label | ebcbcf0f-7793-5e1f-acb2-d048903aafb4 |  | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
label | 67be9e1f-fe12-5235-904b-d18e6a227c3b |  | note | – – – – – – – – –
text | 612a2f5b-e88c-5fee-8f19-8e2d249bf922 |  | textbox | DATE:
checkpoint-status | ce490d3e-01e4-4d76-a964-e47db4add6fe |  | checkpoint | 3.2 Level Conformance
label | 1340f681-928e-507c-ab31-006fd3568aec |  | note | FREQUENCY: Per 4,000m2 at completion of work
label | e15a6aee-587b-5037-99a9-15030fdec04f |  | note | – – – – – – – – –
label | 5f5827ed-cd5e-5546-a5d0-5719f10d56a4 |  | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | c9e3e4c1-3ee4-5ee2-b9eb-e7db81937b4d |  | note | – – – – – – – – –
label | de9356fd-d5eb-5777-abeb-92950158e546 |  | note | REFERENCE DOCUMENTS: Table 407.232
label | d86a7220-4713-595c-a25f-4e73e5dae026 |  | note | – – – – – – – – –
label | 163c845c-8934-5568-8f72-bfdaf0c4706f |  | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
label | 9d825139-094b-5605-a474-76e260cd9ddd |  | note | – – – – – – – – –
label | 0e227fbd-9211-566f-8302-d560b476a917 |  | note | RECORD OF CONFORMITY: Survey Conformance
label | 0d5b1e03-e0eb-5adf-bf97-3d62d0744291 |  | note | – – – – – – – – –
label | 9df82588-9991-5327-b304-6a736548559d |  | note | SCP
label | d27e2644-3add-565a-9a37-40865439301c |  | note | – – – – – – – – –
label | 5e3c1756-0926-5e34-910b-e8358d61bb43 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | 536450ac-1dd0-5079-8455-d0f97fbdd7b4 |  | note | – – – – – – – – –
text | 3289c8cb-3ca7-5f9e-a048-57122605150b |  | textbox | DATE:
checkpoint-status | d94e496f-190e-43c5-b23b-86ce95659c96 |  | checkpoint | Final Inspection
label | 90d24fbc-98d1-5f4c-ab48-6c9dcc3d6de3 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 6fc313d3-d4fe-531f-84a9-760e1f043945 |  | textbox | Print Name:
text | 65e3e709-29b8-595e-810a-49125f821e4c |  | textbox | Position:
text | 6f271c05-635f-5f66-a312-8174ce70b360 |  | textbox | Date:
checklist-sectioned | e0c3dfd1-d6b6-4184-b217-74d0c771267e |  | checklist | ITP-0XX - Profiling | itp |  |  |  | Yes | ITP-0XX - Profiling | 68d66f4b-c699-4d79-8805-b46ccb216c19
checkpoint-group | c20ebecb-967c-4537-b5d1-736943dd4951 |  | section | 1 - Preliminary Works
checkpoint-status | 23878b96-302f-4b93-af93-ce1824416616 |  | checkpoint | 1.1 Check for correct documentation
label | 787b235f-f07e-5520-ae94-fe991838520b |  | note | FREQUENCY: Prior to commencing any activity
label | c808b76a-de47-5000-bd12-2c9a448e7634 |  | note | – – – – – – – – –
label | 4ce0e886-d6da-5e65-9727-28e9db748c3b |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | c7cf21d4-c663-5d0d-9241-b5a519c2281b |  | note | – using the correct and complete set of drawings
label | a2fbde43-3fb1-5698-a6c5-33e83ba3afa9 |  | note | – all drawings are the latest revision
label | 570a2f49-9001-573d-ae21-925f342dde9f |  | note | – – – – – – – – –
label | 8fb52de4-082e-59c0-8881-28797f07ffa2 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | ea44f8b2-5037-501c-bfae-0c8831f7db0f |  | note | – – – – – – – – –
label | e4ae5832-ee9c-58af-ae91-7e23a9858a96 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | b34710f8-7a5f-5b8d-a0fd-0f641e5d8146 |  | note | – – – – – – – – –
label | f2df3d3f-c282-53ef-b9db-73ef36009acb |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1849c4b9-e6d1-5317-9cf2-188be09d9fcc |  | note | – – – – – – – – –
label | cce875e8-e96c-5afa-b55c-dfcc8e1263dc |  | note | HP*
label | e645c0d4-8c7e-538d-bd30-3df59554ae6b |  | note | – – – – – – – – –
label | 3ff7dfa0-8c75-5d05-ac17-7b38810bbf5a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 67120e14-5420-5f68-949d-9990c7d2bf63 |  | note | – – – – – – – – –
text | 23ba41a5-fe2f-5028-85ab-85e960ebba06 |  | textbox | DATE:
checkpoint-status | 89499b17-40cf-49cb-9908-4b3024901661 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 36c8cc31-c5bb-532a-862f-85493170882e |  | note | FREQUENCY: Prior to commencing any activity
label | 68d06acf-4c98-58ae-93e1-6fc5c2d937f7 |  | note | – – – – – – – – –
label | 3fab9e56-f50f-58eb-9cfe-aee403bb952b |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 85776e22-868e-52c5-8185-e1a710626808 |  | note | – – – – – – – – –
label | 86e1a026-5da7-5e22-b762-8b7e8e7a8af5 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 76cde67d-91f6-5859-a2eb-d04a583f277c |  | note | – – – – – – – – –
label | db63d685-10f7-5e11-b206-3dda190723b6 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 24d722e3-4cf0-577b-8179-eeb57e4daa78 |  | note | – – – – – – – – –
label | b09325ad-8f4d-5452-8ed5-471831aa1ea5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 78056396-5820-5e27-b82e-c44fca80a7bc |  | note | – – – – – – – – –
label | d436c5f4-121c-5419-8d81-f2cd7299498e |  | note | HP*
label | c757954c-6fee-5913-8bdb-3ab765c0579a |  | note | – – – – – – – – –
label | 13bce7c0-70e4-5060-9053-1b788a670b0a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
label | 463905e9-4b57-56b5-af4e-80e1e223af19 |  | note | – – – – – – – – –
text | 541f5fbd-eafd-5756-9217-e3bcbd878f60 |  | textbox | DATE:
checkpoint-group | 8800cc6a-1270-4dd8-804b-79f41082f8f5 |  | section | 2 - Construction Works
checkpoint-status | 255262c4-0b94-4098-97b7-ead39c00ee59 |  | checkpoint | 2.1 Profiling Works
label | 3e628fc7-e705-5620-ba7f-3790223ba08f |  | note | FREQUENCY: Each lot
label | 0207147f-47c9-5c19-a0b3-cad9376b9710 |  | note | – – – – – – – – –
label | 22865075-cfbe-5a86-9789-c2f63069b323 |  | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
label | a016cb76-7d65-5eb2-a251-93abcafacfb7 |  | note | – – – – – – – – –
label | b81e12da-01d0-570f-81ee-a52c1b662ce3 |  | note | REFERENCE DOCUMENTS: 402.02
label | 3417e17b-dd46-5266-8561-a640404d9bfd |  | note | – – – – – – – – –
label | dcd8d7b6-8815-5421-b4c7-03b2200a77c4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c3f22372-63fe-5565-880d-5ff962fd229a |  | note | – – – – – – – – –
label | bd4928da-d613-552b-9ce1-65b3f079c291 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b967cd59-91fb-5562-972b-d7baf3c85f36 |  | note | – – – – – – – – –
label | 67c14b30-96aa-56cf-93be-42b65e8f0e6c |  | note | WP
label | f0c96aa8-699b-586f-a9a7-f2995e340ea6 |  | note | – – – – – – – – –
label | 1040df88-14bf-5b5f-9f14-9816ecc58dc4 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | f08996a3-d886-566b-be12-34c2030025fe |  | note | – – – – – – – – –
text | ca38436e-03fe-5733-a21b-b55da236f2fa |  | textbox | DATE:
checkpoint-status | 3b540bfe-166a-47a2-99fe-de4efc693362 |  | checkpoint | 2.2 Depth check
label | 3b1d5123-7be2-543c-8c6b-cfae4a1d4869 |  | note | FREQUENCY: Each lot
label | f05b1198-800d-54e4-9538-25615696703a |  | note | – – – – – – – – –
label | c4cfdf49-ac8f-52d6-884d-b15f166e3bb1 |  | note | ACCEPTANCE CRITERIA:
label | ed139e57-91b0-576d-8c1c-4724b840c74a |  | note | • Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed.
label | 439f3754-ffea-5a62-af35-213d3a739b8d |  | note | • After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
label | 68272f1d-adf7-51ae-80aa-d88ba839034e |  | note | – – – – – – – – –
label | d6b7538c-8a57-547c-a0ad-ef687772c0eb |  | note | REFERENCE DOCUMENTS: 402.02
label | 280fe3ea-7421-5c3c-80da-fbea594fd334 |  | note | – – – – – – – – –
label | 5b494918-4b88-5d76-a89d-45eb5a3043be |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 30ebb786-8f06-5ff6-b3a5-902e685f4fa0 |  | note | – – – – – – – – –
label | 56b82511-5da3-5ce1-b642-f1f261712b12 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 24e00ed0-2a73-55c4-b5c7-2157f8bdcd93 |  | note | – – – – – – – – –
label | 138c112d-5efb-5418-bca7-2f10f1c2eb31 |  | note | WP
label | ca016d91-fc02-57e1-bb44-89cb7540dc04 |  | note | – – – – – – – – –
label | 8425bb33-41e4-5a6d-b9c5-a2bfdb6b64fa |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 268d5b5d-3939-51b9-92fe-4d59b5290cea |  | note | – – – – – – – – –
text | 8589293a-aab7-5692-8d1f-89038747100e |  | textbox | DATE:
checkpoint-status | 310d98dd-fbfb-4d60-af3b-779f4270e71b |  | checkpoint | 3.3 Temporary ramping (longitudinal)
label | 51991f31-04fa-5644-b06a-1ead87c68fa2 |  | note | FREQUENCY: Longitudinal edges
label | ce890a26-d713-556d-97c4-4151b74ae38d |  | note | – – – – – – – – –
label | 3dcd2650-7ca8-51af-8269-fafa3130a76a |  | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
label | d0c87cf0-3bde-59fd-9371-6e7a1b162d27 |  | note | – – – – – – – – –
label | e193038a-e34f-56ea-86ed-7222549ec56f |  | note | REFERENCE DOCUMENTS: 402.05
label | 57bd09ab-f9c7-57ff-8830-46b2d925f3fb |  | note | – – – – – – – – –
label | 0bae7053-e35a-591d-90d1-e126b9f40d8e |  | note | INSPECTION/TEST METHOD: Verify
label | 4d72f14e-e2d5-5fbd-b054-e8c92966db68 |  | note | – – – – – – – – –
label | ad0c59db-ca21-5ff4-9ea2-1550e9df10bc |  | note | RECORD OF CONFORMITY: This ITP signed
label | 46ede4c9-a525-53a1-9a57-c22e4ba83ffe |  | note | – – – – – – – – –
label | a83eadb7-94d5-5f9a-b245-57450faf5567 |  | note | WP
label | c55b6a64-e275-52ba-ae7e-9f812324971e |  | note | – – – – – – – – –
label | f5253c29-d555-54a7-9e35-07764289b4dc |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 162f5f6b-7bee-5ee3-b7fd-5024f880396b |  | note | – – – – – – – – –
text | 17aa3d96-6edb-5b1c-a167-e0a5119970d7 |  | textbox | DATE:
checkpoint-status | d8176a58-1300-4cca-9927-ebfaa675809c |  | checkpoint | 3.4 Temporary ramping (transverse)
label | b9e86fd8-6642-5349-b55b-bb4eaca8eb6a |  | note | FREQUENCY: Transverse Edges
label | 348b121d-0d2b-539d-a59d-2b1a5453b97e |  | note | – – – – – – – – –
label | c92375d2-0c8b-5e49-bd38-016c1a6aa557 |  | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
label | 0b585ff3-b7c0-5034-8a84-8ba6a132042c |  | note | – – – – – – – – –
label | 12ed850c-c6e4-5123-b4c1-5a56671d790b |  | note | REFERENCE DOCUMENTS: 402.05
label | bb56cf86-a9fc-5f12-93f1-8d18a5ea4983 |  | note | – – – – – – – – –
label | b6acc82b-5a66-5363-b9af-2e1874240d83 |  | note | INSPECTION/TEST METHOD: Verify
label | 46eca60c-2ade-5211-9217-af0621109351 |  | note | – – – – – – – – –
label | c8c69947-e37e-5526-9ca4-da01de5d7199 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 59b76026-b50a-5354-ba7e-c0cbe9d3a467 |  | note | – – – – – – – – –
label | 341edb45-dc5f-5e9d-af48-d3049279fb95 |  | note | WP
label | dfce0816-0eea-519a-a696-e1fa4d336734 |  | note | – – – – – – – – –
label | 0d8a188c-835c-5fbc-9ce1-b15d93ef87b9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
label | 4a3a7d1f-3c42-5402-90f3-f4240170abbb |  | note | – – – – – – – – –
text | bd29d11a-c27b-59ba-a548-c8f782f69fc6 |  | textbox | DATE:
checkpoint-status | 7b953d36-faca-4d21-900c-d0d58eee4635 |  | checkpoint | Final Inspection
label | 9be0b008-e218-5322-9e07-11999c0bc897 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 9ab60268-de5c-50c9-bc05-44ec66ce0f39 |  | textbox | Print Name:
text | 9d40a475-48bf-543b-bea3-9c5e268d69a5 |  | textbox | Position:
text | 22408003-bf38-5a6f-80bf-461e59b52ed0 |  | textbox | Date:
checklist-sectioned | 9064c1c7-e108-42f4-b0e5-e7446a0debbd |  | checklist | ITP-01-012 - Hot Mix Asphalt | itp |  |  |  | Yes | ITP-01-012 - Hot Mix Asphalt | e43e4a72-9220-415c-997c-143ad45f4010
checkpoint-group | 17991b5c-285f-4f55-b14d-63f3e1491464 |  | section | 1 - Construction Works
checkpoint-status | bd219442-70d6-4d2f-9dbf-111c5b4a0597 |  | checkpoint | 1.1 Submission of Mix Design
label | 078d2f2c-204c-547f-9873-5796af7912ac |  | note | FREQUENCY: Prior to commencing paving
label | 298c4a1f-b36d-57ae-b52e-4d3dcc1360b5 |  | note | – – – – – – – – –
label | fba76790-5d98-5c86-a192-7f9ac9fa21f3 |  | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | eda649c0-9f37-5ef4-bc28-65051a4ff8a4 |  | note | – – – – – – – – –
label | c9ec3802-6c1c-5016-b631-b7ec0b8dc9d6 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
label | c4f2aa28-c03b-5466-a4b6-6685d2aae0a3 |  | note | – – – – – – – – –
label | 6c135a7a-57f4-5980-bcc3-c34dda005be7 |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | b978f386-8baf-5aa8-bd48-a8d84b736807 |  | note | – – – – – – – – –
label | 3a4d9b27-1657-553d-8cd5-508b5d47e392 |  | note | RECORD OF CONFORMITY: MRPA approval, Completed ITP
label | fe24f0b8-1bbb-5326-88c8-c280cdd4aacb |  | note | – – – – – – – – –
label | 09254e7c-3d4c-5c77-b2be-3e141cb7a5fb |  | note | HP
label | c1064ea8-8343-5ade-9af4-da182c2a8709 |  | note | – – – – – – – – –
label | 6e18e562-a000-5808-b7ed-7dc897b0d44f |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
label | 6ced67a9-6c6c-5718-9e6e-b65aba7a1fa6 |  | note | – – – – – – – – –
text | 4eab24d5-75dd-5e3b-82d3-31c99e873b0e |  | textbox | DATE:
holdpoint | 9e826bb9-51e0-4e2f-96dc-00876f620cfa |  | signoff | HOLD POINT AUTHORITY
checkpoint-status | b52a6d42-77e7-42e7-8d1c-0279aaef4194 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 2f1e742c-9fd3-5e51-a50d-3c1e7a1f8667 |  | note | FREQUENCY: Prior to commencing any activity
label | f4d1f39f-1a7a-568d-ac18-6b75dfadabb3 |  | note | – – – – – – – – –
label | c8393150-738e-5ad9-9dd8-9d3f6eecc5df |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | f3a6cef1-2385-54c2-8e69-345f77bec33e |  | note | – – – – – – – – –
label | 1033a6c1-13c3-50a3-8ac4-c98b34d25fde |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 842e4ed7-e64a-5ee0-a647-a6f7fa17dcdc |  | note | – – – – – – – – –
label | 0efdcdea-add5-554d-9fbf-39b23fe210ea |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 524210bc-f8ec-54c0-b098-a88a419d6ba8 |  | note | – – – – – – – – –
label | 92bd2fe6-6937-5a16-84f2-3a7f88f2ff14 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 46fcff5b-69f3-58ae-bd83-9ce96a53221c |  | note | – – – – – – – – –
label | d3e8706a-28e2-5b0e-92ad-b8a8415b4fc4 |  | note | HP*
label | a7dcf41f-5982-5f52-b8cf-447c914499e8 |  | note | – – – – – – – – –
label | 0fcc75bf-19c3-5a63-a562-ea029cb390d8 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 7e5d059b-0930-5acc-be99-2782612bd192 |  | note | – – – – – – – – –
text | d3cfdad2-52b3-589b-b449-b05c56111923 |  | textbox | DATE:
checkpoint-status | ada59933-fdb7-46d4-9c43-ecca403ba4e7 |  | checkpoint | 1.3 Site Inspection and Base Condition
label | 60a26afe-576a-5004-9ea6-d22f240f81fe |  | note | FREQUENCY: Prior to commencing paving
label | 4d23edfd-57e2-50ee-9c9c-485d04c0537b |  | note | – – – – – – – – –
label | 00bf2d5e-98ca-5326-a1ec-28a69058f195 |  | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | 127baf94-7906-5b39-ac0c-2cbe1731887d |  | note | – – – – – – – – –
label | 7a56f5b9-8b1a-57e2-9ae2-8e445a725da6 |  | note | REFERENCE DOCUMENTS:
label | 9bcba668-e890-56f4-9cba-223d7e23b33b |  | note | • 407.17
label | fece5616-dda7-5b74-a89c-8bb20e433425 |  | note | • AS2150 10.1
label | 7909c992-0ba3-56a7-8748-ca70b8dce0b1 |  | note | • AS2150 10.3
label | aab1804f-4007-5162-9d40-1c012f99015e |  | note | – – – – – – – – –
label | e176de28-4bfa-5ea0-8582-4f043d8f5e5b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c3985aad-9daa-5f5d-96a7-ca1258a1910d |  | note | – – – – – – – – –
label | 878eb012-9097-56dd-9f10-61cb08a45656 |  | note | RECORD OF CONFORMITY: ITP Signed
label | e3594e5d-e8ad-5597-b77c-2ad9df79a27c |  | note | – – – – – – – – –
label | 6b1596ed-d11c-5e2d-b283-27eb87e34d6a |  | note | WP
label | 19af633d-c475-5134-8ec5-eb0bebc94083 |  | note | – – – – – – – – –
label | b74aebfe-6856-5648-bed9-247d72932abe |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 09f45827-4b58-5ff6-95cb-7f1d35b34b8a |  | note | – – – – – – – – –
text | e5368320-e8d8-5b8e-ac56-00cfeb7b1c66 |  | textbox | DATE:
checkpoint-status | 809ba6fd-5615-42a1-ae6c-baae31ba5c66 |  | checkpoint | 1.4 Ambient Conditions for Placing
label | cc925b91-174f-534a-90b4-4b553e14211f |  | note | FREQUENCY: Prior to commencing paving
label | aef56389-3a89-5480-be22-215ad02bac75 |  | note | – – – – – – – – –
label | b4062f0f-c53a-5380-a95f-f342540614ea |  | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | d136b333-7e0f-5028-b09a-18027341bc84 |  | note | • Base & Intermediate Courses: 5°C for conventional binders or
label | d897dd40-374e-50eb-9ccf-3681f6b0ee51 |  | note | • 10°C for PMBs & Class 600
label | 089ac85f-b2a3-5469-ab00-69fc592eff89 |  | note | • Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | daab664a-1e26-551c-bd30-1a93e07c002e |  | note | – – – – – – – – –
label | d9383e48-5df8-5dfa-90ed-bc2a0f035d48 |  | note | REFERENCE DOCUMENTS: 407.17
label | a3563eda-4b09-5afe-acd5-4590f9035d01 |  | note | – – – – – – – – –
label | 7ce5fcd0-c6df-528b-a770-fb8e2da589d8 |  | note | INSPECTION/TEST METHOD: Verify
label | adbc539a-7795-55de-970b-b8549a46845f |  | note | – – – – – – – – –
label | caa502da-857f-5a2c-9910-318f1b80f725 |  | note | RECORD OF CONFORMITY: Thermometer
label | bd7cc401-944f-5338-a850-e7672ee14447 |  | note | – – – – – – – – –
label | e4f461fc-9d8b-5cff-998c-0f7493a60696 |  | note | IP
label | 3d866759-adca-5aca-aee6-d4cb2a22cbb0 |  | note | – – – – – – – – –
label | d436c22d-c23b-5395-9317-805e984d95e9 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 75b549a6-1d00-5096-9a6e-505d59a6041e |  | note | – – – – – – – – –
text | aeaadbd9-5b39-5f21-aaae-9a62da4b1745 |  | textbox | DATE:
checkpoint-status | 3d1656f9-d616-4f06-916f-e77c1a32e59f |  | checkpoint | 1.5 Planning of Joints
label | ed6ad56f-991d-59ec-993f-c4f84ecf9b9e |  | note | FREQUENCY: Prior to commencing paving
label | 1130b496-a637-50f4-bc73-1c7590a45d6b |  | note | – – – – – – – – –
label | a650510d-b3db-5fa4-a50e-cf242b07feb3 |  | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | bacb8a79-1eba-5ec2-a87b-3bedf43d2e87 |  | note | • Transverse Joints Offset from layer to layer by at least 2m
label | e532eb93-45dc-5cc1-9ffd-9ca451264d51 |  | note | • Longitudinal Joints Offset from layer to layer by at least
label | 9f815794-e69b-580b-95af-e46248ba760d |  | note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | fcce5eb7-92ac-581c-8a39-183bbc228125 |  | note | – – – – – – – – –
label | 9286a4e1-b4ac-5695-bb31-265f1b41a854 |  | note | REFERENCE DOCUMENTS: 407.21 (b) & (c) Pavement Drawings
label | de6e14b3-5e61-5f1f-828b-6593da53ff5c |  | note | – – – – – – – – –
label | ceff3c1d-8dea-513a-983b-4238ee1c713a |  | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | 8d6a8b9e-67fb-5280-9017-f76830fa8b18 |  | note | – – – – – – – – –
label | c6f7b758-f504-58e5-a9aa-604f31e39c37 |  | note | RECORD OF CONFORMITY: Paving Plan
label | d96c9d83-e294-5803-bc0e-09fa79a1d0d8 |  | note | – – – – – – – – –
label | 73a199fc-1ade-55bc-a8cd-086263a02d20 |  | note | WP
label | 721f86e8-6378-59fc-8f4d-3d0a8e3e0be2 |  | note | – – – – – – – – –
label | b51d1701-feda-5108-b696-199ec2e3e21f |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
label | aca33b90-83ac-5464-995c-44f10608e6b9 |  | note | – – – – – – – – –
text | cbcc7d69-dcf8-5c22-a5fb-4f40a5527b29 |  | textbox | DATE:
checkpoint-status | 18e837c2-8d48-427b-a4bd-3faef194b120 |  | checkpoint | 1.6 Longitudinal Joints with existing Pavement
label | ec8b140d-5d73-59f9-ba3b-d78046cc7af4 |  | note | FREQUENCY: Prior to commencing paving
label | a4b5c22e-7bf9-5053-ba5a-cae28bab7878 |  | note | – – – – – – – – –
label | fc07acf4-caeb-5709-9487-3658c722322a |  | note | ACCEPTANCE CRITERIA:
label | 88df8eb6-929f-56c6-8f94-698ed690e270 |  | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | b59868d9-47fc-5539-9a2f-1138cb51b09d |  | note | • Depth of step to be cut to the full depth of each indiviual layer.
label | 26a15ddb-6478-5983-ae17-a085bb408dbf |  | note | – – – – – – – – –
label | 99c71117-a13f-5f1c-bc0a-9b21a9bb8098 |  | note | REFERENCE DOCUMENTS: 407.21 (c) (ii)
label | 00ba5275-7e15-5492-9614-6e1cd2d4367e |  | note | – – – – – – – – –
label | f4323960-6f04-556f-832a-0d46caf5a725 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 0155fb54-d9ab-5b33-a1d6-3103e18abd08 |  | note | – – – – – – – – –
label | 537c8b79-0974-5f6e-8ae1-88b126c76fd0 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 8c901f8e-0962-5c69-851e-f378c44d2e89 |  | note | – – – – – – – – –
label | 5c098130-865b-5717-9863-a21c69a1cff0 |  | note | WP
label | 9ef1426e-46fb-5cb6-85df-e678a1192895 |  | note | – – – – – – – – –
label | bc6e4b79-43eb-52f8-961a-7d9260f999a3 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
label | 59ef7245-2728-5b29-9a67-47ad1eafcffa |  | note | – – – – – – – – –
text | b5694312-0138-56c5-9dd0-8373f3da87d1 |  | textbox | DATE:
checkpoint-status | dfd42352-e11a-4815-bd6e-4afb9a824876 |  | checkpoint | 1.7 Lot Size
label | 50aa6eea-3eac-55ea-b81c-ba44aafe972e |  | note | FREQUENCY: Prior to testing
label | 418f6c33-0c47-530f-acbc-d661d21edcff |  | note | – – – – – – – – –
label | 93fa548d-ee4e-5e9c-a394-f7813a6d8f7b |  | note | ACCEPTANCE CRITERIA: Lot size for determination of testing shall be in accordance with 407.27 (b) (ii), where less than 500 m2, reduced testing may apply
label | c478a79f-7fc8-53ca-9d6c-733de3a4efdb |  | note | – – – – – – – – –
label | 68d385fe-6d44-59bd-9017-8607875c4069 |  | note | REFERENCE DOCUMENTS: 407.27 (b) (ii)
label | 224c4ae5-5b4e-5a2a-99c9-6f06252bab9e |  | note | – – – – – – – – –
label | 790f6179-aabd-5f87-9185-540fb69a5ff7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cbb8496d-f30f-5dc6-b48f-735b28eb5d6e |  | note | – – – – – – – – –
label | 138a8641-2c8c-5757-9455-959242d4ec0e |  | note | RECORD OF CONFORMITY: ITP Signed
label | dd4f7eb1-672f-5257-baca-4c8d5c1cc038 |  | note | – – – – – – – – –
label | e4867440-8c16-5cd5-8995-94d539a5b97b |  | note | IP
label | 8d34aa50-3243-560a-8ca2-f105363871f2 |  | note | – – – – – – – – –
label | c19821dd-abcf-5d90-a886-31bbcd319fc7 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
label | 7598219d-1df6-5b79-82bf-a1777bad1126 |  | note | – – – – – – – – –
text | 2d6af7f4-7a45-5d83-831a-23afd4fdfba4 |  | textbox | DATE:
checkpoint-group | b42bc838-62f0-49c7-9b50-d3d7566df211 |  | section | 2 - Asphalt Placement works
checkpoint-status | 92ab563c-2536-4b63-bba4-9c3ee9af069b |  | checkpoint | 2.1 Tack Coat
label | 9c6c7a22-64eb-5f2f-aab4-f89441787e1e |  | note | FREQUENCY: Prior to commencing paving
label | 5c23dbe7-ee4f-596a-b740-a90637147322 |  | note | – – – – – – – – –
label | fa4c0718-279c-5708-bb5b-2b5b7b924832 |  | note | ACCEPTANCE CRITERIA:
label | 9a9e99d2-20e9-516f-8dab-090121741602 |  | note | • Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
label | 53f5a2ca-68cc-5ce1-9014-d1dcf15c40c9 |  | note | • Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | 335387b7-2946-5b6a-b37c-9d3c92ed225b |  | note | – – – – – – – – –
label | 098b8bad-c5bd-597d-9970-8a97c1b55f21 |  | note | REFERENCE DOCUMENTS: 407.19 AS2150 11
label | f087dad2-51ac-586e-9068-fb75130e9f1e |  | note | – – – – – – – – –
label | c5ea7982-655c-5a86-9bba-debb87a2c29e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 246f40e0-5ac1-5b6a-9f60-004faa285e86 |  | note | – – – – – – – – –
label | a45eb08f-101c-58ef-ae8a-fb4bfe419f77 |  | note | RECORD OF CONFORMITY: Spray area
label | b92347a7-172b-596b-813b-6dc3522a0cdb |  | note | – – – – – – – – –
label | f17ed852-f865-5af2-b252-54d892a1d76d |  | note | WP
label | 89b78feb-3eb2-516b-8481-7082edb55975 |  | note | – – – – – – – – –
label | 04f571c9-7b79-5f88-a3f4-1624fa41c98f |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 2ad55b65-266e-5884-9ae3-b5de69b17fb2 |  | note | – – – – – – – – –
text | 1af11a34-bed5-5b27-a8f1-6da589292240 |  | textbox | DATE:
checkpoint-status | b351c882-d8fb-4059-9a9d-c8366d37160e |  | checkpoint | 2.2 Commencement of Placing
label | daceeba2-c5c7-5a46-96f5-20372012c3ba |  | note | FREQUENCY: Prior to commencing Paving
label | 63333606-b278-5158-8811-55c08907a3cf |  | note | – – – – – – – – –
label | 83c43a71-3bda-5768-883e-972578a00506 |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | a802810b-6e15-5763-b630-5640951a0fcf |  | note | – – – – – – – – –
label | b6184926-5935-5af2-a7f7-f1177c079362 |  | note | REFERENCE DOCUMENTS: 407.23
label | f0df8e0a-7422-5da5-8e9e-1462a9bc086c |  | note | – – – – – – – – –
label | d7628213-8427-5f07-8e4a-37a64bc50e5d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 80f0ac54-bee5-5f05-9032-90037c14e3d3 |  | note | – – – – – – – – –
label | c9206bbe-8719-51eb-8222-0a9d5333c796 |  | note | RECORD OF CONFORMITY: ITP Signed
label | f369cd03-2dbc-5b13-927a-d108c2a20b07 |  | note | – – – – – – – – –
label | 04191a30-ac30-55be-9609-e6b5b8e0b989 |  | note | HP
label | 5df9655e-6b4e-5f4b-8f38-80f7d6bfad66 |  | note | – – – – – – – – –
label | ee07c80a-a745-53c1-823c-a5880c89b523 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
label | fbc930b5-3138-58f2-a74f-8f2f6eab1d5f |  | note | – – – – – – – – –
text | 2f4f8545-d287-5bc2-867d-7f541931ec72 |  | textbox | DATE:
holdpoint | b621f658-3d08-4299-b04f-72c6bd67dd07 |  | signoff | HOLD POINT AUTHORITY
checkpoint-status | c858ae54-d46c-42f5-b12f-dcc44712d29c |  | checkpoint | 2.3 Mix Design Confirmation
label | 35a32dc7-735f-5f7d-bf68-8435af14376a |  | note | FREQUENCY: Each lot
label | 711f74e7-e74e-5ae3-a75e-24acf6b296fc |  | note | – – – – – – – – –
label | b0788dee-99d6-55e9-959e-44f1b105b5be |  | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | 117ad2f3-da3e-5655-a2ac-7ec9059d4ff5 |  | note | – – – – – – – – –
label | 74391539-9e63-5581-9f85-3e5371ad6238 |  | note | REFERENCE DOCUMENTS: 407.2
label | e9c38d61-ead3-5576-bfae-de6f2c6a7a2e |  | note | – – – – – – – – –
label | 5226d7f4-bd83-588d-85a6-b5fbb565676e |  | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | afd05478-c90b-5705-9a8f-84e784b3a584 |  | note | – – – – – – – – –
label | ebba5f7b-e6dc-590f-88a6-6ec9f029a965 |  | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
label | 86f6a508-adbc-5f9b-baf7-84c02e30c4b1 |  | note | – – – – – – – – –
label | c04c28d3-2ce0-500f-99bd-c05bd770f3c7 |  | note | HP*
label | b43b900d-d15e-5fb0-9355-7e9736c4f98b |  | note | – – – – – – – – –
label | 5c5c56ec-a33f-55d5-97fc-90dc75ca09de |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | da9f0995-1f61-5922-bd41-f508ac0352ef |  | note | – – – – – – – – –
text | 900cd7e9-cc45-5ce3-90e9-b864f5ef1ffa |  | textbox | DATE:
checkpoint-status | 16680e2c-029f-4900-a841-68c90e946f24 |  | checkpoint | 2.4 Delivery of Mix
label | 80e24168-999b-5970-9d0c-8b85d50c511b |  | note | FREQUENCY: Each load
label | ebab6c21-674c-5a5a-a1eb-59b7a97bc608 |  | note | – – – – – – – – –
label | 4a5014f2-87db-5e93-8ff4-fe08a302c84e |  | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | 9b198f55-9a54-50d6-8b8f-cd13eb2b50eb |  | note | – – – – – – – – –
label | 1360fb9c-9bcc-526e-87f8-99b7cfd4ff1a |  | note | REFERENCE DOCUMENTS: 407.2
label | bacacb82-21c2-5527-ac61-1289e16f2f6e |  | note | – – – – – – – – –
label | 12640b53-cee2-55e9-ae48-fd1691eada19 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1e9349ef-2c10-590d-b393-4281d5898dca |  | note | – – – – – – – – –
label | 12dfee23-4754-5d52-914c-894b9f49e8da |  | note | RECORD OF CONFORMITY: Delivery Docket
label | 2b7b45d2-d8d9-5a15-b585-c23790b185e7 |  | note | – – – – – – – – –
label | f8b84260-4ab6-5efa-8c88-d274208795c0 |  | note | WP
label | 16c16dc4-7daf-5d39-8e24-1e6c5be93c75 |  | note | – – – – – – – – –
label | af594cac-4463-53dd-93ec-5e1a7539d999 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 3a400099-83a7-5988-967f-163805adbc16 |  | note | – – – – – – – – –
text | 54435672-4eba-5166-8523-fba8af13c9f5 |  | textbox | DATE:
checkpoint-status | e716a9de-9d10-4312-b429-8c18a4cb5bb5 |  | checkpoint | 2.5 Traceability
label | 4acc8b84-9f39-55d6-916d-161cfb0b4143 |  | note | FREQUENCY: Each lot
label | 97e8d276-54e9-5f6f-8f54-ba4b5244fb5f |  | note | – – – – – – – – –
label | 7e6ea7e7-047c-5e76-afcf-478808dd8d24 |  | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | 72cd6b14-3d83-5712-8482-58feb60660a2 |  | note | – – – – – – – – –
label | 15c47f04-023f-5beb-bcaa-a240eda6c134 |  | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | 53c73868-f441-5fb4-9d9b-6b8c0ec431c3 |  | note | – – – – – – – – –
label | a958b0fd-03b5-5d45-b936-7284f900458d |  | note | INSPECTION/TEST METHOD: Verify
label | 29065a70-3442-5ec6-9671-47b7b7a5c18b |  | note | – – – – – – – – –
label | 09c3d0ad-7ca1-592f-9623-640b4620f118 |  | note | RECORD OF CONFORMITY: Daily Lot Record
label | 5bac213c-9990-5e14-95a1-cca2d625b0ec |  | note | – – – – – – – – –
label | 3a2a6e64-bd3d-5a20-967e-5e36ddb1f6cf |  | note | IP
label | 94366e90-65eb-56ea-8602-b264fef22ccc |  | note | – – – – – – – – –
label | bd7de729-9a45-53c2-ac45-315756163f32 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | a5449d20-775f-5333-8a41-ddb22cfbd46e |  | note | – – – – – – – – –
text | 7d0aeec1-b58f-5f59-b433-0359008a72e3 |  | textbox | DATE:
checkpoint-status | 67be5a71-3697-4cbc-9ce4-70131010ab34 |  | checkpoint | 2.6 Layer Thickness and Level Control
label | a350fd6b-2d21-560c-846c-7d28ba15f7da |  | note | FREQUENCY: Regularly during paving
label | f2414019-0a89-509e-86f2-d7bf364665a6 |  | note | – – – – – – – – –
label | 16cbde87-3509-558f-be88-689a788419c7 |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | 5fa3866d-ad35-57de-81c5-67ddacc99634 |  | note | – – – – – – – – –
label | 0b4d4ffb-fc2e-5089-9ca6-0668e4e724a2 |  | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | ae53895a-9335-5076-a879-e8a3d3fe2cb1 |  | note | – – – – – – – – –
label | f8a0d799-ca16-5d2d-a605-f2a5837e4050 |  | note | INSPECTION/TEST METHOD: Verify
label | e8b93484-9e56-5074-8f94-f14664b1e907 |  | note | – – – – – – – – –
label | f23c71bc-2213-5002-9da0-d7a31f4b6852 |  | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | acba2ce3-2b78-550e-9900-9394a7afe623 |  | note | – – – – – – – – –
label | e22cdfe9-335e-5139-9077-7d5e896c0cbf |  | note | WP
label | 11bc18bd-1696-5b03-adec-45e76d4b54de |  | note | – – – – – – – – –
label | de15685b-dd7c-5b51-a9da-c20a4bb6814b |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 9ccd139d-7a6e-5138-b256-e475edab3668 |  | note | – – – – – – – – –
text | d4b424bd-1f75-5486-8ff1-895812356d76 |  | textbox | DATE:
checkpoint-status | cca2f668-025c-4d7c-8f7a-967fdd9941b6 |  | checkpoint | 2.7 Paver Stoppages
label | 0d5ffd7f-d99e-5955-a72f-3f1cfe6f7b71 |  | note | FREQUENCY: If paver stops
label | 2f45ed72-e407-5739-b31b-671bbf335c91 |  | note | – – – – – – – – –
label | 22e271dc-886d-53a8-aa4b-aa163c695dce |  | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | 2c0e3aaf-1bfc-5b75-9d3e-85d958b263ff |  | note | – – – – – – – – –
label | 0993798a-8ea6-5d98-8ae3-9b82f44c8e67 |  | note | REFERENCE DOCUMENTS: 407.25 (c)
label | 83f30bfd-af02-54d0-83b3-ef1a0d05e465 |  | note | – – – – – – – – –
label | 10a7f517-12f7-5ab5-9bbb-b3725ac5d41b |  | note | INSPECTION/TEST METHOD: Verify
label | a3d39708-7444-5f00-b33c-1f98ebae6f6a |  | note | – – – – – – – – –
label | a2912627-5d2a-5ff7-ba22-0e778f27a620 |  | note | RECORD OF CONFORMITY: Thermometer
label | 352aee23-cea0-5b28-a2a0-e656edae3122 |  | note | – – – – – – – – –
label | 85a5f4e6-9c77-5bd7-9c7d-a3aa1dfbfe72 |  | note | WP
label | 6526b3d0-d2c4-5563-b944-156a029cd255 |  | note | – – – – – – – – –
label | cd6ce515-bc51-5eb4-a47c-7cc7ca70e295 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | c436f1aa-c435-59c6-8efb-acbd6f609f55 |  | note | – – – – – – – – –
text | f5602480-b48d-5b5a-bebd-70ee2b75307e |  | textbox | DATE:
checkpoint-status | 7372d863-dab8-4cbd-a52b-2154e1ab475a |  | checkpoint | 2.8 Surface Finish of Wearing Course
label | b051eac9-9ee9-5c1d-8864-971166bc5da2 |  | note | FREQUENCY: During paving and after final roll
label | 8e3c9585-d655-5ca9-9514-fbe126dab4d9 |  | note | – – – – – – – – –
label | 2104eed3-b7d2-51be-9687-ab522b75afcb |  | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | 1778c2fb-81ee-5df4-a682-9f4ae2b73b9f |  | note | – – – – – – – – –
label | 67ca660e-9147-5cc3-bb91-4a7a999d4e66 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
label | 65429f8f-3a47-5416-b4d1-df3ab3ca4cbb |  | note | – – – – – – – – –
label | e42f5eae-bc77-598f-916c-508adfd5fdce |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 76c8e1ef-f437-5883-ae95-ed4cd292b701 |  | note | – – – – – – – – –
label | 55f42efa-d245-5466-930e-4856c03635a6 |  | note | RECORD OF CONFORMITY: ITP Signed
label | e867c700-8df2-5fc3-a7e3-67ba5e0fc433 |  | note | – – – – – – – – –
label | 22408e48-ef28-52e9-b568-b8973b07f3ba |  | note | WP
label | 4231eae9-5b86-543f-9d55-cbf9415652b0 |  | note | – – – – – – – – –
label | 39db1d96-5ca7-5caa-ab9c-3719a8ea0561 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 24e00d79-8c1f-5615-a8f3-c0fa0dbfd72c |  | note | – – – – – – – – –
text | 98a90369-7e80-5fd2-8f76-f9f5907c69c3 |  | textbox | DATE:
checkpoint-status | f311d2b4-8fff-45ac-bfa4-f2bcb60e0bf4 |  | checkpoint | 2.9 Kerb and Channel
label | 004acdc5-691e-5cfe-80fe-f6273ce85eb8 |  | note | FREQUENCY: During paving and after final roll
label | 04b00584-39f7-5e91-8344-21d6324dd51b |  | note | – – – – – – – – –
label | 42c0ec72-f0fc-5eba-abb5-32d5433e5034 |  | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | 05fcc736-83a3-566a-a142-54dc78aa20b0 |  | note | – – – – – – – – –
label | cd91e5e4-8faf-57b8-9f92-89f14be48444 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
label | 3c5757fd-b734-5e58-8b5e-b6fd9fbfde20 |  | note | – – – – – – – – –
label | 90394b55-9e8c-5d7f-893e-d868d0fc4d09 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6019aa86-e247-504f-aa82-48120c7965d9 |  | note | – – – – – – – – –
label | 1ac33809-9fa2-5d0a-9046-de483e1605b3 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 55f9e2c3-2bd7-5d4e-b3c6-1e34be3cf332 |  | note | – – – – – – – – –
label | 22e272f0-6b9b-51d1-b017-9265bf734f21 |  | note | WP
label | cc553060-f2f1-57d5-a678-e0e183f93805 |  | note | – – – – – – – – –
label | 29d23cbe-05b0-5c14-899b-7ea76d7e0738 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | e0c25688-31d9-5e6c-87e5-3a8a1436a562 |  | note | – – – – – – – – –
text | f2b5f8ea-b8c2-5588-ba7d-af72a5fec385 |  | textbox | DATE:
checkpoint-status | fd7b9a81-578a-4d9c-b862-8e7b5540248a |  | checkpoint | 2.10 Alignment of layers not placed against concrete edge
label | 12569536-5cf7-595e-a2cb-ac19a41888e7 |  | note | FREQUENCY: During paving and at completion of work
label | e50ed131-2c6d-5179-9428-e47523e85ad6 |  | note | – – – – – – – – –
label | fe10f192-56ba-51db-8eee-cb6a4c05e284 |  | note | ACCEPTANCE CRITERIA:
label | 9e584fc5-8cea-5a65-8750-eaa1ed9a2eb0 |  | note | • The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | a458af17-27ea-5db2-a948-7be3a73b849b |  | note | • The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | 0e2dd75f-80c7-5cb1-8b0d-94954ad36bf5 |  | note | – – – – – – – – –
label | a19c0ec2-4eaf-5bfe-b502-a282d4852704 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
label | 15f050a0-27b9-5191-9d3a-64f568246c3e |  | note | – – – – – – – – –
label | a5b98005-3960-56cc-a144-0837db693d2d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | fe6be8c7-be2d-5afd-a8d6-37e5f13dc432 |  | note | – – – – – – – – –
label | bbf79549-4fdd-5d56-bd61-da60a8fc45df |  | note | RECORD OF CONFORMITY: ITP Signed
label | 9b1d9b5b-0207-5a27-9543-a67b3da84e6d |  | note | – – – – – – – – –
label | b958de95-2327-5d59-8e2d-4ef66a705071 |  | note | IP
label | 9260919b-15c3-5786-a696-2ccb2898b0f6 |  | note | – – – – – – – – –
label | ab1070ab-0d1b-5feb-a20e-ddfbd6e31b27 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 9e9ce590-f9c4-5eee-a004-f3089b5c885b |  | note | – – – – – – – – –
text | 903eb813-9b76-5ba0-bef0-ff20d2690d6c |  | textbox | DATE:
checkpoint-status | 6ceb5306-d54b-4e82-8d46-32caabedbfb0 |  | checkpoint | 2.11 Width of layers not placed against concrete edge
label | 06ecb0de-3944-5259-8e9f-d9bd15695729 |  | note | FREQUENCY: During paving and at completion of work
label | 211f0dc0-ee13-5727-b8c3-dd38b968504f |  | note | – – – – – – – – –
label | 38f8bebb-bde0-5cc6-90ae-b2ba121b698b |  | note | ACCEPTANCE CRITERIA:
label | 04ca08e9-22f4-50dc-b44a-ce7a516018a7 |  | note | • The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
label | 1847a9a2-0458-57d6-a21a-1f21f12a5d9b |  | note | • The average width over any 300m shall not be less than the design or specified width
label | 9f145a01-9f57-5ce1-ac99-d498a400f7bf |  | note | – – – – – – – – –
label | a25c3a1b-f1ee-59cb-b4f3-d856a3d9ac56 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
label | 693236de-3440-5e3d-b1cc-11f30fe2ee98 |  | note | – – – – – – – – –
label | 82120400-4cb9-594d-a123-1838c61e6f37 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 86782a29-a7c4-5e26-8127-27dd3c92ae85 |  | note | – – – – – – – – –
label | 36db32e3-9ecc-5f92-b091-05dd82636bf3 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 12791e41-3efb-5141-9349-c6cc2be58a08 |  | note | – – – – – – – – –
label | 1407ccc5-e3e9-554b-9858-37b1e77e38db |  | note | IP
label | 332c519a-9c76-5962-b186-b6d30c3d3ff6 |  | note | – – – – – – – – –
label | f360f5b5-56c0-5a08-9501-d47a04561cee |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 0a9bf146-c963-52e3-bfc9-58590d74e75f |  | note | – – – – – – – – –
text | 759f4767-85cf-5cf0-8d8a-1fafa1005de3 |  | textbox | DATE:
checkpoint-group | 2bf7e95b-7704-4e2d-9b57-1d18a7634fc8 |  | section | 3 - Testing
checkpoint-status | 48cc50b7-3bdd-405b-9994-2961dd4cd78d |  | checkpoint | 3.1 Compaction
label | d5099b04-bc9c-540b-8052-7aaa7c94b55c |  | note | FREQUENCY: Per Lot
label | d893b2b9-990c-54e1-9f7e-bdd8c1f8e1ef |  | note | – – – – – – – – –
label | 773caf0e-e0ac-5043-966d-c62e84f57ec8 |  | note | ACCEPTANCE CRITERIA:
label | 6566315e-434a-5363-a9df-1f399fd5f107 |  | note | ○ For layers <50mm, if characteristic density ratio is:
label | 173a4a41-20c2-5e2d-94a7-46259c5e8bb4 |  | note | • 95.0% or greater Accept lot
label | fcb66631-ba19-582e-a5cf-895031d5b2d7 |  | note | • 93.0% to 94.9% Lot may be accepted at reduced rate
label | 73d59fd0-2e38-5448-a2c4-7de21d7e5b1f |  | note | ○ For layers ≥50mm, if characteristic thickness is:
label | cbac16ea-1066-5bf0-9fd4-b51dc586ff22 |  | note | • 96.0% or greater Accept lot
label | d454f90a-8ef8-5a8a-aa9a-d144d4a5a85a |  | note | • 94.0% to 95.9% Lot may be accepted at reduced rate
label | 77179e7d-0f7d-550f-b82c-950bf23ceefb |  | note | – – – – – – – – –
label | 1a4bcebe-0f64-5a54-bc90-b348d21b2a3f |  | note | REFERENCE DOCUMENTS: 407.27
label | d2bddc75-62d9-52cf-96e5-c15585d2bf3a |  | note | – – – – – – – – –
label | 130211c4-bcc2-5c96-b84d-2bec80c85ff8 |  | note | INSPECTION/TEST METHOD: Verify
label | 873d96c6-cbbb-5212-bd68-7e93c8b4fc9a |  | note | – – – – – – – – –
label | fb69e3f5-c892-53fe-b03b-08b30e4778ef |  | note | RECORD OF CONFORMITY: Test Report
label | 399330ef-332f-5187-ae0c-642b583300c7 |  | note | – – – – – – – – –
label | 2c8e5517-ec46-54d8-95e3-84fcd40751ea |  | note | TP
label | c293864d-b19e-58f5-9a93-764bb1c65daa |  | note | – – – – – – – – –
label | 3cb1f784-d268-5fdc-bf5b-90a01047db26 |  | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
label | cddacc7f-1ad5-5db9-bcf9-94b1edc3016f |  | note | – – – – – – – – –
text | 632a82d4-8f23-5c3b-b7cb-7bbf8ef59c4e |  | textbox | DATE:
checkpoint-status | 5696a0e1-7c13-49c5-ab6e-2288b8a76eaf |  | checkpoint | 3.2 Level Conformance
label | b10d7990-6ac3-5aa4-8462-ac19e0b7bdfb |  | note | FREQUENCY: Per 4,000m2 at completion of work
label | 903771ac-08b1-5d5b-9df9-fd4cd6252f35 |  | note | – – – – – – – – –
label | 096a127a-0c86-55e0-ae62-bef14538440c |  | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | ce487714-772a-5e74-b29b-38fe4cfb6185 |  | note | – – – – – – – – –
label | e603322f-bcb1-55ab-8436-b5d53b7cb956 |  | note | REFERENCE DOCUMENTS: Table 407.293
label | 251cb530-4846-563a-9452-6a525b344355 |  | note | – – – – – – – – –
label | d2b607ab-9db2-567c-b548-cd34811f733f |  | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
label | 4aaaa5f5-b523-54c0-84a5-08acca03c7c8 |  | note | – – – – – – – – –
label | d726dbf3-08ae-5fc4-9304-774e6231677a |  | note | RECORD OF CONFORMITY: Survey Conformance
label | b8fc0bf8-0fea-5b46-9f57-4abe1126e71e |  | note | – – – – – – – – –
label | 6bf7fa97-6841-5fd2-ba8f-757b4afc8a51 |  | note | SCP
label | 1dbf7072-00fa-535e-bc43-949028a52fb6 |  | note | – – – – – – – – –
label | 63aa8712-aff7-54a5-9650-a2bf2ded845e |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | 95458254-4437-5aa4-8459-bb27cc1633be |  | note | – – – – – – – – –
text | 069ee5c4-87ed-546d-b8fd-5f3b3470d263 |  | textbox | DATE:
checkpoint-status | 4566de0c-4fff-4d70-bc19-c994c71f98e3 |  | checkpoint | Final Inspection
label | 62a91b4f-e403-51f6-8615-be191d9c28cc |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | b6ae980d-1a6c-5303-9e8e-fc21a9a13241 |  | textbox | Print Name:
text | bbe4616b-9df6-5c15-b8ec-33195621b42b |  | textbox | Position:
text | 1b498663-bfad-5a2b-9cb9-b4f498966652 |  | textbox | Date: