## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-040
[11 empty] | Revision : 1 | 2020-12-16
Client: |  | DoT (Roads) |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Profiling |  | Name: | Aaron Hatch | Name: | Ruan Dippenaar |  | Name: | Shaun Kent
Contract No: |  |  |  | Specifications: VicRoads Standard Specification - Sections 402 Removal of Pavement by cold planning
|  |  |  | Structure / Component: Bridge Deck |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 01/12/2020 |  | Date : | 2020-12-16 |  | Date : | 2020-12-16
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Profiling Works |  | Each lot | Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement | 402.02 | Visual Inspection | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A |  | N/A
3.2 | Depth check |  | Each lot | Ensure average depth of pavement removed is in accordance with relevant methodologies. Ensure a maximum of 50mm to be removed per pass. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction. | 402.02 | Visual Inspection | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A |  | N/A
3.3 | Temporary ramping (longitudinal) |  | Longitudinal edges | Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical. | 402.05 | Verify | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A |  | N/A
3.4 | Temporary ramping (transverse) |  | Transverse Edges | Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less | 402.05 | Verify | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.