## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-040 - Profiling | itp |  |  |  |  | ITP-040 - Profiling
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Profiling Works
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
note | REFERENCE DOCUMENTS: 402.02
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | DATE:
checkpoint | 2.2 Depth check
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Ensure average depth of pavement removed is in accordance with relevant methodologies. Ensure a maximum of 50mm to be removed per pass.
note | After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
note | REFERENCE DOCUMENTS: 402.02
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | DATE:
checkpoint | 2.3 Temporary ramping (longitudinal)
note | FREQUENCY: Longitudinal edges
note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
note | REFERENCE DOCUMENTS: 402.05
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | DATE:
checkpoint | 2.4 Temporary ramping (transverse)
note | FREQUENCY: Transverse Edges
note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
note | REFERENCE DOCUMENTS: 402.05
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: