## Kevin Hickman Stage 10
Kevin Hickman
Stage 10 (THB18 & THB19)
|  | THB18 |  | Pre Wire | Area is left clean and tidy, and approval to start work is obtained
|  |  | Townhouse Unit 32 |  | Internal cabling complete
|  |  | Townhouse Unit 33 |  | Main cabling complete (Photos Attached)
|  |  | Townhouse Unit 34 |  | Building entry point (Photos Attached)
|  |  | Townhouse Unit 35 |  | Fire boxes installed (Photos Attached)
|  |  | Plinth 9 Commissioning |  | Flush boxes installed
|  | THB19 |  |  | Sub-reticulation installed (Attach Photos)
Townhouse Unit 36
Townhouse Unit 37
|  |  | Townhouse Unit 38 | Termination and Testing | Area is left clean and tidy, and approval to start work is obtained
|  |  | Townhouse Unit 39 |  | Install DB
Fit off DB (Photos Attached)
LAN test internals (Add signature)
|  |  |  | Fit Off | Area is left clean and tidy, and approval to start work is obtained
TV/DATA Fit Off (Photos Attached)
Nurse Call Fit Off (Photos Attached)
Smoke Alarms and CO detectors (Photos Attached)
6 core Fibre spliced (Photos Attached)
|  |  |  | Plinth Commissioning | Nurse Call Terminated (Photos Attached)
MATV Terminated (Photos Attached)
Fibre spliced (Photos Attached)
Power Supply installed (Photos Attached)
Krone module terminated (Photos Attached)