## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Infill Cladding Installation Checklist |  |  |  |  | Yes | Infill Cladding Installation Checklist | 04de9940-a3fd-4ff8-ab3a-903d6e0c671a
checkpoint-group |  |  | section | Cladding Supplied Correct and Unblemished
checkpoint-status |  |  | checkpoint | Panels chip, scratch and crack free.
checkpoint-status |  |  | checkpoint | Cladding type correct.
checkpoint-status |  |  | checkpoint | Cladding colour correct.
checkpoint-status |  |  | checkpoint | Cladding dimensions correct
checkpoint-status |  |  | checkpoint | Cladding penetration positions correct.
label | a8f030d5-964b-5429-afdb-17e47507fea1 |  | note | (All above checked against fabrication drawings)
checkpoint-group |  |  | section | EDPM Foam Tape Installed Correctly
checkpoint-status |  |  | checkpoint | Foam tape attached as per fabrication drawing details.
checkpoint-group |  |  | section | Vertical Flashing Installed Correctly
checkpoint-status |  |  | checkpoint | Vertical flashing installed as per fabrication drawings.
checkpoint-group |  |  | section | Panels Secured Correctly
checkpoint-status |  |  | checkpoint | Panel attachment positions as per fabrication drawings.
checkpoint-status |  |  | checkpoint | Panels attached using fixings detailed in fabrication drawings.
checkpoint-status |  |  | checkpoint | Panels protected as required contractually.
checkpoint-group |  |  | section | Final Holdpoint/Signoff
checkpoint-status |  |  | checkpoint | Holdpoint 1
holdpoint |  |  | signoff | HOLDPOINT: PM sign off required to proceed.
checkpoint-status |  |  | checkpoint | Holdpoint 2
holdpoint |  |  | signoff | HOLDPOINT: MAIN CONTRACTOR SIGN OFF PANEL COMPLETE.
checklist-sectioned |  |  | checklist | Infill Top Hat Installation Checklist |  |  |  |  | Yes | Infill Top Hat Installation Checklist | 1768bce6-a2c3-409d-9aa0-07f1ac1d7863
checkpoint-group |  |  | section | Confirm Correct Profiles Have Been Supplied
checkpoint-status |  |  | checkpoint | Profile match those detailed in fabrication drawings.
checkpoint-group |  |  | section | Top Hat Rails Correctly Fixed
checkpoint-status |  |  | checkpoint | Mark rail positions from dimension details in fabrication drawings.
checkpoint-status |  |  | checkpoint | Attach rails using fixings detailed in fabrication drawings.
checkpoint-status |  |  | checkpoint | Confirm fixing meet max. span details in fabrication drawings.
checklist-sectioned |  |  | checklist | Glass Installation Checklist |  |  |  |  | Yes | Glass Installation Checklist | 530b73a8-257f-4158-bdf8-5c169163f06c
checkpoint-group |  |  | section | Confirm Glass Supplied Correct
checkpoint-status |  |  | checkpoint | Details
text | 528877ce-31eb-5525-91e8-8b79e358b7fe |  | textbox | Type.
text | cf8181dd-450d-5ec2-940b-afceef70f915 |  | textbox | Colour.
text | 8940989f-8c67-52bf-87d8-0faf5b31c801 |  | textbox | Thickness.
text | afb86902-8832-5614-a4a4-a0f1fd683dd0 |  | textbox | Dimensions.
checkpoint-group |  |  | section | Confirm Glass Supplied Damage Free
checkpoint-status |  |  | checkpoint | Crack free.
checkpoint-status |  |  | checkpoint | Scratch free.
checkpoint-status |  |  | checkpoint | Chip free.
checkpoint-status |  |  | checkpoint | Double glaze edge seal integrity.
checkpoint-group |  |  | section | Setting Blocks & Gaskets Installed Correctly
checkpoint-status |  |  | checkpoint | Profiles & dimensions as per fabrication drawings.
checkpoint-status |  |  | checkpoint | Set out as per fabrication drawings.
checkpoint-group |  |  | section | Beads, Clips, Perimeter Frames Fitted Correctly
checkpoint-status |  |  | checkpoint | Check components correct against fabrication drawings.
checkpoint-status |  |  | checkpoint | Install as per fabrication drawings.
holdpoint |  |  | signoff | HOLDPOINT: PM sign off required to proceed.
checklist-sectioned |  |  | checklist | Infill Horizontal / Vertical Cavity Barrier Installation Checklist |  |  |  |  | Yes | Infill Horizontal / Vertical Cavity Barrier Installation Checklist | 668c0380-58f2-4fb5-b9a2-f1a7f88646cf
checkpoint-group |  |  | section | Confirm Siderise Product Supplied Correct
checkpoint-status |  |  | checkpoint | Check against fabrication drawings.
checkpoint-group |  |  | section | Location Identified Correctly
checkpoint-status |  |  | checkpoint | Check against fabrication drawings.
checkpoint-group |  |  | section | Cavity Barrier Support brackets Fitted Correctly
checkpoint-status |  |  | checkpoint | Confirm against details in fabrication drawings.
checkpoint-group |  |  | section | Siderise Cavity Barrier Strip Fitted Correctly
checkpoint-status |  |  | checkpoint | Siderise label side visible.
checkpoint-status |  |  | checkpoint | Attach using nominated fixings from fabrication drawings.
checkpoint-status |  |  | checkpoint | Fix along centreline of Siderise strip.
checkpoint-status |  |  | checkpoint | Adjacent lengths to be tightly butt joined.
holdpoint |  |  | signoff | HOLDPOINT: PM sign off required to proceed.
checklist-sectioned |  |  | checklist | Panel Delivery Quality Checklist |  |  |  |  | Yes | Panel Delivery Quality Checklist | 67e02892-aac5-4bb1-a945-99c261b906db
checkpoint-group |  |  | section | Panel as per Fabrication Drawings
checkpoint-status |  |  | checkpoint | Check against attached Fabrication Drawing
checkpoint-group |  |  | section | Weatherline Gib & Wrap Contaminant Free
checkpoint-status |  |  | checkpoint | Remove dirt & dust with clean dry cloth.
checkpoint-status |  |  | checkpoint | Remove oil and / or grease with solvent & allow to dry.
checkpoint-status |  |  | checkpoint | Check for sharp objects. Remove or file back.
checkpoint-group |  |  | section | Building Wrap where exposed correctly applied
checkpoint-status |  |  | checkpoint | Air bubble free.
checkpoint-status |  |  | checkpoint | Creases in wrap correctly flattened.
checkpoint-status |  |  | checkpoint | Wrap overlaps correct. 150mm top over bottom.
checkpoint-group |  |  | section | Building Wrap where exposed damage free
checkpoint-status |  |  | checkpoint | Check wrap for cuts, tears, holes.
checkpoint-status |  |  | checkpoint | Repair wrap damage withTescon Extora Flashing Tape.
checkpoint-status |  |  | checkpoint | Apply tape to 50mm beyond damaged area.
checklist-sectioned |  |  | checklist | Flashing Installation Checklist |  |  |  |  | Yes | Flashing Installation Checklist | b3aea8d2-725b-4ad4-858c-0c318d4a1175
checkpoint-group |  |  | section | Interstory Wraps / Flashings Installed Correctly
checkpoint-status |  |  | checkpoint | Check correct flashing profile supplied.
checkpoint-status |  |  | checkpoint | Check flashing is correct length.
checkpoint-status |  |  | checkpoint | Mark flashing position from fabrication drawings.
checkpoint-status |  |  | checkpoint | Secure with correct screws.
checkpoint-group |  |  | section | Corner Flashings Installed Correctly
checkpoint-status |  |  | checkpoint | Check correct flashing profile supplied.
checkpoint-status |  |  | checkpoint | Check flashing is correct length.
checkpoint-status |  |  | checkpoint | Mark flashing position from fabrication drawings.
checkpoint-status |  |  | checkpoint | Secure with correct screws.
checkpoint-group |  |  | section | Flashing Tape Applied Correctly
checkpoint-status |  |  | checkpoint | Tescon Extora Tape 100mm wide.
checkpoint-status |  |  | checkpoint | All fixing screws to be completely covered.
checklist-sectioned |  |  | checklist | Panel Placement Checklist |  |  |  |  | Yes | Panel Placement Checklist | d66c2d3a-e937-4a46-96c9-4a5ecc47bda8
checkpoint-group |  |  | section | Panel Position Confirmed as Accurate
checkpoint-status |  |  | checkpoint | Façade gridlines installed and confirmed.
checkpoint-status |  |  | checkpoint | Dimensions as per approved shop drawings.
checkpoint-status |  |  | checkpoint | Access to complete panel install area available.
checkpoint-status |  |  | checkpoint | All required safety protections in place.
checkpoint-group |  |  | section | Previous Required Work Complete
checkpoint-status |  |  | checkpoint | Sill trays / flashings installed. Check dimensions & positions.
checkpoint-status |  |  | checkpoint | Waterproofing by others complete.
checkpoint-status |  |  | checkpoint | Third party inspections where required completed & approved.
checkpoint-status |  |  | checkpoint | Other subcontractors advised when required to assist.
checkpoint-group |  |  | section | PreLift Checks Complete
checkpoint-status |  |  | checkpoint | Crane Task Analysis sighted & signed by all.
checkpoint-status |  |  | checkpoint | Panel temporary lifting brackets checked and secure.
checkpoint-status |  |  | checkpoint | EWP prestart checks complete.
checkpoint-status |  |  | checkpoint | Safety perimeter established.
checkpoint-group |  |  | section | Holdpoint/Signoff
checkpoint-status |  |  | checkpoint | Holdpoint 1
holdpoint |  |  | signoff | HOLDPOINT: PM sign off required to proceed.
checkpoint-status |  |  | checkpoint | Holdpoint 2
holdpoint |  |  | signoff | HOLDPOINT: Main Contractor sign off required to proceed.
checkpoint-group |  |  | section | Lift Panel Into Position on Building
checkpoint-status |  |  | checkpoint | Secure to building as per approved shop drawings.
checklist-flat |  |  | checklist | Drawings |  |  |  |  | Yes | Drawings | f6c69824-5001-43e5-9bdd-104a45a2dbfe
checkpoint-status |  |  | checkpoint | Drawings attached
checklist-sectioned |  |  | checklist | Infill Insulation Installation Checklist |  |  |  |  | Yes | Infill Insulation Installation Checklist | fdb51f78-7e51-48bf-84a8-dca99802c2e7
checkpoint-group |  |  | section | Confirm Correct Insulation Material Supplied
checkpoint-status |  |  | checkpoint | Check against fabrication drawings.
checkpoint-group |  |  | section | Confirm Correct Coverage
checkpoint-status |  |  | checkpoint | Mark coverage boundaries from fabrication drawings.
checkpoint-status |  |  | checkpoint | Fit infill insulation tightly leaving no gaps.
checkpoint-status |  |  | checkpoint | Insulation to be secured using overlaid metal Top Hats.