## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | POST - S - Second Fix - Plumbing |  |  |  |  | Yes | POST - S - Second Fix - Plumbing | 1bcf26ac-8b76-4590-b198-72ce71e15e42
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Permission to begin work obtained
checkpoint-status |  |  | checkpoint | Drawings correct issue and construction set
checkpoint-status |  |  | checkpoint | Area is left clean and tidy and work can begin
checkpoint-status |  |  | checkpoint | Fit-off materials match schedule or drawings
checkpoint-status |  |  | checkpoint | Setouts/min clearances as per specification
checkpoint-status |  |  | checkpoint | Water pipework maintained test throughout
checkpoint-status |  |  | checkpoint | No debris in floor wastes or subs
checkpoint-group |  |  | section | Water Supplies
checkpoint-status |  |  | checkpoint | Toilet full flush and half flush working as required. Visual check for leaks on pan cone and close coupled connection
checkpoint-status |  |  | checkpoint | Vanity basin mixer working to required flow rate and overflow able to keep up with flow rate from mixer
checkpoint-status |  |  | checkpoint | Sink overflow able to keep up with flow rate from mixer
checkpoint-status |  |  | checkpoint | Dishwasher commissioned
checkpoint-status |  |  | checkpoint | Showers - Mixer working to required flow rate and shower hoses fitted with non-returns
checkpoint-group |  |  | section | Hot water cylinder
checkpoint-status |  |  | checkpoint | Trap installed on tray if required
checkpoint-status |  |  | checkpoint | HWC relief lines have 25mm clearance
checkpoint-status |  |  | checkpoint | Restraints installed
checkpoint-status |  |  | checkpoint | Hot water set to Min 60°
checkpoint-status |  |  | checkpoint | Tempering valve set to required temperature
checkpoint-status |  |  | checkpoint | Timber blocks installed
checkpoint-group |  |  | section | Finishing
checkpoint-status |  |  | checkpoint | Flanges installed on all pipework penetrations
checkpoint-status |  |  | checkpoint | All soil pipes are connected to sanitary sewer
checkpoint-status |  |  | checkpoint | No crossovers, hot on left and cold on right on all mixers
checkpoint-status |  |  | checkpoint | All fixtures are siliconed down and splash sealed
checkpoint-status |  |  | checkpoint | Hose taps are complete with Vacuum Breakers
checkpoint-status |  |  | checkpoint | Area is left clean and tidy
checkpoint-status |  |  | checkpoint | Work is 100% competed to required specifications
holdpoint |  |  | signoff | Raise remedial/Request signoff
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | FC - R - Down Pipes |  |  |  |  | Yes | FC - R - Down Pipes | 55c0e5cc-1386-4e97-b4ef-d4a001f1827d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Downpipe installation completed and acceptable
checklist-flat |  |  | checklist | F - S - Waterproofing |  |  |  |  | Yes | F - S - Waterproofing | 5950b72c-c78f-4c83-b2d6-1d9627064ce5
checkpoint-status |  |  | checkpoint | Lap distance for sheet membrane complies with manufacturers specification
checkpoint-status |  |  | checkpoint | Upstand/ perimeter detail installed as specified
checkpoint-status |  |  | checkpoint | Adhesives fully applied as specified and acceptable
checkpoint-status |  |  | checkpoint | Check for air pockets, wrinkles, holes, tears & note and remediated if required
checkpoint-status |  |  | checkpoint | Checked for penetrations/ pipework/ upstands sealed to specified detail
checkpoint-status |  |  | checkpoint | Checked membrane detail at expansion/ construction joints and acceptable
checkpoint-status |  |  | checkpoint | Flood test conducted and no leaks found
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed and correct and any remedial works completed
boolean | 0a9738f3-4aa4-528f-8bfa-ce064ca7fb34 |  | tickbox | Specified membrane protection is in place
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | PRE - S - First Fix - Plumbing |  |  |  |  | Yes | PRE - S - First Fix - Plumbing | 969fc9bb-c80e-4979-a1d0-dbfecc8d1292
checkpoint-status |  |  | checkpoint | Hot water supply lines run the shortest
checkpoint-status |  |  | checkpoint | Specified Waste pipework is Acoustic lagged and acceptable
checkpoint-status |  |  | checkpoint | Penetrations through fire cells are fire protected
checkpoint-status |  |  | checkpoint | All joist Brackets or Reinforcement installed, if required
checkpoint-status |  |  | checkpoint | Nog's and fixings are installed for water closet, shower, hot water cylinder and etc.
checkpoint-status |  |  | checkpoint | Penetrations through building paper are trade sealed
checkpoint-status |  |  | checkpoint | Hot Water Ring main is thermally lagged
checkpoint-status |  |  | checkpoint | All Pipework clipped neatly and tidy
checkpoint-status |  |  | checkpoint | All pipework secured/ siliconed
checkpoint-status |  |  | checkpoint | Floor Waste Gully Flange is recessed into flooring and installed
text | 3e110886-7cf2-5723-b1a1-e97c3135e419 |  | textbox | Enter water pressure value tested for. Confirm loop not effect lining
checkpoint-status |  |  | checkpoint | Checked for drips on water and waste piping
checkpoint-status |  |  | checkpoint | Soil and waste piping hydrostatic test ( Flood test )
checkpoint-status |  |  | checkpoint | Test plug & Gauge removed from pipe system
checkpoint-status |  |  | checkpoint | Fire penetration Schedule is completed
checkpoint-status |  |  | checkpoint | Flange and all through installed pipework flood tested
checkpoint-status |  |  | checkpoint | Plumbing First Fix complete and acceptable and area clean and tidy for next trade
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | F - S - Backfilling |  |  |  |  | Yes | F - S - Backfilling | cb2eddf9-048b-4fce-bda4-e1cdc24f5e84
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed
checkpoint-status |  |  | checkpoint | Area clean of debris
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | e3eec693-55fe-4c19-bd1a-4d2edbc47b8f
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | bdbb26b1-6669-5a80-adcb-8f21122aeef7 |  | tickbox | LBP Memorandum/ Record of works filled out, signed and attached
boolean | b8bdbdb1-ca62-57f7-8f02-1703fa941294 |  | tickbox | Any Additional Compliance Documentation - Completed and Attached
label | f1ab32ee-c5dc-5752-b322-adc0af7e8c5e |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | F - S - Underslab plumbing |  |  |  |  | Yes | F - S - Underslab plumbing | fcbc727f-7e0b-409b-bbd9-35abf94d4d93
checkpoint-status |  |  | checkpoint | Correct gradient of the pipework achieved
checkpoint-status |  |  | checkpoint | Pipe wrapped/protected and acceptable
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Pipe capped and acceptable
checkpoint-status |  |  | checkpoint | All underfloor plumbing works installed as per specifications
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS