## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Watermain | itp |  |  |  | Yes | ITP - Watermain | 0255ba0f-b61c-4e87-965e-b9c8d877c229
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 400.1 - Survey Set Out
label | 7892bc5f-37de-5136-a47b-7e7ca4279356 |  | note | Detail of Activity - GPS Setout of the watermain as per the construction drawings.
label | 9487458a-e401-5341-8977-e88aaa4d2d7e |  | note | Action - W
label | 3764699f-8ef4-5576-b31b-f018055d9e6f |  | note | Minimum Test Frequency - All lengths of watermain and connections
label | 30057d85-5fcf-5eb4-b706-b17944d24ec3 |  | note | Inspection / Test method - Visual Inspection
label | 089d64bb-0537-5346-b2e5-15f3646f4079 |  | note | Acceptance Criteria - N/A
label | bb22d449-235d-5e68-bd16-eae066d8ce44 |  | note | Record documents - Contractor's site diary and/or photos
label | 4f0b9d1c-7689-5e0e-bffd-90e22e901674 |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 400.2 - Materials Approvals
label | 419eeec1-375a-5530-99fd-b9df0244e6f7 |  | note | Detail of Activity - Line Materials/Fittings
label | 2211042e-6f00-5bc0-9924-d81076512817 |  | note | Action - M
label | 0d87a3cc-7cfa-5cec-b6ca-a2882e3f6687 |  | note | Minimum Test Frequency - All materials/fittings
label | c2a9eef7-e738-57dc-93a9-bc9c2c6cf4f1 |  | note | Inspection / Test method - Review
label | ed226c26-f42c-5f95-ab07-d41d25a61efb |  | note | Acceptance Criteria - All fittings and materials per RLC's Approved Fittings and Materials List. Any not listed are to be submitted and approved by RDC and the Engineer.
label | 6dcd6ea0-9b1e-5bfe-b733-5d949f1f301a |  | note | Record documents - Contractor's site diary/QC sheets
label | 845f1a64-71e7-5017-8a71-4745bc909d3d |  | note | In Eight record
checkpoint-status |  |  | checkpoint | 400.3 - Materials Approvals
label | 7987c5bc-be13-5e88-b243-ea83ed342a9a |  | note | Detail of Activity - Bedding/Backfill
label | 7326e914-b64d-5b6e-8414-754088976d36 |  | note | Action - H
label | 5884b5aa-bf92-5719-b157-95f46c04020e |  | note | Minimum Test Frequency - Once per imported backfill material type.
label | 99b40fd2-aeb5-5694-9f5c-82f6bf561b18 |  | note | Inspection / Test method - Material Testing Data
label | 2ee3b374-938c-59d0-bb26-6e06316c9a35 |  | note | Acceptance Criteria - Engineer's acceptance
label | bd00ed0c-df13-513b-953c-40fa0ab00a9e |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.4 - Asbestos Management Plan
label | 78078f45-2f62-55b5-b17e-83160e40831f |  | note | Detail of Activity - Submit Asbestos/Contaminated Material Management Plan
label | cc5f64c3-ee23-5776-8d83-13019746409b |  | note | Action - H
label | af8d2aa9-4aa8-56ce-a9ea-0042b56871e7 |  | note | Minimum Test Frequency - Once for Project
label | 1d59b071-9fd9-5a47-82c8-58b1e58cec62 |  | note | Inspection / Test method - Plan Submission
label | 88ef26d0-ebe6-5535-92c0-435d6aa3c20c |  | note | Acceptance Criteria - Engineer approval.
label | 487011c8-16a0-5df0-b26f-229bddd47904 |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.5 - Personnel - Registered Drain Layer Records
label | 7cec8ae9-2f97-5b86-ab1c-87e74817fa65 |  | note | Detail of Activity - All pipe layers to be registered drain layers
label | 037a5525-b5f7-574c-914e-c8d01ccfae79 |  | note | Action - H
label | 7bf3f428-b0e6-5921-8169-fbdb30c9c99d |  | note | Minimum Test Frequency - Once for all personnel on project
label | 9ccef0f5-fad9-5ca6-bf83-9cdf31079ac6 |  | note | Inspection / Test method - Training Record Verification
label | 0eec11e8-2fd2-51b8-a82a-699db3705fcd |  | note | Acceptance Criteria - Competencies forwarded to the Engineer.
label | d0ee8b72-7346-5a61-a412-c0a71872b2ae |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 400.6 - Open Cut/Trenched Excavation
label | 25bbc0c5-7bcc-5a72-bd00-d2f5bd07e1fe |  | note | Detail of Activity - Confirm trench excavation is to the correct dimensions
label | 5bb57ca9-b236-580e-be5e-8ff9b3ef0ea5 |  | note | Action - W
label | 7be8b99b-8a6e-58de-9207-74cac0b1a81d |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 996f0e01-d26e-5d8d-b785-fb1dd77c8531 |  | note | Inspection / Test method - Visual Inspection with tape measure.
label | 28271551-997d-58c4-9563-45871653c163 |  | note | Acceptance Criteria - Depths/widths in accordance with design.
label | 64002e5e-37c9-5a02-9f14-b94e215a33fa |  | note | Record documents - Contractor's site diary and/or photos
checkpoint-status |  |  | checkpoint | 400.7 - Open Cut/Trenched Excavation
label | cbe5b8e1-497d-51c7-9993-31c7e4c9213d |  | note | Detail of Activity - Check quality of trench subgrade/foundation
label | b82ee02d-688c-5e4d-81b5-8bd5234fa30a |  | note | Action - W
label | 6f9c10c0-5dc5-5d39-a14f-7566a1470d21 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 17e6ea87-d62b-59ca-9caf-5165690b7d49 |  | note | Inspection / Test method - Visual inspection / Scala Test
label | 784937d6-0fc7-5caf-b48b-d318e3e0054e |  | note | Acceptance Criteria - Firm and unyielding. Scala result of 2 blows per 100mm at 300mm depth.
label | 498fa7f9-93ae-530b-a9b9-061d834661b2 |  | note | If Scala doesn't pass undercut 200mm and replace with geotextile and GAP65.
label | 85d9b2dd-937c-5465-87cb-31759467dd42 |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.8 - Installation of Pipes
label | bf406b81-6a2e-552a-bc29-c605831aefab |  | note | Detail of Activity - Confirm minimum pipe cover - in carriageway
label | bcd13416-bb53-5b40-87b0-4134a1766888 |  | note | Action - W
label | 940d706b-8c93-58cf-83f5-ee7b001df257 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 7982d7fc-36ec-5d8b-8448-3de36fc41c2c |  | note | Inspection / Test method - Visual Inspection
label | 99d1b3ae-53b8-54b5-9bd0-7259525e97c2 |  | note | Acceptance Criteria - Min 1m cover to top of pipe in carriageways.
label | 22c60346-0597-5645-8e7d-ba8f46215283 |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.9 - Installation of Pipes
label | 2a9e5924-fa83-5b57-9e35-5ad19db3c6a6 |  | note | Detail of Activity - Confirm minimum pipe cover - in berm
label | 580c466d-ba48-5648-a32b-7804fefc547d |  | note | Action - W
label | a875c189-d170-58c6-af81-ec7a1faac36f |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 26a5590b-cd7a-5a96-b5a4-9d17183d9918 |  | note | Inspection / Test method - Visual Inspection
label | 7214bf9f-d287-5500-8713-b9a407db9ddf |  | note | Acceptance Criteria - Min 0.75m cover to top of pipe in nontrafficed areas.
label | 3c0e2fd9-6e5b-5e1d-9692-2ee2967ebddd |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.10 - Installation of Pipes
label | ccdc13ce-57b2-5332-a945-949d480c317a |  | note | Detail of Activity - Verify pipe levels are within tolerances
label | e4d8b3b2-f51d-58c2-9476-9da59d8dde35 |  | note | Action - M
label | 6c7e5cf5-e68f-5be7-a96c-777e51ad9975 |  | note | Minimum Test Frequency - Every 50 lineal meters.
label | 6f5d2726-3566-5f6f-ae2b-41f93468498d |  | note | Inspection / Test method - Visual Inspection
label | 5da775b4-65b3-58f8-9c95-0d8c48cec7e0 |  | note | Acceptance Criteria - + / - 100mm from DL
label | 50a1559d-4baf-5043-bddd-05c0b9a9815d |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.11 - Installation of Pipes
label | c5aee3da-9a9b-55df-aade-8d17504021b3 |  | note | Detail of Activity - Install warning tape
label | b910c4d4-06c7-5474-a4b6-aab0686851aa |  | note | Action - M
label | 2310a16e-9f99-5864-a400-90e256b1295c |  | note | Minimum Test Frequency - Continuous along pipe.
label | 78bb7dac-0d8c-5c48-87c8-74b749987e2b |  | note | Inspection / Test method - Visual Inspection
label | 4d32002d-4212-5ece-b704-57215470de6e |  | note | Acceptance Criteria - Warning tape at 300mm above pipe.
label | f4fea4e9-8a41-567a-bc66-94646c628996 |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.12 - Pipe Connections
label | 0830783e-eec8-56bf-a0cd-3244493f0797 |  | note | Detail of Activity - Record connection configurations
label | 511785e2-c307-52c4-a0ee-d6d5d8fd22f3 |  | note | Action - W
label | 742005b7-132b-53da-a730-4bc970aff8ce |  | note | Minimum Test Frequency - Every connection.
label | 85bf2629-f121-5408-abfd-0b59e9683441 |  | note | Inspection / Test method - Visual Inspection
label | ad911992-84e1-5b0a-8db2-03c5aca4670a |  | note | Acceptance Criteria - Photo and sketch of connection.
label | b112aa1d-a898-51dc-be86-66c12177468f |  | note | All buried bolted connections wrapped appropriately (i.e. denso)
label | 81549139-b183-55c0-9455-fa5032973448 |  | note | Record documents - Watermain Pipeline QC Sheet / Contractors Site Diary
checkpoint-status |  |  | checkpoint | 400.13 - Thrust / Anchor Blocks
label | 449bf1cb-7ccd-5e0e-893a-271d2246fff2 |  | note | Detail of Activity - Test thrust block subgrade
label | 363bf5e8-d2d2-56db-a2d1-e685f32a0fcf |  | note | Action - H
label | 53147438-62ba-50bc-8535-9aa2b4a74aa5 |  | note | Minimum Test Frequency - All thrust block locations.
label | f2c3a63b-a837-59f2-b8f7-f42cf6c46331 |  | note | Inspection / Test method - Scala Test
label | 8f41f832-d0cc-5ea3-9cd2-07582c14e8b4 |  | note | Acceptance Criteria - Scala result of 2 blows per 100mm at 300mm depth.
label | 47fa7d47-f785-5234-8a5d-f0cc998d19de |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.14 - Thrust / Anchor Blocks
label | c7a753cf-8bd9-5f63-ae62-f50fda3f948b |  | note | Detail of Activity - Confirm thrust block size
label | cd2d657b-5792-5705-a4f5-2ed559ae019f |  | note | Action - H
label | 4ecb3e43-e45b-56d7-a32c-39e98a484943 |  | note | Minimum Test Frequency - All thrust blocks
label | cef9cfbe-def2-5484-8f1f-cf9b2bb984c4 |  | note | Inspection / Test method - Engineer's Confirmation
label | 103f2dea-1ac4-504a-b100-38b81f155b54 |  | note | Acceptance Criteria - Engineer's confirmation of design size or advise otherwise.
label | 3968b90d-91d2-58dd-a4ad-e4cea9118629 |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.15 - Thrust / Anchor Blocks
label | ae561f57-9a8e-5dff-ab5a-3bbffbdb3859 |  | note | Detail of Activity - Wrap PE pipe/pipe fittings through anchor block
label | 13974826-b6b4-5224-b595-da3fe2d1d805 |  | note | Action - W
label | 96f12947-78ac-54f8-81a7-0ebd739f426c |  | note | Minimum Test Frequency - All pipes through thrust block concrete
label | 0f79aa3f-3b96-5e65-962d-205bcfbe7701 |  | note | Inspection / Test method - Visual Inspection
label | e85ada9e-380e-5182-9c8b-0a570e276091 |  | note | Acceptance Criteria - Wrapped in 2 layers, extending 50mm beyond edge.
label | 7d73b76c-dcb5-54e1-9c92-ee5f00af896b |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.16 - Thrust / Anchor Blocks
label | 8a799167-58b9-58df-b8f2-43474806a448 |  | note | Detail of Activity - Thrust block construction
label | c72d7bf7-99b7-5322-ad94-559ca018ff9d |  | note | Action - W
label | d3be45eb-3b60-5b90-9f5a-ff40d7dadf42 |  | note | Minimum Test Frequency - All thrust blocks
label | 23f65904-d71d-500e-9dc0-395f5e9de99f |  | note | Inspection / Test method - Visual Inspection
label | 9ec50ee0-b153-5ed8-9ce9-16d6fd6b502a |  | note | Acceptance Criteria - 17.5MPa concrete with 7 days cure time (no loading).
label | 4a55dc35-8370-54bd-be12-f84b650a3c5b |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.17 - Thrust / Anchor Blocks
label | eb941c75-05ba-5192-bd72-88321502873d |  | note | Detail of Activity - Engineer's Inspection
label | 90bb0e8e-6d49-5d3c-8290-2776aa79ef25 |  | note | Action - H
label | 31a2b343-2ecc-5859-8727-1c4c0b7b4a4d |  | note | Minimum Test Frequency - All thrust blocks
label | 722a0650-f643-5f5f-94fc-9e67e8ec7b8d |  | note | Inspection / Test method - Engineer's Confirmation
label | 88be94c2-cbea-506b-9495-9bbe38d567c1 |  | note | Acceptance Criteria - Engineer's acceptance
label | 90cdc951-18e1-51d0-bf37-cc44c7bbfefe |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.18 - Valves
label | 4dab3fa9-8841-57d0-9c49-6733369e8ea7 |  | note | Detail of Activity - Check valve levels are within tolerances
label | 1f1943b2-3fde-50c8-aef2-99a51b2ce025 |  | note | Action - H
label | 3e11ce63-bfd6-53a7-aae1-8732e21b700d |  | note | Minimum Test Frequency - All valves
label | 0adedd8d-56ff-5c33-8e09-a1ecfdaa5c82 |  | note | Inspection / Test method - Visual Inspection
label | 7f211685-f05f-5060-97a0-3d01122e9707 |  | note | Acceptance Criteria - Grass Berm: +5mm / -5mm
label | 7a10a653-2b60-54ea-8ce6-79010b982eab |  | note | Footpath or seal: +10mm / -0mm
label | 3ec8d63e-a398-5d51-ae71-747e90e4963b |  | note | Heavy Trafficked Areas: +10mm / -0mm
label | 0625174f-de2e-58cc-9da5-9e297d17c8b4 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.19 - Backfill in Berm
label | 2a0a8c44-0828-5b5c-b074-5e93f12111bb |  | note | Detail of Activity - Layer Thickness for compaction
label | d7acd4cc-624a-5785-9659-64bde2de6b0d |  | note | Action - M
label | cd37bbe9-dc88-5dfa-b70d-f3face9a6560 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 6b6debb6-12d6-5452-b33b-88b1bfad4e73 |  | note | Inspection / Test method - Visual Inspection with tape measure & photo.
label | 37819956-e373-5ac0-8482-c75c8c4f6905 |  | note | Acceptance Criteria - Layers ≤ 150mm thick
label | 6cd5c2b9-b1ec-537e-bbd3-b07bd495c6eb |  | note | Record documents - Contractor's site diary and/or photos
checkpoint-status |  |  | checkpoint | 400.20 - Backfill in Berm
label | 2d8a1612-6283-504c-a4a4-0c2b19862317 |  | note | Detail of Activity - Berm Compaction - as-dug material
label | 874b001f-4a86-5292-bdd1-c518b4943142 |  | note | Action - H
label | e4e82b46-35fa-56f3-b459-dcda992537cc |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 2dc3b0c2-9358-59e8-a17c-1087815d6bce |  | note | Inspection / Test method - Scala Test
label | 20583398-e1e8-5a51-94ce-42f51ce73637 |  | note | Acceptance Criteria - Scala result of 4 blows per 100mm at 300mm depth.
label | 520afbdc-0570-50af-81ef-222971a2e1e0 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.21 - Backfill in Berm
label | 2c8c7e82-0c25-5601-a142-1eaa58791f15 |  | note | Detail of Activity - Berm Compaction - imported GAP40 hardfill material (as-dug unsuitable)
label | a0acb571-d395-5068-860c-93c58d1314d0 |  | note | Action - H
label | 0b74c38c-dbb4-5773-9ddf-331ef5f3fb8f |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | e49213d8-2cb6-5aad-b3de-07214cd691f0 |  | note | Inspection / Test method - Clegg Test
label | ca733c9e-0e05-5fa9-8a11-0c1669546f67 |  | note | Acceptance Criteria - CIV ≥ 15 at top of trench
label | f1e8f37e-954a-5bf3-88a1-60a5c197a54e |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.22 - Backfill in Road
label | 13a45997-ce3d-57fe-8341-76d259bf1793 |  | note | Detail of Activity - Subgrade: Carriageway Compaction - as-dug if suitable or GAP40 hardfill to subbase level (500mm below FL)
label | 556eaa58-b357-59f9-8b2e-fda834b995d7 |  | note | Action - H
label | e3fb25cb-36f7-5013-8f72-f69dd2346fc7 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 55268838-2b2c-5afb-af8e-9676da0e27e9 |  | note | Inspection / Test method - Scala Test/Clegg test
label | 869974b4-15ce-56d9-ac68-47e21158be26 |  | note | Acceptance Criteria - Scala to 500mm. Target = 3 blows per 100mm.
label | f79fc93d-b103-5511-952b-45cd7de3d4c8 |  | note | CIV ≥ 12
label | d6fcdddc-a2f0-56d2-8621-5ce242c47f16 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.23 - Backfill in Road
label | dd49a5d5-e029-569b-a175-e1f2c604c2ac |  | note | Detail of Activity - Subbase: Carriageway Compaction - GAP 65 subbase (to 80mm below FL)
label | edd28012-3606-5ab5-b470-74c766f1e45e |  | note | Action - H
label | 5133031e-bbf9-543d-8033-2590c01d7d02 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 40ba3886-51fe-567b-933d-2ae7e1acc79c |  | note | Inspection / Test method - Clegg Test
label | b6522157-2d52-58a1-a21a-9b6e439689c0 |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift (i.e. 2 lifts). CIV ≥ 20.
label | d184d4ee-4b25-5de9-8c9b-afd30e007fc6 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.24 - Trench Surface
label | 6d0fcab5-0b5b-5764-bcb2-5373817f8345 |  | note | Detail of Activity - Visual Inspection
label | bfb1be8a-3894-5af0-9f41-e88797d51c3f |  | note | Action - M
label | bf357ce6-8310-59e9-a8e3-ec6e502352c8 |  | note | Minimum Test Frequency - All filled trench surfaces
label | 97400de8-7b89-5ed1-9643-19c4b361e3cf |  | note | Inspection / Test method - Visual Inspection
label | f1453ac6-8d0a-5500-a60d-ab4420d67587 |  | note | Acceptance Criteria - Left appropriate for temporary or permanent use (as applicable). I.E. temporary sealed, left flush or ramped with surrounding area and maintained.
label | b9fd1536-06ac-58fa-a27f-12188da1725a |  | note | Record documents - Contractor's site diary and/or photos
checkpoint-status |  |  | checkpoint | 400.25 - Pipe Testing
label | f8293820-713e-52ea-8ae6-a9495992ad91 |  | note | Detail of Activity - Sterilization
label | e5e2cdb0-0739-5edf-a298-c23cd2038e7a |  | note | Action - H
label | 4ed5030f-ce61-5317-81f2-751000eb33bc |  | note | Minimum Test Frequency - All pipelines
label | 8a76a347-845c-5faf-a4ea-8c0fce2bbc85 |  | note | Inspection / Test method - Residual Chlorine Test
label | b1632b95-1f20-5a80-9630-303def8eed55 |  | note | Acceptance Criteria - Test passed
label | 813b729c-9943-5bb7-9c12-b2fac3d88a97 |  | note | Record documents - Watermain Pipeline QC Sheet / Results Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.26 - Pipe Testing
label | 259f33d7-ad13-5b53-acf1-3997f0ed6401 |  | note | Detail of Activity - Pressure Testing
label | 9e3d7c10-a012-55fb-93d7-9dbd37ac10cb |  | note | Action - H
label | 13ed5302-2e07-50ec-aed4-bde29129ff23 |  | note | Minimum Test Frequency - All pipelines
label | 874ac193-7223-5ac4-ab30-c3214f47d3ea |  | note | Inspection / Test method - Pressure Testing
label | 396bb61e-6bdd-55e1-961f-aa44314241b5 |  | note | Acceptance Criteria - Test passed
label | 28a93ef4-aaa1-5bea-b845-fa660c6a2c3c |  | note | Record documents - Watermain Pipeline QC Sheet / Results Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 400.27 - Collate above documentation
label | 000f670a-1d3e-56db-9d26-5c1c1d8eb229 |  | note | Detail of Activity - Document review
label | 2f9065b2-b701-5cc7-88bb-fd6184388200 |  | note | Action - H
label | 591faf52-94ba-5e15-828b-c055335a7880 |  | note | Minimum Test Frequency - Each ITP
label | d16e5c0d-f595-5f1f-9e9d-37a8df2fddc3 |  | note | Inspection / Test method - Review
label | 43774ac7-117e-5345-8dd7-791beb510b91 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | e2c1f006-c956-5786-bf39-a192614bb855 |  | note | Record documents - Review
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.28 - As-built drawings
label | 8bc22391-8cb1-5041-8b22-89775ae9d8df |  | note | Detail of Activity - Survey
label | 1f50cfdb-d833-5136-b4c0-c3f2cd0230e7 |  | note | Action - H
label | c7fb2d5a-3559-5e8b-aaf1-b19622370587 |  | note | Minimum Test Frequency - At completion of construction
label | 3fa54fac-a344-5ce7-8fff-abfeadb6afb5 |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | fcd54269-9a5c-5b8c-91d2-915145a6c25c |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 804e6aa0-5997-575e-b996-dc8a82fdeaec |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.29 - Acceptance Certificate
label | 6cb172ed-9e5b-5666-971a-d71cda24d897 |  | note | Detail of Activity - Acceptance certificate jointly signed by contractor and respective service owners.
label | a62ed8c2-26e3-512b-a7f1-42c96a3c7ddc |  | note | Action - H
label | 7cd9211a-3c18-5217-9531-c0908385b1b7 |  | note | Minimum Test Frequency - At completion of work or stage
label | 0f0bd67c-bd6c-5301-bf32-8a8d1c294866 |  | note | Inspection / Test method - Certificate
label | 01326cc1-6b0f-5c6a-9cbd-c4c430ca9e1b |  | note | Acceptance Criteria - Submission of jointly signed certificate.
label | 02b8ce7b-da7a-5a1d-8b2e-e1d140ceb8ce |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | bcf6969b-6e25-5928-be8e-fbf11e3ecdae |  | textbox | Contractor's Rep Name:
text | 0038f27a-c77d-57c0-8485-edbf5a1bb226 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Traffic Signals |  |  |  |  | Yes | ITP - Traffic Signals | 07795f08-0b93-4954-81f0-16c8e0a0e5c8
checkpoint-group |  |  | section | 900 Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 900.1 - Method Statement Development / Job Safety & Environmental Analysis
label | 105adb0f-1c29-5920-b613-a31caeff3580 |  | note | Detail of Activity - Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | 94715ac7-45c8-58da-94d4-e79b547a47db |  | note | H
label | 314d319c-a92a-5bf8-aa93-eb091d88943a |  | note | Minimum Test Frequency - NA
label | ed97f43b-1ab7-508f-93f5-996b43c26780 |  | note | Inspection / Test method - NA
label | 48e2266e-4018-50db-bd00-ef259ddb72ee |  | note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority.
label | 2e554bf3-e29d-5af2-9861-cb3f958e8ddf |  | note | Record documents - MS & JSEA
label | 65469b65-1585-5d90-9240-84113515cdd1 |  | note | Responsibility - Contractor
label | d053055b-723e-5625-849e-077515eaf40c |  | note | Comments - Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.2 - Drawings and Specifications
label | 2f1c2202-c737-58d0-b2aa-f34c2938afd7 |  | note | Detail of Activity - Check drawings are for construction and latest revision. Check Specification is for construction and latest revision
label | 16994a3f-9dcb-5eca-8e30-5209cacf75e0 |  | note | H
label | fce5f9ae-2183-5bed-ba2e-cdf6e9edbac6 |  | note | Minimum Test Frequency - NA
label | ab31859d-f495-5e45-9cb6-01eb64116137 |  | note | Inspection / Test method - NA
label | 9485376b-7cab-5610-a568-8d4900dd8ace |  | note | Acceptance Criteria - Drawings and Specification are the latest revision.
label | 9f75aa88-4a51-51c7-b27f-859c1e8278d0 |  | note | Record documents - IFC Drawings and Specification
label | 77cfac0f-b320-514f-ae86-e517bce1f9b3 |  | note | Responsibility - Contractor
label | 9e0850a6-e05d-5ee5-b046-f5d73d2574cc |  | note | Comments - Up to date drawings and specification to be reviewed before construction.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.3 - Power Connection
label | bb10f087-ea4e-5552-aa38-0344e97bcd8e |  | note | Detail of Activity - Ensure power supply is organised and connection is in place
label | a78e39ad-c499-56fb-b9cd-6e5214d429bb |  | note | H
label | a79c8267-ad2a-5511-b78b-08d8efb6dc4f |  | note | Minimum Test Frequency - once per set of traffic lights
label | a01e4d9a-b6b6-5e1d-975d-76d1941f9e03 |  | note | Inspection / Test method - NA
label | 81b9064a-2160-51e8-b96a-7955bcd1ff8b |  | note | Acceptance Criteria - Complete NC1 form and ensure ducting for power is in place.
label | b8a7b4aa-4c56-5c7b-8017-93c233e46d84 |  | note | Record documents - NC1 Form
label | 9fe26c6d-a28d-5dc6-8632-ae7d61e00f48 |  | note | Responsibility - WSP / Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.4 - Comms Connection
label | f585f3d7-33d4-5dfe-99d3-0439d902db8e |  | note | Detail of Activity - Ensure comms connection is organised and ducting is in place
label | 123cb97a-689b-5800-955a-364c48ead526 |  | note | H
label | 9b529345-6fd2-5066-848f-3a05c7572f9f |  | note | Minimum Test Frequency - once per set of traffic lights
label | d780acfc-2252-5a9a-9085-0acea37435cb |  | note | Inspection / Test method - NA
label | a2cbfb9f-c6d1-5a95-a5e8-00034f9c96b5 |  | note | Acceptance Criteria - Liase with service provider and organise connection (UCG) Universal communications group.
label | d0803876-fbcf-555c-8390-c5c12a6cb943 |  | note | Responsibility - Contractor
label | 23bc0734-26e1-501a-b5ff-5ef856e0f21a |  | note | Comments - Order connection from Chorus
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.5 - Survey Set Out
label | faf840a2-7db5-5ac5-aa99-e17c6dd3e67a |  | note | Detail of Activity - GPS Setout of the shared services trench location as per the construction drawings.
label | a54ae7c7-c4a8-52f8-b2a8-9b99b50defb2 |  | note | W
label | bb806397-6bce-511b-ab71-dae3760ddb40 |  | note | Minimum Test Frequency - All shared trenches.
label | cf26677e-c881-5960-9f64-0262d1b60253 |  | note | Inspection / Test method - Visual Inspection
label | 00597f42-48cc-5b01-8884-2621a0fe57a0 |  | note | Acceptance Criteria - N/A
label | 60b00f0a-9d8b-533f-a0fc-908fd9edb244 |  | note | Record documents - Contractor's site diary and/or photos
label | ffc7b735-7454-5185-9edb-be4cb486b79a |  | note | Responsibility - Contractor
label | 9747205a-ef17-5c95-8b4f-6245c7e5a853 |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 900.6 - Sediment Controls are in place for the particular section
label | ddd96093-ee36-5bbf-9f8f-cca049ba12af |  | note | Detail of Activity - Check ESCP and ensure any controls needed are in place before excavation.
label | 901db767-ddd8-5be0-9c61-4168c27adc57 |  | note | M
label | 46ded844-74aa-5df7-a5d2-e96c1a3458f2 |  | note | Minimum Test Frequency - once per section
label | da8f3b3e-b04e-5115-843c-3939e12917b4 |  | note | Inspection / Test method - Visual Inspection
label | cb663310-36fd-597c-a07c-35e6609aa885 |  | note | Acceptance Criteria - Erosion and Sediment controls are in place prior to starting works.
label | 8ecfd64d-216f-5e60-b9a4-77bb7f9470e0 |  | note | Record documents - Contractor's site diary and/or photos
label | 33c08e3a-ac3d-5239-91b2-f2ee09ce13d8 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Construction and Finshing
checkpoint-status |  |  | checkpoint | 900.7 - Element Locations / Positioning / Types
label | 5d301014-9e15-5529-bdb4-ee665ccce6e4 |  | note | Detail of Activity - Walk over with TTOC, WSP, TSL & Downer representatives to agree positions of intersection elements
label | 6660a64a-483e-56df-9f7e-5ff006b86999 |  | note | H
label | 56d226c3-fc73-5b4b-8b38-94f62d7b0edc |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 0cb067a3-5f17-5354-89b6-9d0c09c850f5 |  | note | Inspection / Test method - Visual Inspection
label | 46264ac8-ad19-5937-9302-567021b8fa94 |  | note | Acceptance Criteria - TTOC, WSP, TSL acceptance.
label | 830d852d-b4c2-5d15-b2c7-fe5accdca13d |  | note | Record documents - Written confirmation
label | 4400c05c-90fd-50c7-8f6b-0b690d9addd4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.8 - CIS Production
label | 572712d7-783e-55a4-a644-d16a8f4f2b6f |  | note | Detail of Activity - Draft CIS to be produced, independently reviewed and approved.
label | 3b27ce38-8e52-5e16-b530-1e881e9cf4eb |  | note | H
label | bc4aca45-9c22-59a4-bfca-3148a61db2ff |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | d7407b3c-12d3-50b6-b4f0-99963f765542 |  | note | Inspection / Test method - Document Review
label | 92fe801b-de2f-5807-895e-604cca4e0b76 |  | note | Acceptance Criteria - Review completed and development approved.
label | c671aea4-4709-5a73-8110-bfbc4d24dc63 |  | note | Record documents - InEight Documents
label | c8756b0e-1821-5271-ba48-2860d8ea4f7a |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.9 - Software Testing
label | bf0f66aa-b468-578a-897e-579b7b0cd719 |  | note | Detail of Activity - Software to be independently tested using traffic signal emulator software (SFT Testing)
label | 4d0c2719-ee84-56f2-9731-172c1efb8a4a |  | note | H
label | f62137d2-3116-5068-8b9d-797eeef592c0 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | ad270cd4-67b4-585c-b696-602d3d8f2d27 |  | note | Inspection / Test method - Document Review
label | 7a2883d1-c14e-5f0d-be3c-26afb66cabcc |  | note | Acceptance Criteria - Approval for release received.
label | 4ec71430-4c11-5f98-9755-01745fa16a39 |  | note | Record documents - SFT Test Result Summary Sheet
label | e60fba1c-b905-5b04-b1c1-608889513b08 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.1 -
label | 0ef7b159-66d7-588d-80c8-eebcd661a4ea |  | note | Detail of Activity - SFT files provided to create PROM, bench testing to be completed by TSL
label | 06859e5f-e5d9-5ce6-b540-956e378d3273 |  | note | H
label | ba5cdfb1-e1a7-504b-8f2e-2b96bd7ebf2a |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | db4455da-756f-5681-9dab-2455063af60e |  | note | Inspection / Test method - Document Review
label | c13f3485-c56e-5da2-b292-03d9e8c97211 |  | note | Acceptance Criteria - Pass result for bench test on "Appendix H - Controller Bench Testing Form".
label | 80eb7553-3c44-561d-b8df-a5226b7488b3 |  | note | Record documents - Appendix H NZTA P43
label | 1327b2f4-0615-5265-b64a-fc8a630f04d3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.11 - Pole - Installation
label | 57cfac5e-44c4-5818-8b8c-6d58a6263457 |  | note | Detail of Activity - Ensure poles are plumbed vertical
label | e6850dc1-fe67-558f-84d3-097503e03ca0 |  | note | W
label | 4c18a130-6a24-50be-b930-f2c8383244cd |  | note | Minimum Test Frequency - Each pole
label | c37b833a-42c2-50e9-bdaa-409857d95d73 |  | note | Inspection / Test method - Location/Position Acceptance
label | 0c885a7b-8a93-50b3-97bf-6b7441aa0905 |  | note | Acceptance Criteria - Plumbed vertical Tolerance: +/- 10mm per 5.0m length
label | a56bbe7c-eb24-5100-9e0e-af21f49ef7e2 |  | note | Record documents - QC Sheets
label | 607a6578-b696-5cbc-a502-14d6ea350c59 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.12 - Pole - Identification / Finishing
label | fb9020ef-f800-5293-8d5c-fecb6d4e5cbd |  | note | Detail of Activity - Pole Number Verification
label | 80f3a163-8c39-5764-b86b-a0d734ae6336 |  | note | W
label | 429f24ca-a303-523d-8faf-fb6f71d5866a |  | note | Minimum Test Frequency - Each pole
label | b55e9df7-c0d1-52db-862e-17e28e6a38d1 |  | note | Inspection / Test method - Visual Inspection
label | 61d03303-db1a-5941-ac6a-8166993fc89b |  | note | Acceptance Criteria - Ensure poles are numbered correctly and match the CIS sheets (pole numbers match program and diagram numbers).
label | e4512c65-a2e6-56b3-b5d8-b371a2c683f6 |  | note | Record documents - QC Sheets
label | ba410db0-1771-52a6-a13c-4178d5887fc5 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.13 - Pole - Footings
label | 813f8acd-081b-5756-b875-8db363ace475 |  | note | Detail of Activity - Footing Type
label | 73b63e40-d802-55f7-9ab1-1677e9c664f3 |  | note | W
label | f1a0af8d-da24-51b3-9998-2ac54f51327f |  | note | Minimum Test Frequency - Each pole
label | 1b1f90d1-a246-5c41-b0d3-a8cac14e9b0a |  | note | Inspection / Test method - Visual Inspection
label | ab340585-deac-532e-acd2-30351eb51325 |  | note | Acceptance Criteria - TSL engineer confirmation that poles are founded securely and have adequatley sized footings for the site conditions.
label | 28356d70-135a-522d-925a-a23834c0dc3e |  | note | Record documents - QC Sheets
label | 46416c62-9a39-5be4-8f0b-51fe12ed7651 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.14 -
label | 442d06f3-dd69-52ab-9a19-5ca878cefe59 |  | note | Detail of Activity - Footing Concrete Strength
label | 6ac36f0c-4cf0-5afc-8060-2d3bc87f0443 |  | note | M
label | b3d2f349-4b9d-5dcc-b077-42e66f70c130 |  | note | Minimum Test Frequency - Each footing requiring concrete
label | 24fd07c3-bd16-5226-bf71-2abaf8a23295 |  | note | Inspection / Test method - Visual Inspection/Concrete Dockets
label | e00ef5a6-4b21-50e4-a00d-3f06eaebff36 |  | note | Acceptance Criteria - Confirmation footing concrete strength (where required - i.e. delivery dockets) is min 20MPa at 28days, or as specified in foudation design.
label | 0ef31632-696e-539b-a74b-52e9588feb03 |  | note | Record documents - QC Sheets/concrete dockets
label | 508b5a4d-53a4-5bf8-9832-1948b923bc4d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.15 - Cabling
label | d7725886-a521-56ad-931b-95d2f3373b08 |  | note | Detail of Activity - Continuous Lengths
label | 35b377e1-c9ec-583f-bd2e-a1c2eb797d60 |  | note | M
label | 3cef9e6a-4d7d-5f6b-b56e-62dfd9140844 |  | note | Minimum Test Frequency - All lengths
label | 1d59b4e7-2431-5e5f-9888-f54a75ca040d |  | note | Inspection / Test method - Visual Inspection
label | 1ef3fb62-5e4c-5f66-93de-a62adcc3b1f8 |  | note | Acceptance Criteria - Cabling to be continuous lengths from controller to the pole, and from pole to pole (i.e. no joints between poles).
label | ed067392-815e-5896-88e4-b266fa993a62 |  | note | Record documents - QC Sheets
label | 7e697dac-05f0-5816-8a59-29551d1b57d9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.16 -
label | 91aed092-7863-5f30-bcba-ca84856041d0 |  | note | Detail of Activity - Looper Feeder Cable Slack
label | 87940460-5553-5346-9a8c-755f45500a09 |  | note | M
label | 6a6042c4-ac78-5b60-ac96-2063955d6d2d |  | note | Minimum Test Frequency - All lengths
label | aa61b13b-50f4-55ab-8b7c-d3ada3579bfa |  | note | Inspection / Test method - Visual Inspection
label | 8db32eb1-e667-53a7-b3a0-f8e11ee780b3 |  | note | Acceptance Criteria - Following cable slacks to be provided: - 1.8m (minimum) at controller base - 0.5m (minimum) inside KSJB
label | ed9e3013-58ca-5943-8345-fb302b5158d3 |  | note | Record documents - QC Sheets
label | a6d94807-7a6b-5ecd-9cc5-fd8beed7ed41 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.17 - Cable Termination Chart
label | f7a81a81-0677-5807-976f-08f469376b0f |  | note | Detail of Activity - Provide cable termination chart in controller cabinet.
label | ef06cfc8-9f27-54cc-947f-e295f89d120e |  | note | H
label | 42a20b9e-6931-50db-93bf-1f1f0ab9a6e4 |  | note | Minimum Test Frequency - Each controller cabinet
label | e63f1e75-f4ce-5f6f-b278-cbae0e455a78 |  | note | Inspection / Test method - Inspection
label | 1e6c5e9d-0878-5ac9-8e1d-ed59018ed5be |  | note | Acceptance Criteria - Cable termination chart provided.
label | 55bb2de9-7b92-56be-a881-dc05a1e016eb |  | note | Record documents - QC Sheets
label | bd64db07-d2a8-52cd-857e-2bc95291851a |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.18 - Earth / Earth Loop Impedance Testing
label | f7ec46c8-b503-579d-b5de-05caab527290 |  | note | Detail of Activity - Complete earth loop impedance testing per 3.15.2 of NZTA P43.
label | c6514376-488a-5aec-bb0a-0c4478556edc |  | note | H
label | e4cb704e-cd19-572d-969c-e89f9f724ae5 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection as specified in 3.15.2 of NZTA P43
label | 817e8e6d-73c4-5c06-8613-12d56e57b98c |  | note | Inspection / Test method - Inspection
label | 786fa568-2782-5cf9-ac51-e8160ae71de6 |  | note | Acceptance Criteria - Submit results in a report.
label | b24d7035-c982-5bbd-afd5-f6b7d6b5de3f |  | note | Record documents - QC Sheets
label | 4ab2c433-eee1-5940-8e72-794a85fe368c |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.19 - Loop Testing
label | d6ce7219-dd81-5d87-8eed-dd51a5cf3ea4 |  | note | Detail of Activity - 500V test from the isolated conductors down to earth.
label | 4914d6bb-9819-5ba5-a7db-543be1112230 |  | note | H
label | bdd11eb1-39b1-5f3e-8854-1cf9eb6b5655 |  | note | Minimum Test Frequency - All loops
label | cea169db-3d5a-5a5f-8ef5-beeb0659cddb |  | note | Inspection / Test method - Electrical Testing
label | ee72b100-2202-5f99-9427-a1e7684d1c37 |  | note | Acceptance Criteria - Result ≥ 10 megaohms. Q ≥ 15 when measured in the kerbside junction box (KJB). Submit results signed by technician who conducted the testing and in a report.
label | 10ccc2dd-31dc-5fcb-9810-c086745289ac |  | note | Record documents - QC Sheets
label | 0adde78e-dda2-5006-9ed2-3d89444994fd |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.2 - Loop Feeder Cable Testing
label | 86e6c8bc-bf8f-5e96-96ee-74cfdc05a0ef |  | note | Detail of Activity - 500V test from isolated conductors down to earth.
label | 2912ebed-ec65-57ee-8c34-7acd7efb5d28 |  | note | H
label | 11195267-e82f-5d38-99a3-855f3ece3d49 |  | note | Minimum Test Frequency - All feeder cables
label | 15ea2858-d5f1-5c2b-9065-fbafa988d2fe |  | note | Inspection / Test method - Electrical Testing
label | 270f5d2f-7f32-55a1-8be8-eeae8b05202b |  | note | Acceptance Criteria - Result ≥ 10 megaohms. Resistance of feeder cable ≤ 10 megaohms when measured at the controller. Submit results signed by technician who conducted the testing and in a report.
label | fb4d9d11-80a7-58d9-9ada-2cee2015b2f4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.21 - Log Book
label | 788fb157-b8fb-53c7-8a47-dd2a763ee4f5 |  | note | Detail of Activity - Log book detailing any attendance at site, reason for attending and brief description of work carried out.
label | cebd87a3-04b2-5e73-b7f6-7f286a290aeb |  | note | H
label | f36760fd-4604-57ed-a073-12975de3bfcb |  | note | Minimum Test Frequency - Once per controller box
label | e93a179a-79f6-5465-a576-e3bb28295a36 |  | note | Inspection / Test method - Visual Inspection
label | e81534aa-210e-5e05-9fb7-515fcbf7a88d |  | note | Acceptance Criteria - Log book provided/completed as required.
label | 90b90f46-4549-5ff0-b9c0-706183479633 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.22 - Site Acceptance Testing
label | 828f6b66-409e-51cc-97f0-8f60c77de52a |  | note | Detail of Activity - Completion and sign off of TTOC-07 Site Acceptance Test (SAT) documentation.
label | abcc2cb5-298a-5de0-8c78-f7d139e140b8 |  | note | H
label | f668757c-1a5d-57f2-9820-93011dc2dfe8 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | f703d431-a83c-58bd-a849-bf28040b2450 |  | note | Inspection / Test method - Inspection / Audit
label | b7419fa8-4fb7-5079-8f87-4ba3c16b0b4f |  | note | Acceptance Criteria - All requirements satisfied and TTOC Traffic Signals Engineer signed acceptance of SAT document.
label | c5acf66d-550b-5881-b886-ad15523900af |  | note | Record documents - TTOC-07 SAT
label | 8cdb0b3c-81ac-5383-86f3-f96300b173c3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.23 - Electrical certificate of compliance and record of inspection
label | 521d941c-9da2-5dec-8bac-fc8a2f6145b7 |  | note | Detail of Activity - Complete COC and ROI.
label | 8aa9ba60-931a-5ef5-aac6-cf5e3b642a42 |  | note | H
label | f028a4ad-46d0-5553-b667-cedfd65b9d81 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 9fa7a20b-cfce-57d2-a37a-0debf80a9bb3 |  | note | Inspection / Test method - Inspection / Audit
label | 93762220-ea42-59ed-b367-0cd69f23b9a2 |  | note | Acceptance Criteria - Submit COC and ROI.
label | b28c7222-1904-5ec3-ac27-ed39d3b26456 |  | note | Record documents - COC & ROI
label | c3bff617-76f6-553f-800f-709e49a5e053 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.24 - Commissioning
label | 04f189fe-a43e-5a02-bdb9-a80de142eefa |  | note | Detail of Activity - Submit completed and signed Appendix H forms 5 working days prior to commissioning.
label | f4f616d9-4a0c-5c41-aab6-129193cc65f3 |  | note | H
label | 5c9b57e5-c7c3-5bb3-8008-eeedaac2825a |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 41d2af85-927a-542d-84b9-2debdf531f91 |  | note | Inspection / Test method - Document Submission
label | 75f2479d-feba-5071-98cf-b31f150ee7aa |  | note | Acceptance Criteria - Submit Appendix H forms to TTOC.
label | d8e0b99f-3335-50a2-a757-363ce1272608 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.25 -
label | bb1f7fd5-b833-5791-ae9f-2951cf7cbfa9 |  | note | Detail of Activity - Notify TTOC with 48hrs notice before commissioning lights.
label | a7815f59-b632-592c-b73b-57819934d99c |  | note | H
label | 74f20b7d-e97f-5885-83d3-ed30909823e0 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 161d0154-5e59-50c5-b327-b888fe2c5a91 |  | note | Inspection / Test method - Inspection
label | c14fc511-6ba1-58b0-a591-c4d0ba227fcf |  | note | Acceptance Criteria - TTOC Acceptance.
label | 40bd3889-f314-53a7-8788-a08ef5fe9476 |  | note | Record documents - Written confirmation
label | 33cf7acd-2674-58ed-b3aa-cdd6000249c3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 900.26 - Collate above documentation
label | 55f20c0e-9684-56cd-abc4-c0d161c4671b |  | note | Detail of Activity - Document review
label | 1be4b1e3-1748-59a9-a0e1-703228ffe97f |  | note | H
label | 3d58b9db-9595-517e-a77e-7507e33870f4 |  | note | Minimum Test Frequency - Each ITP
label | 81c4fe26-c11d-5a5a-b833-e7a8151a92e7 |  | note | Inspection / Test method - Review
label | 88d97789-4bf0-5286-b7f9-17f50c82b856 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 7165cd74-84f4-5c52-b359-01a431888527 |  | note | Record documents - Review
label | f0b8ebc3-b281-527a-9433-7eabe1db03f5 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.27 - Controller cabinet documents
label | 2cb622fd-460f-53dd-a608-49a6a3cc4071 |  | note | Detail of Activity - Controller Cabinet Information
label | ab25afb2-bf7c-5642-a4f8-aef4ad95fcf4 |  | note | H
label | 1eda2f01-3a97-5bfa-bd26-3a48196c67cc |  | note | Minimum Test Frequency - At time of commissioning
label | 5524a14e-cc72-553d-92f5-1d02821b6791 |  | note | Inspection / Test method - Review
label | cca5fb79-ad74-531f-b63e-c3d4e177ec78 |  | note | Acceptance Criteria - Laminated copies of below placed in document pocket inside controller cabinet, within two weeks of commissioning: - As-built plans, - Completed cable termination chart - Controller Information Sheet (CIS) - Log-book
label | c5ed4026-faaa-5031-ba94-3f42ffa7cf6e |  | note | Record documents - Review
label | 14287aa3-de21-57f5-88f6-28995ff3d8b8 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.28 - As-built drawings
label | c83c3901-e447-563c-9303-ae9c10221895 |  | note | Detail of Activity - Survey
label | ba72b262-629a-5ea9-b4b6-01243d4b39b5 |  | note | H
label | 76fb8e38-3dc4-576f-b64f-e120560f2fa0 |  | note | Minimum Test Frequency - At completion of construction
label | d767eca4-be94-5f0b-b6a9-ae2be1e1bbf7 |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured regularly.
label | f24dfecf-e558-521f-9276-39e64476e4fd |  | note | Acceptance Criteria - Asbuilts reviewed and submitted showing final location of all poles, access chambers, KJB, loops, lantern displays and cabinets. Completion and sign off of TTOC-08 Site Asset Collection Sheet/Appendix K of NZTA P43 documentation.
label | 2c3d0851-c501-5d2b-9fbc-213f7e07c266 |  | note | Record documents - In Eight record
label | 966e497e-5536-5f43-be05-b1099f7db27a |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4c1a6dc2-03c1-5613-bbf0-16ec52cf1d8d |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 6c8379b2-46c7-5162-8c3b-44e00c71fcc9 |  | textbox | Contractor's Rep Name
text | d9612ee5-07d6-598c-9016-f732a3c999f4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 8e034b10-848c-5ded-bedc-3745e81e4425 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 28d9cac6-c115-569e-8057-4acda09e0c02 |  | textbox | Contractor's Rep Name
text | 1aa2b2c7-4306-5ab1-b6d5-61d9ace15d18 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP - Retaining Wall |  |  |  |  | Yes | ITP - Retaining Wall | b674d29f-959a-4c84-be0e-c444ce5ffcc0
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | .1 - Survey Set Out
label | ad732764-75c8-59c9-ba18-2d799d6c7a1a |  | note | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings.
label | 967aa605-8a80-5c6c-8c87-765caa5505b1 |  | note | W
label | 1e0de175-7e83-5058-b91e-5061f3cf6044 |  | note | Minimum Test Frequency - Length of the retaining wall
label | 5036012b-51e4-5029-9997-3cd6321499cf |  | note | Inspection / Test method - Visual Inspection
label | 063d6288-d86e-58f8-a6b0-0475b0712ff1 |  | note | Acceptance Criteria - N/A
label | 10aef099-004e-5225-b812-a588aef47949 |  | note | Record documents - Contractor's site diary and/or photos
label | a23aafc0-9e64-5aff-a318-91f44017b6e0 |  | note | Responsibility - Contractor
label | 3133468e-b62e-56d2-a3d5-fa0b8c30a203 |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | .2 - Materials Approvals
label | acab6a58-62ef-54a3-9591-d584427ad2bc |  | note | Detail of Activity - Submit testing data fir the following materials:
label | d944ef5e-461a-5d30-bd96-017df0410c9a |  | note | – AP65
label | dccd6762-9278-5d37-afbc-35aa0f2cfe83 |  | note | – GAP 40
label | 3e72681f-f08d-5140-9590-e229c15d1bb1 |  | note | – GAP 20
label | e25349a8-6e2e-5fd8-9a81-5e7119eda07e |  | note | – Hardfill
label | 4bd761d4-8299-5ad1-9243-9c2eeb5b309d |  | note | H
label | af7412c9-9335-5b36-8f88-039c4ee72be2 |  | note | Minimum Test Frequency - Once for each material
label | 3b7b4ded-0891-554c-8964-118625a64220 |  | note | Inspection / Test method - Quarry Testing Data
label | c320fdee-c351-5ade-ac3d-29b44ebf6b95 |  | note | Acceptance Criteria - Engineer's Acceptance
label | 50959863-9ec5-5efd-a820-e810b2ef1c93 |  | note | Record documents - InEight Records
label | 2d8a6e5e-c531-5ca3-bbd7-0ad5d0054941 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction and Finshing
checkpoint-status |  |  | checkpoint | .3 - Bases, Footings and/or Toes
label | 0d92c3e7-0259-550e-a063-87a4b0d58fc1 |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | ed60c655-e00a-5f70-8002-00ee01ebfdd3 |  | note | M
label | 73e6711b-d942-5644-b6c1-3852e6eccb94 |  | note | Minimum Test Frequency - Every 5m section
label | 5e9a1902-ad84-5f76-be66-7dd49ad55abb |  | note | Inspection / Test method - Visual Inspection
label | 599bc99d-decc-5cb8-903a-4c980ddab854 |  | note | Acceptance Criteria - As per drawing
label | 393b0c33-301f-5a4a-8256-1a7db9bc0fbb |  | note | Record documents - QC Sheets
label | bd532e46-50ac-53f8-b2f4-44926f0f9cb3 |  | note | Responsibility - Contractor
label | 4976c1e2-3d1a-5063-bf53-50b7808b315b |  | note | Comments - THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT.
checkpoint-status |  |  | checkpoint | .4 - Bases, Footings and/or Toes
label | 44e09303-9fbe-5f19-a7c1-4be8bca27a2a |  | note | Detail of Activity - Subgrade Testing
label | 6f6466fd-4d76-5ff6-a33f-8a61d6214430 |  | note | H
label | e58ccaa8-03ce-5834-9ec5-8130b06bb6d1 |  | note | Minimum Test Frequency - Every 20m
label | 6a67f84a-2486-5dd9-9cbc-6aa6ae243efa |  | note | Inspection / Test method - Scalar Penetrometer
label | 0a4d966f-e77d-5cb4-ad69-0b7929a7a525 |  | note | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth.
label | 6bec47eb-b7c0-593c-83c3-97f6f2eee2ca |  | note | Record documents - QC Sheets
label | 6d4e888f-e631-5b34-b084-a64e9463e1b6 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .5 - Bases, Footings and/or Toes
label | e23f6817-5ca5-58d9-b4e0-c83fc167c873 |  | note | Detail of Activity - Reinforcing
label | 4fb04d3e-fc89-56b3-8a65-6af36a9ce906 |  | note | M
label | 9132f6a7-7933-5e1c-8e4f-dc8db7e16523 |  | note | Minimum Test Frequency - Every 6m panels
label | 6c1104d0-e791-58e8-9e57-b27e7c8fa622 |  | note | Inspection / Test method - Visual Inspection
label | 66e6dcd7-e255-589b-95b8-d8fc1bcc941f |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | 11c5a9ae-6b91-5e86-b006-3ce4739663ca |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | 945600ad-377d-5206-b31a-5494a212cb25 |  | note | Record documents - QC Sheets
label | c9907e4e-2073-5529-82b1-5d647080f657 |  | note | Responsibility - Contractor/Engineer
checkpoint-status |  |  | checkpoint | .5 - Bases, Footings and/or Toes (2)
label | 248e40f6-3a8e-5d0a-a468-1e9b27591b30 |  | note | Detail of Activity - WSP INSPECTION
label | bdd85db4-0de4-59b4-9baa-3eae517ab9e4 |  | note | H
label | 961ad5db-d3c1-5065-8ca6-7fd5bb96fff2 |  | note | Minimum Test Frequency - Every 6m panels
label | 7abcbb09-0af6-5ccd-ab6e-26f2e6c4dc78 |  | note | Inspection / Test method - Visual Inspection
label | 860b0906-e1da-52b3-ac71-754b93c4661d |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | a90b6124-00bc-5fd7-8151-5a1db9c813f0 |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | 4366f5d1-a912-5d22-9c6b-450b399fe7cb |  | note | Record documents - QC Sheets
label | a386d624-d994-5e4d-bcfd-e827da8eca4c |  | note | Responsibility - Contractor/Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .6 - Bases, Footings and/or Toes
label | 555214e4-15ed-56db-a271-adc7ccae12ff |  | note | Detail of Activity - Formwork
label | 4e499663-e7e4-5101-bf39-0255fe37d095 |  | note | Minimum Test Frequency - Every 6m
label | 68b36227-bf81-505a-bb9c-ffdd4ac071ff |  | note | Inspection / Test method - Visual Inspection
label | 9258313d-66d8-5203-a407-db029ca7c073 |  | note | Acceptance Criteria - As per drawing
label | b60a0023-a6f6-5f3f-a14e-214c09be2e9f |  | note | Record documents - QC Sheets
label | f954b3a6-f369-573e-8abe-42f9c9505777 |  | note | Responsibility - Contractor
label | 3a07bf6f-8c77-50e5-bd8b-81296f0ca020 |  | note | Comments - FORMWORK SUPPLIED BY DOKA
checkpoint-status |  |  | checkpoint | .6 - Bases, Footings and/or Toes (2)
label | a93ee675-9f79-53e4-a3f8-8a94448d20b1 |  | note | Detail of Activity - Concrete
label | 4c654b2f-f7a3-56e3-89f0-8c742f5339a0 |  | note | H
label | bfb14c78-64c3-504b-8672-5c9d1c13691d |  | note | Minimum Test Frequency - All concrete orders
label | a18fe902-c77f-5d50-8192-a06f2a54383e |  | note | Inspection / Test method - Concrete Dockets
label | e45fe36c-7478-511d-b429-471130a1460f |  | note | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | e5d71eb4-7189-5a23-ad7a-7c2207439ad6 |  | note | Record documents - Concrete Dockets
label | b1944f55-ca54-5128-a50d-4baa5a573caa |  | note | Responsibility - Contractor
label | 226a14f9-1786-573d-93f4-ac6d0b207b4d |  | note | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | c1a62ba8-a6cf-54b4-8062-44e4921e3ae4 |  | note | • ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
label | b94313bb-4a8b-5171-a36a-850f374ddb4b |  | note | • THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .7 - Bases, Footings and/or Toes
label | 0d36684b-48bd-5006-b7b8-594a2ff8bdf9 |  | note | Detail of Activity - Dowels (greased and plain ended)
label | d66d11a6-2760-5e0e-b7f8-48127557316c |  | note | H
label | 423db358-6aea-576f-9b74-a540e3a0f523 |  | note | Minimum Test Frequency - Every 300mm centers
label | 55bfa214-b67c-516d-8e75-4a844f9e82b5 |  | note | Inspection / Test method - Visual Inspection
label | a3493e97-0de4-5059-aec8-534351bd4864 |  | note | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS
label | 0e8254ba-5bbf-51f8-b726-436f0c7ce79e |  | note | Record documents - QC Sheets
label | 3ff3b18a-3c81-5bde-a7f5-aac63504d595 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .9 - Walls
label | 78de2d51-2ad0-58bf-97a8-bc02ea946dba |  | note | Detail of Activity - Reinforcing
label | 8401053a-5b11-5a85-90f0-76604ece4ae7 |  | note | M
label | 0e5f8181-e775-56af-b2cd-f5f326fbcd02 |  | note | Minimum Test Frequency - Every 6m panels
label | 82649a37-d679-5ffd-960a-cc93a4e165c8 |  | note | Inspection / Test method - Visual Inspection
label | a4f4cf7b-0d59-5d10-8f3a-558bebb6355e |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | dc337b21-f635-53c1-88bb-c10f602aa760 |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | bffccc93-c699-5bea-bf40-02f856d4f879 |  | note | Record documents - QC Sheets
label | c41b5c21-6667-503d-a9a2-fb5b9c5f9507 |  | note | Responsibility - Contractor/Engineer
checkpoint-status |  |  | checkpoint | .9 - Walls (2)
label | 4e47ac8c-83a4-51fd-87bd-4e1478b10e8b |  | note | Detail of Activity - WSP INSPECTION
label | 20a79f12-c5d9-503f-a4ff-56566de0c22f |  | note | H
label | bb63a194-a49b-5908-a09b-4dd797a4700e |  | note | Minimum Test Frequency - Every 6m panels
label | d9cb24fe-d1c6-545a-8966-dc5ec413b332 |  | note | Inspection / Test method - Visual Inspection
label | a14e82c9-b673-5d3f-8f59-419c259ca1b5 |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | f241b69a-cbb1-5233-a933-0b189b7e164c |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | e395a9d3-e6f1-51d6-b2a6-795ec35dc9cd |  | note | Record documents - QC Sheets
label | e9aeac44-2853-5dfa-a6c0-c9f44da7518c |  | note | Responsibility - Contractor/Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .10 - Walls
label | 6058771e-20cf-53b0-be96-563f3a15b297 |  | note | Detail of Activity - Formwork
label | 7a79795d-8c45-5dd8-b334-ead9310a4fc4 |  | note | H
label | 80ea54c7-e2e8-5acc-a7c9-bb6859551411 |  | note | Minimum Test Frequency - Every 5m
label | a9d7bdbd-74ce-5388-ae8f-183f418cf8d3 |  | note | Inspection / Test method - Visual Inspection
label | 7f05ce1a-25e6-501c-aca0-b97913edc127 |  | note | Acceptance Criteria - As per drawing
label | ab97ead9-ca82-5e58-9d54-f390723035c2 |  | note | Record documents - QC Sheets
label | b21e4d79-b6c4-5097-ae26-2f2718f9f2d0 |  | note | Responsibility - Contractor
label | 0b64499c-48a9-566a-bdf0-34f7cb4a46b7 |  | note | Comments - FORMWORK SUPPLIED BY DOKA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .11 - Walls
label | 46e64e3b-5146-51ee-8853-2aceac9ddeff |  | note | Detail of Activity - Dowels (greased & plain ended)
label | 426f4635-a1e3-5386-a8b8-708cd7c91ed3 |  | note | M
label | 66cb1b79-919a-504b-9b05-91a47e36f3f2 |  | note | Minimum Test Frequency - Every 300mm centers
label | 7f6af286-ce42-5be2-8033-4553fa6cfb9d |  | note | Inspection / Test method - Visual Inspection
label | a6cb24fd-bd20-5fe3-88ac-a536b51b02c0 |  | note | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 5.0m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED
label | d0f9ac41-5179-582b-882f-e5ddc7b6166a |  | note | Record documents - QC Sheets
label | b7e1a74d-30c9-5ffb-8e00-3849d0a4414b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .12 - Walls
label | 50b6cb17-41bc-536d-bc3d-5e86b6eeedfc |  | note | Detail of Activity - Finish / Joints
label | ade0cfb6-399d-5327-90f3-34e6de177970 |  | note | W
label | 7371f567-106b-5e1a-a657-186a7a45c897 |  | note | Minimum Test Frequency - All areas
label | 46d7ed1c-cebf-564e-b5b3-acfbe9ca4b8f |  | note | Inspection / Test method - Visual Inspection
label | 81000cbb-40e5-5185-aad8-e4b183c8da4c |  | note | Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate.
label | 1bdeb65f-e261-5d90-9edb-663d4ad6df77 |  | note | Record documents - QC Sheets
label | 325170b0-b2c9-5191-8e4f-9fc7aede07c6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .13 - Walls
label | 3fbd486d-54cc-5183-bc3a-ab308852378c |  | note | Detail of Activity - Concrete
label | 90c6bd8b-4b33-553a-b674-dacddd8f9159 |  | note | H
label | f7e0ad55-1d7a-595c-a706-172ba06a3ed9 |  | note | Minimum Test Frequency - All concrete orders
label | b1921a98-05a2-5ea4-a53b-28166690bbe1 |  | note | Inspection / Test method - Concrete Dockets
label | c31804e3-597b-5369-8382-f6a1371a1c24 |  | note | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | 3a137108-b4cf-5246-a1b0-0a311c0d3a3c |  | note | Record documents - Concrete Dockets
label | aa372659-38d0-547e-9845-4d3a958163b1 |  | note | Responsibility - Contractor
label | 78da034c-7982-5e7c-bd1b-96f03ac4e5a3 |  | note | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | c1bb3056-cdae-5afe-8af6-5f56a291c502 |  | note | • ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .14 - Walls
label | 42cf30a2-e61d-54eb-b1f0-b09ced491e56 |  | note | Detail of Activity - Weep Holes
label | ca04536f-85c6-5d2c-a1b6-f70668afb9f7 |  | note | W
label | 6f13cab9-4a47-5226-a0af-69ee471fa0bf |  | note | Minimum Test Frequency - Every 2,000mm
label | c4cd8ab0-b3ac-55e9-a7fb-21cf345f2148 |  | note | Inspection / Test method - Visual Inspection
label | 7f91f5f1-6fb4-5bee-81c8-f266cdfa0266 |  | note | Acceptance Criteria - As per drawing
label | edc95259-8354-5ce9-a85a-b561c7a04495 |  | note | Record documents - QC Sheets
label | 77067acf-8bf7-5db0-8a6d-8569a3d0925c |  | note | Responsibility - Contractor
label | 1c0aae70-5147-5527-b6ae-e49a3d4330ce |  | note | Comments - 50mm Ø WEEPHOLES THROUGH WALL STEM AT 2.0m INTERVALS
checkpoint-status |  |  | checkpoint | .15 - Backfill
label | 6b8c2659-9613-518b-9b4d-6a12e4eb9ae3 |  | note | Detail of Activity - Backfill behind wall (Shared service trench)
label | 90894e4d-cfb3-5a10-b758-63387231c495 |  | note | W
label | 19d1e4d1-9f48-58e7-8b97-c661f08316f6 |  | note | Minimum Test Frequency - Refer to Shared Service Trench ITP
label | dec13276-aa40-59d5-82d3-e70df36b31a6 |  | note | Inspection / Test method - Refer to Shared Service Trench ITP
label | 700233e2-de26-579a-984f-9f7dee5d6276 |  | note | Acceptance Criteria - Refer to Shared Service Trench ITP
label | fc6067d1-c333-57b0-ab00-026544f9e3e6 |  | note | Record documents - Refer to Shared Service Trench ITP
label | 7478b117-ad73-5d87-97eb-f659f47ed3d4 |  | note | Responsibility - Refer to Shared Service Trench ITP
label | 2b706ddf-ed44-53a1-9342-b2fd0fb65a85 |  | note | Comments - Refer to Shared Service Trench ITP
checkpoint-status |  |  | checkpoint | .16 - Joints
label | ef6a5909-ac3d-5630-ab75-3a7276c09c74 |  | note | Detail of Activity - Completed Joints
label | e1970a41-905a-56c7-a279-dbd7dbb9af7b |  | note | W
label | 8d075182-8686-57ba-b1dd-1837712ba1c3 |  | note | Minimum Test Frequency - All concrete orders
label | e4cac294-e1f6-5b22-b2c4-9d1d350fcaee |  | note | Inspection / Test method - Visual Inspection
label | 007e08f5-0ba6-57e7-afb0-7ff3d622b650 |  | note | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | a9293d7f-f5c0-52f7-b684-49169de9908e |  | note | Record documents - Concrete Dockets
label | 92b9885d-5eee-58c8-8604-36bc2c0c5448 |  | note | Responsibility - Contractor
label | a4299cc5-9f65-5190-a576-e5bdfdda8996 |  | note | Comments - SIKAFLEX SEALANT OR APPROVED EQUIVALENT
checkpoint-status |  |  | checkpoint | .17 - Joints
label | e7f2342e-8db1-56e8-9063-6706fd3e3d7a |  | note | Detail of Activity - Joint formwork
label | 4e0a676e-a7a6-5432-a3cc-64c47e3aeb1d |  | note | W
label | 1f6f5164-a739-5597-8bf8-4ce1d1c00cae |  | note | Minimum Test Frequency - At joints between sections
label | 4ac12ac3-e3e1-5ea6-841d-14cbf60a5353 |  | note | Inspection / Test method - Visual Inspection
label | 4fa5380c-35ee-57d1-ac6a-1c12bd4d8bda |  | note | Acceptance Criteria - Smooth, off shutter finish. Construction joints as per drawing
label | 93bc5e15-1335-5a7d-b1c9-1492905e6176 |  | note | Record documents - QC Sheets
label | 8eec121a-cc8e-5c91-89c4-911f91c42267 |  | note | Responsibility - Contractor
label | 5cb34c23-c1c4-5716-a100-037d585346b3 |  | note | Comments - COMPRESSIBLE BOARD BETWEEN WALL SECTIONS
checkpoint-status |  |  | checkpoint | .18 - Subsoil drainage - front of wall
label | 76600f48-d781-5acd-9933-7362ebdbd338 |  | note | Detail of Activity - Subsoil drain - back of wall
label | 1d05c38c-59a4-5b96-aa6f-a96ccd434104 |  | note | H
label | bd84c01a-12f3-525d-89b0-c127e7f6f04c |  | note | Minimum Test Frequency - Length of wall
label | f20771cd-5601-5659-8766-1d1aa84b08af |  | note | Inspection / Test method - N/A
label | c6423d36-d7a4-5056-98a2-59a1b924966e |  | note | Acceptance Criteria - As per drawing
label | 66d91f69-e804-597e-99d3-79b5f5f6fd8c |  | note | Record documents - QC Sheets
label | 5f8b1a33-c913-5c92-a0c5-ebfaa4b9cb83 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .18 - Subsoil drainage - back of wall
label | 953a795c-d711-5872-8c41-5325c98eba00 |  | note | Detail of Activity - Installation of subsoil drain
label | 0c64a1e4-b204-59b1-a55d-6116e3dba580 |  | note | H
label | 3be016d3-1e42-5536-86de-1fdedc83a6e3 |  | note | Minimum Test Frequency - Length of wall
label | cf622e87-7684-56ce-8b59-551be59ab9e0 |  | note | Inspection / Test method - N/A
label | f9cda22d-7518-5ae9-83da-c5c45d798477 |  | note | Acceptance Criteria - As per drawing
label | b253e12b-828f-5547-bb64-cd81a4705348 |  | note | Record documents - QC Sheets
label | 21137880-ec12-5367-b8e2-da1876fb3304 |  | note | Responsibility - Contractor
label | 850e6ea3-9e3c-5eb8-8280-9f25bacc5e1b |  | note | Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | .20 - Collate above documentation
label | 09fd92bd-e3af-5664-bc22-c8e0e7b976ff |  | note | Detail of Activity - Document review
label | 7c07a862-c05c-50a7-86fe-53d6403d8cf7 |  | note | H
label | 43096411-306b-55ef-8408-3a3d79302042 |  | note | Minimum Test Frequency - Each ITP
label | 95789fb6-9a94-5a4f-a060-77d5e5883b24 |  | note | Inspection / Test method - Review
label | b3c69935-dc1c-59c6-bf40-e2532ee391ed |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 5868a199-2df7-58c2-bf70-aba087157c0b |  | note | Record documents - Review
label | 4e9dbd2d-bc23-5b1b-a50f-e5dadf42d8aa |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .21 - As-built drawings
label | 39eb6dc4-0d62-5cf5-9fea-35e28a7e2f94 |  | note | Detail of Activity - Survey
label | 7e455253-bda0-5180-89f8-a831030f1fde |  | note | H
label | f8524b42-e7dd-59d8-86e7-7a4f2fdeac25 |  | note | Minimum Test Frequency - At completion of construction
label | 6d948b7c-4943-52d8-a085-540c002ae4c4 |  | note | Inspection / Test method - Asbuilts to besubmitted at the completion of construction, information to be captured
label | c6f81283-0f72-5c2a-84e5-f04c72183525 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 1735577b-1016-5186-affe-757d5b85b9b0 |  | note | Record documents - In Eight record
label | f3c7c634-9123-53a2-a743-91f043bd6e79 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 451de089-1f68-51b4-b16b-b082c048853c |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 977027b8-95b4-50bd-b972-4dd6fbd3aeb1 |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | e504052f-8467-5ef0-9127-3eff94ce8d34 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | effcd013-472b-5be1-86d2-2cdf0acc9ad0 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Shared Services Trench | itp |  |  |  | Yes | ITP - Shared Services Trench | e1370c48-9e34-4fa9-8753-6adc9c2eadb1
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 100.1 - Method Statement Development / Job Safety & Environmental Analysis
label | d52f9343-0408-50ca-804b-5befb797cd59 |  | note | Detail of Activity: Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | a746fd45-9d61-5a93-a689-9252bb779e53 |  | note | H
label | 35b9cdaa-7b5d-5aba-9e92-7b6aab78483c |  | note | Minimum Test Frequency: NA
label | 56372370-82e3-5eec-977a-d18075136a0b |  | note | Inspection / Test method: NA
label | fd5dad64-e9ba-5a7d-8ca1-f1a3c4a139a4 |  | note | Acceptance Criteria: Method Statement and JSEA Completed and signed by relevant authority.
label | 17db8fe7-7448-540e-bbd6-e7e809547641 |  | note | Record documents: MS & JSEA
label | 34650602-ec83-55f8-8bff-b62341cbd092 |  | note | Responsibility: Contractor
label | cfb7d730-8324-590d-9b49-1ac99af46f11 |  | note | Comments: Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.2 - Drawings and Specifications
label | b783f199-622d-5caf-98f9-4cd3509b3ec6 |  | note | Detail of Activity: Check drawings are for construction and latest revision. Check Specification is for construction and latest revision
label | d00dd963-8752-55af-af34-4a3f811ccb9c |  | note | H
label | b14c8c6a-b0fa-567b-ad0f-51a6fb690609 |  | note | Minimum Test Frequency: NA
label | 21bfa70e-9823-5ddd-abb2-ca0ababea69b |  | note | Inspection / Test method: NA
label | 5d8f42ff-c31c-5ea6-999c-ede6ff4ed825 |  | note | Acceptance Criteria: Drawings and Specification are the latest revision.
label | 1dddb281-9f9d-543c-9383-259654c29e3f |  | note | Record documents: IFC Drawings and Specification
label | c8d02ccd-e924-5df0-950d-d2701c0f4b19 |  | note | Responsibility: Contractor
label | a6dab572-5fc5-550f-931c-b2c89da666e0 |  | note | Comments: Up to date drawings and specification to be reviewed before construction.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.3 - Ducting / Piping
label | c1135a14-0814-5b42-a45f-b6986871cae2 |  | note | Detail of Activity: Power, Telecommunications and Gas ducting / piping to be provided by the service provider.
label | b41a26b1-9657-5208-be71-ba8e1906da88 |  | note | W
label | 790a459c-e1df-5972-b47e-27e273ae151e |  | note | Minimum Test Frequency: NA
label | 5f9ad357-bb7d-5466-90c1-1ace9e51ec18 |  | note | Inspection / Test method: NA
label | 285ce73e-2f52-543d-ba09-d045c9ffdb8c |  | note | Acceptance Criteria: All ducting / piping is to be provided by service provider
label | 32a46830-1b0a-59bd-bfea-cb79e04bc230 |  | note | Record documents: Contract Documents
label | db51b181-0ad4-53cb-92c9-2067e170f68d |  | note | Responsibility: Unison, Chorus & Gas
label | 606ff985-28ba-58f8-85f0-9dca66c0bbfa |  | note | Comments: Ensure ducts are ordered and being delivered when needed
checkpoint-status |  |  | checkpoint | 100.4 - Service Pits / Chambers
label | 1b45b1ba-bdc3-5bc5-a915-4a43c2b44c80 |  | note | Detail of Activity: Service pits / chambers to be provided by the service provider.
label | a463a6a8-e0d8-5882-984b-4215699912ac |  | note | W
label | 73435f88-66de-5a3f-8c95-5d15ad8143b0 |  | note | Minimum Test Frequency: NA
label | 1bfe900a-f947-56bb-be71-1362df58171f |  | note | Inspection / Test method: NA
label | 0e4e863a-5fe2-52d0-864d-9a6e4340976f |  | note | Acceptance Criteria: All service pits / chambers are to be provided by service provider
label | bd66fb62-54c3-52e0-bd84-00487904b1af |  | note | Record documents: Contract Documents
label | 6d0c987a-bc3b-5c0b-999b-90e411b575f9 |  | note | Responsibility: Unison, Chorus & Gas
label | 0806ba6b-1b31-5641-ab35-d3451c8991a4 |  | note | Comments: Ensure service pits / chambers are ordered and being delivered when needed
checkpoint-status |  |  | checkpoint | 100.5 - Tape / Mag Slab
label | 8fd54965-5391-592a-864d-5c526dd644f2 |  | note | Detail of Activity: Warning tape / mag slabs to be provided by service provider
label | c64d8cb1-1c47-5e60-814b-f3401818fd8d |  | note | W
label | e32884f8-f922-557d-8ecb-b9347d13f7c9 |  | note | Minimum Test Frequency: NA
label | 6184aa06-7ce5-5c7d-8d03-0978bcf8d93e |  | note | Inspection / Test method: NA
label | 2daf8c70-29e2-54c0-833e-f2253903f658 |  | note | Acceptance Criteria: Warning tape / mag slabs to be provided by service provider
label | 5d2a0039-2a98-56ab-98b4-9669827c5f52 |  | note | Record documents: Contract Documents
label | 4839c1cc-500a-59c1-9519-d60f6620fea8 |  | note | Responsibility: Unison, Chorus & Gas
label | 1e0d1a3d-54c3-5c00-ae0b-c07e5e8a235d |  | note | Comments: Supplied by services provider.
checkpoint-status |  |  | checkpoint | 100.6 - Survey Set Out
label | 91eafdcf-6d14-5dd1-9e95-ae63b195aceb |  | note | Detail of Activity: GPS Setout of the shared services trench location as per the construction drawings.
label | dfd011e7-8ef5-54ef-bc37-e608f78bab70 |  | note | W
label | 9becb08e-42e0-5f36-b67c-1841a41d2df9 |  | note | Minimum Test Frequency: All shared trenches.
label | 5f92234e-18b0-5661-9c07-df2f54229c53 |  | note | Inspection / Test method: Visual Inspection
label | 5e089d83-fb4e-5913-8129-173b51be989d |  | note | Acceptance Criteria: N/A
label | 2f0654cf-8dc8-577f-b976-64e315eaec7a |  | note | Record documents: Contractor's site diary and/or photos
label | 334a3396-ba34-5c89-ae61-d32759f3edde |  | note | Responsibility: Contractor
label | 3ceae959-8a46-507f-bb4c-67daa1b3a256 |  | note | Comments: Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 100.7 - Sediment Controls are in place for the particular section
label | adcb36ca-158d-5097-bbf0-97b1451db633 |  | note | Detail of Activity: Check ESCP and ensure any controls needed are in place before excavation.
label | 06aa0448-3edc-5b96-80ab-4c7b323c7146 |  | note | M
label | b812460b-f0b5-5e40-8018-939e3f58f35a |  | note | Minimum Test Frequency: once per section
label | 977f7e25-5ea0-5d9b-afe4-92fc47d74ca1 |  | note | Inspection / Test method: Visual Inspection
label | 0187263c-c7c2-56f5-bb12-9bf4260a2240 |  | note | Acceptance Criteria: Erosion and Sediment controls are in place prior to starting works.
label | e008f9b1-612e-5299-ac8e-36fdcb7d061e |  | note | Record documents: Contractor's site diary and/or photos
label | 0933bc53-98c1-5195-98b0-220e61d952d2 |  | note | Responsibility: Contractor
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 100.8 - Excavation of trench
label | 944acbca-652d-5fc9-82f4-16773bf0619b |  | note | Detail of Activity: Confirm trench excavation is to the correct dimensions
label | c86d6e16-3e6a-599f-841b-a849ae582980 |  | note | W
label | 516f269f-9cf3-53fe-8a40-ef0a548750d1 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 9be6304b-1cb0-5271-a773-d4d25ed6e2d6 |  | note | Inspection / Test method: Visual Inspection with tape measure.
label | eb75479a-4e35-5b50-a4ff-df5f69ccc795 |  | note | Acceptance Criteria: Formation materials in accordance with design assumptions.
label | 46881c51-b44a-554b-bea8-e9c95a1fa7d6 |  | note | Record documents: Contractor's site diary and/or photos
label | 0d5889b5-c71c-5847-97bc-89e5e36a97af |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.9 - Installation of Ducts
label | b489e469-d656-5d64-8fc9-08bf3be41d08 |  | note | Detail of Activity: Temporary Capping
label | 72208796-7c1b-5551-b55c-5921e5e98cc7 |  | note | W
label | 5437b37d-42a8-5fc4-9e69-7bec51e9c186 |  | note | Minimum Test Frequency: At the end of each day.
label | fafe8602-c958-5463-b5fb-a266a5d9e4d3 |  | note | Inspection / Test method: Visual Inspection
label | c41740c2-b4ca-5cd3-887d-1c320ed5231d |  | note | Acceptance Criteria: Ensure any open ends of ducts are temporarily capped to prevent ingress of dirt.
label | 4c4e3ecb-9c87-5348-b13c-f7f3a7f93bed |  | note | Record documents: Contractor's site diary and/or photos
label | 65f3bbcc-0686-5632-9ceb-c8bea3d70bc3 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.10 - Installation of Ducts
label | 586b15f1-d6a1-504d-a63e-1ac18f16b5fa |  | note | Detail of Activity: Duct Spacings
label | d32bfc39-4938-5af2-81a8-7be480307d02 |  | note | W
label | d1303286-3751-5092-a90b-a13d53655b31 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 789950f0-2636-512f-ae06-4f5be8bdcb76 |  | note | Inspection / Test method: Visual Inspection with tape measure & photo.
label | da31d5d5-ef2c-5d03-8768-3d77c5ff4025 |  | note | Acceptance Criteria: Check ducts are spaced as shown in the trench cross section.
label | 08fc0278-8c5a-539e-98ce-81fc44e58e74 |  | note | Record documents: Contractor's site diary and/or photos
label | 06cb35ee-ecb7-5099-98d2-2cc90e05d205 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.11 - Installation of Ducts
label | 89c9f853-d097-59cc-a525-1b5fa2b26ddd |  | note | Detail of Activity: Good for purpose check
label | bd4b43db-46e2-52e5-9830-1f5be8fbeb61 |  | note | W
label | 6ea738d4-69df-5e34-bf5e-810fb6268eb0 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 0764ded3-4104-57bc-9250-b3678f72be88 |  | note | Inspection / Test method: Visual Inspection
label | c1891e6d-135b-5dfd-b66c-70dfcff129cc |  | note | Acceptance Criteria: Prove. (i.e. laid straight with no kinks, correctly connected, not squashed/damaged, clear of blockages and any materials such as dirt and cement)
label | aa81f576-8256-5bba-8e82-fb7afcb88530 |  | note | Record documents: Contractor's site diary and/or photos
label | 923671dd-5fac-5657-8060-853d50238034 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.12 - Installation of Ducts
label | da30fb25-fad8-55bd-9387-f461d5095e46 |  | note | Detail of Activity: Protective Tape / Mag Slabs
label | 59081a89-4755-5814-9f06-e1304dbae44f |  | note | W
label | fb32e2d0-f8dd-5f74-a3e9-221524abf835 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | ddfac55b-6b87-5577-9a34-e7ac38b8a638 |  | note | Inspection / Test method: Visual Inspection
label | 0cdb8232-a4e1-5276-9724-cdd73b656c86 |  | note | Acceptance Criteria: Placed in trench as indicated in drawings
label | d93ec248-5543-5c4d-9e55-3c01e1f69b9c |  | note | Record documents: Contractor's site diary and/or photos
label | 0bf191ba-d3cb-5c7d-886d-001dfa4222bd |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.13
label | a96c7ad5-7b2a-59b2-b6aa-2f33919ac0fb |  | note | Detail of Activity: Compaction
label | 3557cc6c-97be-54a1-b893-52795e1ad478 |  | note | H
label | f444e8c5-5337-5492-9050-48635c4a3293 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 565eff4c-6c72-5156-95c8-67d1d18ae96a |  | note | Inspection / Test method: Clegg Test
label | a201fa26-0a95-5162-b93f-aa5ee886d849 |  | note | Acceptance Criteria: Top of trench in berm. CIV ≥ 15.
label | c8888937-6ffe-5770-9908-6fd22aa5a9c8 |  | note | Record documents: Scala/Clegg QC sheet
label | 0fa93df0-6b54-57e5-975b-3354dfa0e928 |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.14
label | 0bb6b3f8-503b-5e5b-8c57-89f13eaa3236 |  | note | Detail of Activity: Layer Thickness
label | 0963df86-56ee-57ee-bd37-966e85b8b50f |  | note | M
label | f7357e82-224d-58ef-a297-f19a27b1e381 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 4284bdab-d4b1-5559-9378-bb6db2e86476 |  | note | Inspection / Test method: Visual Inspection with tape measure & photo.
label | 0aa0ba52-0023-558a-8cd8-40c836be5dfe |  | note | Acceptance Criteria: Layers ≤ 300mm thick
label | a6c2dee6-ff4c-511f-a17d-6e9eb729250c |  | note | Record documents: Contractor's site diary and/or photos
label | 13d20b4b-2b59-589e-8ff7-03371f385f12 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.15 - Pavement Layer Construction
label | 8c37175c-5078-501c-b393-1200b366abe4 |  | note | Detail of Activity: Subgrade
label | 9d3e0d94-51c5-59f9-8384-65b08452209a |  | note | M
label | 8a1512cf-9eb0-5bb3-9e38-1706974e8692 |  | note | Minimum Test Frequency: Every 20 lineal meters in pavement.
label | 0db043f8-2ac4-5291-bdfa-868b709a7c31 |  | note | Scala Test
label | e05d2ff3-0e5f-5ff6-8fcc-746651161337 |  | note | Acceptance Criteria: Scala 500mm deep. Target = 3 blows per 100mm.
label | 0092dd7d-b075-5115-a3ef-49f6c056011c |  | note | Record documents: Scala QC sheet
label | eac23ca3-1122-5951-b995-1dcdfbc72efe |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.15.1 - Pavement Layer Construction
label | d6c021b2-50af-5b6f-b5f1-75a9e194ca9f |  | note | Detail of Activity: Subbase
label | d3da921a-5b80-5b72-82d6-cc92cafcb096 |  | note | M
label | 8c33dfb7-2ab5-559c-8355-501628f51069 |  | note | Minimum Test Frequency: Every 20 lineal meters in pavement.
label | 9ec937e7-5a05-5291-820e-87caba207855 |  | note | Clegg Test
label | a9cdd4b6-21f4-5d65-b671-483aa0ad2248 |  | note | Acceptance Criteria: In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 20.
label | 43414843-69e6-5741-a484-82b74b825724 |  | note | Record documents: Clegg QC sheet
label | b329b8ba-4805-5750-97bd-6550d3527be7 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.15.2 - Pavement Layer Construction
label | 0149b2bf-72b0-5847-88bf-7251ec50d7af |  | note | Detail of Activity: Basecourse
label | 1d9179ef-c60e-5f03-88bb-1ce2ec5dbb83 |  | note | M
label | 76dfcb64-6730-5288-9934-3339bd81c839 |  | note | Minimum Test Frequency: Every 20 lineal meters in pavement.
label | 9ce15986-7bb8-5a33-ac0e-5aaeb9e5f966 |  | note | Clegg Test
label | 458c1c00-ffbd-58b4-b45d-57a1b00f7d71 |  | note | Acceptance Criteria: In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 35.
label | 58e1fd57-db7c-59e7-8939-ca3b2417e244 |  | note | Record documents: Clegg QC sheet
label | d2fc887a-37bd-535f-a2ab-0b7c0997a2cc |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.16 - Finished Surface
label | fa2f6ad4-a1b8-55c1-929f-1d873cdd7c68 |  | note | Detail of Activity: Visual Inspection
label | b000732a-b8e0-5578-a1e3-b9c5c91a6b41 |  | note | M
label | eca696a4-dda3-5030-bdf2-c51364b179b5 |  | note | Minimum Test Frequency: All filled trench surfaces
label | 4d44339c-191a-5373-b9bf-9452bd591956 |  | note | Visual Inspection
label | 258a9d04-3958-5741-aff4-4addcc64ae50 |  | note | Acceptance Criteria: Left appropriate for temporary or permanent use (as applicable). I.E. temporary sealed, left flush or ramped with surrounding area and maintained.
label | 80b3aeb7-1112-5563-a375-7ce7f7f11b42 |  | note | Record documents: Contractor's site diary and/or photos
label | bdf7dad0-18ca-5bc3-9730-a94644cd42f7 |  | note | Responsibility: Contractor
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 100.17 - Collate above documentation
label | c0489889-e6d9-55f0-903c-c578a88b218d |  | note | Detail of Activity: Document review
label | 7a3f857d-aad9-5d94-b3ed-efd8dc77f03b |  | note | H
label | 30f4d8f2-46f3-5d9e-851b-aa6bd59d588e |  | note | Minimum Test Frequency: Each ITP
label | 8ed650af-8521-53c6-855d-2c19af41d6f5 |  | note | Review
label | 59f24eb0-33af-5f0b-90a1-33345dcaa920 |  | note | Acceptance Criteria: All above documentation is shown as attached to this work pack.
label | 3228fb03-f5c9-5880-9e35-7fbde2b83ee5 |  | note | Record documents: Review
label | a4168edd-dc43-5142-865c-43f4fd9b4faa |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.18 - As-built drawings
label | 857ca7ef-bd82-538e-b51b-27bc296ea91f |  | note | Detail of Activity: Survey
label | c06ad5cb-339a-5f78-aa17-6b962549025b |  | note | H
label | 173646fd-b510-58b6-94b1-bc7ea782b13e |  | note | Minimum Test Frequency: At completion of construction
label | a4b47731-c905-5314-b1a8-044104ea807c |  | note | Asbuilts to be submitted at the completion of construction, information to be captured
label | 9a103b79-1dc3-593f-a882-68184401f0dc |  | note | Acceptance Criteria: Asbuilts reviewed and submitted
label | 535bd078-10fb-5ddb-b795-7c81c0048c9b |  | note | Record documents: In Eight record
label | 1707528c-ec41-5beb-b34f-6d42626bb857 |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 8b9cc965-0e0a-59e6-981b-deda5e98f736 |  | textbox | Contractor's Rep Name:
text | ce0f743d-4f04-5bde-a1fb-786791c0bd15 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Concrete Works |  |  |  |  | Yes | ITP - Concrete Works | e5058e26-62ec-4413-82ef-dfdeabaa3d53
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | .1 - Survey Set Out
label | f5c75a8f-cb04-5751-b309-86fd58d4c014 |  | note | Detail of Activity - GPS Setout of the watermain as per the construction drawings.
label | 8003f692-1a43-5a61-9f58-5360b32cb52e |  | note | Action - W
label | f9b45156-f179-50b7-be97-49cb2e5b3063 |  | note | Minimum Test Frequency - All lengths of watermain and connections
label | a03e3d8e-a5a5-593d-ab48-46c46103846f |  | note | Inspection / Test method - Visual Inspection
label | 77543751-c045-5d30-8eaf-a8dbd41b68da |  | note | Acceptance Criteria - N/A
label | f06d0505-ede5-5d53-b713-1dd3a8efcdd4 |  | note | Record documents - Contractor's site diary and/or photos
label | c7f0e722-09d5-5f00-8854-7170c9998859 |  | note | Responsibility - Contractor
label | 3cd400d9-4b4b-5f83-9c24-c10c5c2563ec |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | .2 - Materials Approvals
label | 58346c7b-10a1-518f-b1a7-f0f2d5df8a9c |  | note | Detail of Activity - Submit testing data for the following materials: - AP65 - GAP 40 - GAP 20 - Hardfill
label | f760f0dd-a719-52fb-aeb9-9ecf1b301c7c |  | note | Action - H
label | f099d4b8-7c24-5dc7-aac1-10b4a8beca09 |  | note | Minimum Test Frequency - Once for each material
label | d518c7a1-c31c-5dcf-9361-e280db692b0f |  | note | Inspection / Test method - Quarry Testing Data
label | 5be2152a-e095-5f02-8f6e-38377cd65187 |  | note | Acceptance Criteria - Engineer's Acceptance
label | 55b8055b-7e17-5e83-ba6f-257a35608cce |  | note | Record documents - InEight Records
label | c128ce03-f44d-5b17-b68e-2883f6058fb9 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | .3 - Kerbs
label | 13245d2e-66a8-5d67-bf98-b7666f7e8c26 |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | a6fa2713-76f9-5230-8322-6a338d1394cb |  | note | Action - H
label | c3d0e8cf-4293-531f-a845-a428ed73e6a6 |  | note | Minimum Test Frequency - Every 20m
label | 38b45cae-3f38-5bd3-8e43-26d13f1200dc |  | note | Inspection / Test method - Visual Inspection
label | b0e5fc63-cc03-5066-a1b7-f12c65e5f4c4 |  | note | Acceptance Criteria - 530mm from TOK. Tolerance: - 30mm / +0mm
label | f46a62f0-9aa0-5a59-8195-c2049b31a66c |  | note | Record documents - QC Sheets/String Sheets
label | dcf5b5ba-cb69-5b1b-ad11-75bec3bf695f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .4 - Kerbs
label | 624f931b-dff7-5be1-85b2-d7ed56851d72 |  | note | Detail of Activity - Subgrade Testing
label | 31512d06-55a0-513f-99d6-d7511e399002 |  | note | Action - H
label | 089034df-a984-5bae-b622-8eef133d817e |  | note | Minimum Test Frequency - Every 20m
label | 74b20bd6-f11d-58ec-96a5-d4322606ba6a |  | note | Inspection / Test method - Scala Penetrometer
label | 255df7d9-0ec2-56f5-8bde-b13c032cbc44 |  | note | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth. ≥ 3 blows per 100mm - no undercut. 2-3 blows per 100mm - 200mm. 1-2 blows per 100mm - 300mm. <1 blow per 100mm - 450mm undercut
label | 8e5614e0-ce12-59da-b59a-ad6713daffd4 |  | note | Record documents - QC Sheets
label | 2012c03e-e708-59f4-b374-2c57c66cfa92 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .5 - Kerbs
label | b18038c3-303f-5247-a085-70837b54ae11 |  | note | Detail of Activity - Undercats
label | 4180333e-315a-5353-946f-edd802079e1a |  | note | Action - H
label | 9d91a2cf-9e91-5e6d-b2d9-1ee76cf23a0f |  | note | Minimum Test Frequency - Locations where scalas results are <3 blows/100mm
label | 3c389b4f-b98d-56e7-8e98-32ab8c4cf9be |  | note | Inspection / Test method - N/A
label | a5c745e1-77bd-564f-ba37-b7ee04ff58ac |  | note | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth. ≥ 3 blows per 100mm - no undercut. 2-3 blows per 100mm - 200mm. 1-2 blows per 100mm - 300mm. <1 blow per 100mm - 450mm undercut
label | 4f7849c1-6b3b-557f-87ff-8a9a4b613cd0 |  | note | Record documents - QC Sheets
label | f3bb20a1-17b6-5ad3-b188-3620ae575f42 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .6 - Kerbs
label | b1299469-fe9f-59b1-a4a6-284f3ac8dd58 |  | note | Detail of Activity - Subbase Backfill/Prep Heights (AP65)
label | bd18301c-8d20-53ec-9c24-e4c02788c7ba |  | note | Action - W
label | 64495d5a-674e-5198-91f9-887743998144 |  | note | Minimum Test Frequency - Every 20m
label | a26021d1-d83e-5c3c-b580-3b5ab2924ed6 |  | note | Inspection / Test method - Visual Inspection
label | 0e7880cc-24be-5e4e-8e3c-187c6dcac60d |  | note | Acceptance Criteria - 230mm from TOK. Tolerance: - 10mm / +0mm
label | 88102fd8-93b5-52e0-8c37-a5afd1d7cfc5 |  | note | Record documents - QC Sheets/String Sheets
label | 27c73dd4-fde4-5924-89cc-cb2deb2429e2 |  | note | Responsibility - Contractor
label | 40f7e529-3abc-5f13-8765-adb26b7b3155 |  | note | Comments - Roughly to height with AP65, then can make up final prep height with max 50mm GAP20.
checkpoint-status |  |  | checkpoint | .7 - Kerbs
label | 083e3381-f674-5537-8ad6-2c75505279b3 |  | note | Detail of Activity - Subbase Backfill/Prep Testing (AP65)
label | d608ae4b-33b2-5cf5-bac7-8edda9282eda |  | note | Action - H
label | e60034a7-74eb-5af7-b282-d0f314c0a7db |  | note | Minimum Test Frequency - Every 20m
label | 55d4c7e1-e584-5f9d-bfe2-54f340819ee5 |  | note | Inspection / Test method - Clegg Hammer
label | 29befaa9-bded-5399-8287-bd61af2dddc8 |  | note | Acceptance Criteria - CIV ≥ 20
label | 3d647035-c7b7-5fe8-bdef-44a6b4625ea6 |  | note | Record documents - QC Sheets
label | 14717c6b-d494-57c1-8988-278156543f17 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .8 - Kerbs
label | b2696eb8-7a74-50c5-a149-7956eb96f3fb |  | note | Detail of Activity - Stringlines
label | c0306407-31bd-5a08-a7a0-cd11dd665e8c |  | note | Action - W
label | 0e1a95a3-14e7-5531-a087-6b98e96acbf8 |  | note | Minimum Test Frequency - Along each alignment
label | 07b01ad2-a320-5f64-b261-aef87f5e1d7e |  | note | Inspection / Test method - Visual Inspection
label | 9cc5aff9-27a0-5caf-84a5-7501f520dae7 |  | note | Acceptance Criteria - All stringlines are set per design layout/levels and eyed in to create smooth transitions.
label | 34a507d5-adc6-5645-a94d-57978e378314 |  | note | Record documents - QC Sheets
label | 789bd1ce-52f2-5189-93ca-b7238ccdd120 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .9 - Kerbs
label | 366e0a4f-59e6-5cdb-bb00-9b1cc0b0af9d |  | note | Detail of Activity - Kerb Pours
label | 3bc0a545-0a90-5630-a587-fbd1df6161d6 |  | note | Action - H
label | afa9fff6-9fad-59e3-80f0-1c70c826f46a |  | note | Minimum Test Frequency - All concrete orders
label | 3f965983-5508-5645-9713-e5d57e680c20 |  | note | Inspection / Test method - Concrete Dockets
label | 4ff9616d-dbca-5d20-96b4-b4b82b6125b0 |  | note | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | aadb1ddc-24a0-5218-aa50-6d67f948bbac |  | note | Record documents - Concrete Dockets
label | 234e4418-e659-5ca4-914b-6b85591d0610 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .10 - Kerbs
label | 62f5a570-6454-510c-97ad-1624086164b1 |  | note | Detail of Activity - Kerb Alignment/Levels
label | 0a82ecf9-0775-5910-8117-cd00c9eb515c |  | note | Action - H
label | a3cc9571-9eb7-5aa4-a859-da0f7f598557 |  | note | Minimum Test Frequency - Every 20m
label | 13dc8168-8b59-5438-bd27-70202ed0ffe3 |  | note | Inspection / Test method - Visual Inspection
label | e1a21ad3-a697-5cb6-bc0a-9ac17ee1bc84 |  | note | Acceptance Criteria - Vertical: ± 5mm Horizontal: ± 10mm Straight Edge: ≤3mm
label | fd0bca5f-d444-5000-a06d-baa57484bf67 |  | note | Record documents - QC Sheets
label | 1a74e85f-8018-510c-b78c-906d694635a7 |  | note | Responsibility - Contractor
label | 1ab345de-6b25-57ee-8463-d191755c369a |  | note | Comments - As builts will be provided.
checkpoint-status |  |  | checkpoint | .11 - Kerbs
label | 9853c27d-0a94-560c-a6c2-d65e77c8fb26 |  | note | Detail of Activity - Expansion/Contraction Joints
label | be55e462-e8de-55fd-beae-1b0965d9d644 |  | note | Action - W
label | 9f5de29c-c77a-559c-9501-6461fadda84c |  | note | Minimum Test Frequency - Every 3m
label | aabeb67f-66b1-5dd9-a052-a9c71acc5e4a |  | note | Inspection / Test method - Visual Inspection
label | 962bd7cf-7b8c-5b34-93b9-762ef75c4cd8 |  | note | Acceptance Criteria - ≥50mm deep joints formed at 3m (max) spacings.
label | a76a42ba-88ea-518e-958a-4cf1753d82f8 |  | note | Record documents - QC Sheets
label | fc7fd826-5cc4-50fa-959e-f4b7bdaa055d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .12 - Footpath/Shared Paths
label | 816f3731-fed4-55ab-adbb-692c6175a25c |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | acd5d173-24fd-561b-8443-06fb341b6ab3 |  | note | Action - H
label | ebf55326-bdee-5b37-971c-10059e46fca8 |  | note | Minimum Test Frequency - Every 20m
label | 9ee2e73f-93ec-506d-b3ef-b81ddbfbc4dd |  | note | Inspection / Test method - Visual Inspection
label | fb3b7a89-21e2-5e41-9288-4d024b769745 |  | note | Acceptance Criteria - 150mm from FL Tolerance: - 30mm / +0mm
label | b7edeeb8-b367-5542-b989-dd77aa8273ed |  | note | Record documents - QC Sheets/String Sheets
label | 50f10567-1685-5ff2-9a7f-c997d4b0769a |  | note | Responsibility - Contractor
label | 1f4dd979-98dc-5cff-95f0-82010da22d1b |  | note | Comments - Check for multiple services within the construction area. Compact with plate compactor
checkpoint-status |  |  | checkpoint | .13 - Footpath/Shared Paths
label | 074e149b-ebbb-5a86-8a52-a2477bed39f4 |  | note | Detail of Activity - Subgrade Quality
label | b740a6a0-40a6-556c-901c-b879e0bec4b4 |  | note | Action - W
label | cccca54f-5e64-5176-a9e8-020b81e4706b |  | note | Minimum Test Frequency - All areas
label | aefb27ec-efd2-5df7-b931-9fab3af42b2c |  | note | Inspection / Test method - Visual Inspection
label | 8a2c0269-da9e-5863-9ffa-c939973a4a8e |  | note | Acceptance Criteria - No areas of significant subgrade weakness present.
label | 2a35769e-11dc-5e4b-8803-c41ddb8b3ac2 |  | note | Record documents - QC Sheets
label | 44410a77-7c46-57a0-b0c7-b85273881bd9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .14 - Footpath/Shared Paths
label | 3a555e98-61a3-5415-9cec-618c854bdc75 |  | note | Detail of Activity - Base/Prep Heights (GAP20/Hardfill)
label | 81a43f52-cca9-5185-afe7-1175905f9e17 |  | note | Action - W
label | 8adcf18b-0159-58bd-95c0-9e3e78d5f43c |  | note | Minimum Test Frequency - Every 20m
label | a6d2efa4-2161-53b0-b7ee-97f18347049c |  | note | Inspection / Test method - Visual Inspection
label | 17c12a86-bcf7-5723-9bcc-bf3b0ce0a52b |  | note | Acceptance Criteria - 2% max fall to road or as per drawings. Tolerance: - 10mm / + 0mm
label | d4808565-d1ee-5b32-889b-0700e9674e57 |  | note | Record documents - Stringsheet
label | 73480f89-f771-5ad8-b1cc-ec8be17a675a |  | note | Responsibility - Contractor
label | ed1fc84d-18dd-583e-b1d8-66f8d4e7c81b |  | note | Comments - Roughly to height with Hardfill, then can make up final prep height with max 50mm GAP20 if required.
checkpoint-status |  |  | checkpoint | .15 - Footpath/Shared Paths
label | f42e9089-5cb3-5b53-995d-20897a1c57de |  | note | Detail of Activity - Basse/Prep Testing (GAP20/Hardfill)
label | ade24fba-d43e-5501-9c3b-af4cad38ee86 |  | note | Action - H
label | a011e8e4-81f8-5884-b2d4-1b230d670000 |  | note | Minimum Test Frequency - Every 20m
label | 59a5ea35-c19b-53a2-b29c-c6b2c801b7a9 |  | note | Inspection / Test method - Clegg Hammer
label | fde6aa37-7298-5dc5-a0df-b710d4887e49 |  | note | Acceptance Criteria - CIV ≥ 12
label | a1273fe9-74d7-5266-b09d-816515ecf3ab |  | note | Record documents - QC Sheets
label | 0c5c0548-943f-5862-b09c-276b557a4449 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .16 - Footpath/Shared Paths
label | ed6b4937-12a9-5e60-afb1-c0bd619c52f8 |  | note | Detail of Activity - Concrete Pours
label | 355e5cae-dc9e-59f8-bdea-3cbd89df8931 |  | note | Action - H
label | 01aefaa2-2767-548e-b9c1-06d8d6b53ae5 |  | note | Minimum Test Frequency - All concrete orders
label | 7bbecba5-d67b-5279-9124-2da625934d98 |  | note | Inspection / Test method - Concrete Dockets
label | 0fb20e31-cca1-52bb-a551-9774e3cb7cf9 |  | note | Acceptance Criteria - 100mm concrete strength 20MPa, 3% black oxide, at 28 days
label | e5f4e1de-69fa-58cf-9698-f27745df5dfb |  | note | Record documents - Concrete Dockets
label | 71cf51ea-800b-5ca6-acf2-d28565744dc0 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .17 - Footpath/Shared Paths
label | cda58710-aa0d-5094-a44e-a234936fbf81 |  | note | Detail of Activity - Finish / Joints
label | 229a3b29-97e0-57a2-b348-21a3c32d63d2 |  | note | Action - W
label | 4f6188cf-a536-5e2d-86cf-ce4eee08d461 |  | note | Minimum Test Frequency - All areas
label | 7ca3c2c5-a959-59fd-b2d2-4fe301b15f10 |  | note | Inspection / Test method - Visual Inspection
label | ec343a5c-1d9f-556a-893f-c88aff698bcf |  | note | Acceptance Criteria - Broomed finish. Joints cut at 4m centres.
label | fa9d8719-771b-5921-874c-fa3a0f80814c |  | note | Record documents - QC Sheets
label | 64211c12-a65a-565e-b952-5bf3761f3f15 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .18 - Residential Vehicle Entrances/Driveways
label | dc403529-a4a5-5c21-8e8c-f647597a7bbd |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | c59d376a-9009-50a9-b378-79f813c2c902 |  | note | Action - H
label | 936df976-d0eb-5353-8a7d-466bcf230038 |  | note | Minimum Test Frequency - Once per entrance
label | 205fd7b5-134d-57d9-8d03-bd59029992ed |  | note | Inspection / Test method - Visual Inspection
label | 93bc0d82-2384-5f05-a9ed-22c3abee6e5c |  | note | Acceptance Criteria - 175mm down from adjacent tie in surfaces. Tolerance: - 30mm / + 0mm
label | 5e43ad0f-5cd8-5b90-9127-91daf05ec1c4 |  | note | Record documents - QC Sheets/String Sheets
label | 79c1c8d9-fa6b-5c94-a172-4d1290d38646 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .19 - Residential Vehicle Entrances/Driveways
label | c2624ad2-e4b9-5346-bb6a-b82c51687b55 |  | note | Detail of Activity - Subgrade Quality
label | 0489c15f-322b-587b-a3ca-dac644683d94 |  | note | Action - W
label | 1ea17e0a-8933-5bd5-9fb6-024f4d1692d6 |  | note | Minimum Test Frequency - All areas
label | 8e8ea391-80a5-5a97-8286-ff90e0661683 |  | note | Inspection / Test method - Visual Inspection
label | 24f5dc18-0af4-5752-af2c-12d6b65ccab0 |  | note | Acceptance Criteria - No areas of significant subgrade weakness present.
label | a2f18ffd-9c69-56b1-bd1f-bf219a628971 |  | note | Record documents - QC Sheets
label | 33d4b4c0-d0df-5546-a267-c3a557e28abd |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .20 - Residential Vehicle Entrances/Driveways
label | 34c5f6d5-8d0b-5633-aba7-39e9f259687b |  | note | Detail of Activity - Base/Prep Heights (GAP20/Hardfill)
label | ced01e33-aa98-5e99-afa3-f7d50b137787 |  | note | Action - W
label | 083e16b8-2052-5b6c-a199-2f4b0a8a4c60 |  | note | Minimum Test Frequency - Once per entrance
label | 5268e16d-cb7a-5624-8608-3c7adc0f7717 |  | note | Inspection / Test method - Visual Inspection
label | f144c3b1-5e22-5e0a-81c6-e0bfbdb3674e |  | note | Acceptance Criteria - 125mm down from adjacent tie in surfaces. Tolerance: - 10mm / + 0mm
label | c9874c61-962d-53d5-acc9-44429bf95698 |  | note | Record documents - Stringsheet
label | d119bb7b-7b74-51e6-ac07-189d05c6162f |  | note | Responsibility - Contractor
label | 181d2575-e885-5b16-ad5a-ad58c82bc5e9 |  | note | Comments - Roughly to height with GAP 40 Hardfill, then can make up final prep height with max 50mm GAP20.
checkpoint-status |  |  | checkpoint | .21 - Residential Vehicle Entrances/Driveways
label | 325b42cb-c51d-55c2-b495-50a2253d256d |  | note | Detail of Activity - Base Prep Testing
label | ec2583c8-d44f-5b19-ada6-1e70c6f4bbf7 |  | note | Action - H
label | 7899c920-d51b-5a7f-b2bd-6a59f87c8299 |  | note | Minimum Test Frequency - Once per 10m
label | 810fef35-1ee8-5608-9f9e-c078b0907ea0 |  | note | Inspection / Test method - Clegg Hammer
label | 5116c842-f091-567f-a072-2c227d957c20 |  | note | Acceptance Criteria - CIV ≥ 12
label | c2ebd8d0-19c2-5d7f-a491-55ac50e4793d |  | note | Record documents - QC Sheets
label | caa2a509-a7a6-50ef-a201-7128d690b009 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .22 - Residential Vehicle Entrances/Driveways
label | 1cea6029-63e9-5ae2-a4e7-ecae39d5602c |  | note | Detail of Activity - Base Prep Testing Concrete Pours
label | 7f08c0dc-5030-576f-8e49-5a36afa9f816 |  | note | Action - H
label | c91ca4ad-b570-542d-b2fa-bf06f273034d |  | note | Minimum Test Frequency - All concrete orders
label | d5d12fc1-a4c7-57b2-9b15-5c1abd9d0e8c |  | note | Inspection / Test method - Concrete Dockets
label | 5b34d393-6b9e-5bcc-b4af-c436dd3a6973 |  | note | Acceptance Criteria - 125mm concrete strength 20MPa, 3% black oxide, at 28 days
label | c8c3e0a0-7cf9-589d-8eaf-0342b4d9033f |  | note | Record documents - Concrete Dockets
label | a0a81683-104a-5607-aec8-584b18171350 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .23 - Residential Vehicle Entrances/Driveways
label | fbd11047-a9b4-5d03-bb29-7c103ed539ca |  | note | Detail of Activity - Finish / Joints
label | 4814538e-5f89-5fde-9739-86a15c9f2866 |  | note | Action - W
label | 0b8c2123-b299-5805-9793-3ab291d1a00a |  | note | Minimum Test Frequency - All areas
label | c68ac48c-0ec7-59cb-80ac-07d712fe9ca5 |  | note | Inspection / Test method - Visual Inspection
label | f5c5e56d-3433-5001-ad13-556cfb3f3634 |  | note | Acceptance Criteria - Smooth, broomed finish. No depressions for ponding to occur. Cut joints as appropriate.
label | b1fcda2a-226a-5217-bb43-96a49bffa9f5 |  | note | Record documents - QC Sheets
label | 929da907-d1a3-5fdc-aecb-ad0ef30d9aa9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .21 - Industrial Vehicle Entrances/Driveways
label | b2844c89-d6d5-55f8-aa08-2d1f910dc447 |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | 902c9a2a-4bd1-5a59-981b-c708bb1ead18 |  | note | Action - H
label | cf9b12f6-300e-5cb8-9c29-3d8d7e7d0fe1 |  | note | Minimum Test Frequency - Once per entrance
label | 14e2b36f-983e-53c1-8bfa-d6541ea8e12b |  | note | Inspection / Test method - Visual Inspection
label | 3eaa9fe8-4c32-5734-b098-7c61951c376b |  | note | Acceptance Criteria - 250mm down from adjacent tie in surfaces. Tolerance: - 30mm / + 0mm
label | a04b0357-347b-5a21-9746-273e342a16e6 |  | note | Record documents - QC Sheets/String Sheets
label | 8ef85525-bed2-5929-8202-11371e9ecabf |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .22 - Industrial Vehicle Entrances/Driveways
label | e11f2e6b-e7a9-5851-b939-2b849b0a0be6 |  | note | Detail of Activity - Subgrade Quality
label | cbd86c6e-4ed9-565f-b809-61283edee69b |  | note | Action - W
label | ba82af71-3391-5d4d-a74b-6025240184ee |  | note | Minimum Test Frequency - All areas
label | 0edeccf8-ff10-5263-b002-ebcfe3ba3a21 |  | note | Inspection / Test method - Visual Inspection
label | 80337723-a580-5272-b0a5-7efe574ed4f9 |  | note | Acceptance Criteria - No areas of significant subgrade weakness present. Minimum CBR of 5%. Scala ≥2 blows per 100mm to 200mm depth.
label | 922318ad-9cab-50a8-a4c8-035c229662af |  | note | Record documents - QC Sheets
label | 97e5c377-4b65-57db-864f-c453b80626fb |  | note | Responsibility - Contractor
label | 8e888598-3c51-528d-91eb-1f887b14b5c5 |  | note | Comments - See notes on Drawing D3.3.4
checkpoint-status |  |  | checkpoint | .23 - Industrial Vehicle Entrances/Driveways
label | 62c6028c-ca90-5371-a0ce-5628a343b673 |  | note | Detail of Activity - Base/Prep Heights (GAP20/Hardfill)
label | 6f040918-dc97-5dec-ba04-5a5bb433d47e |  | note | Action - W
label | a9062448-6a24-5391-96a0-c7795955e84a |  | note | Minimum Test Frequency - Once per entrance
label | ae0d5002-ad55-5ffd-8d05-b4daf72720b8 |  | note | Inspection / Test method - Visual Inspection
label | 5b3241f5-9279-53ac-8f64-51e823ecafae |  | note | Acceptance Criteria - 175mm down from adjacent tie in surfaces. Tolerance: - 10mm / + 0mm
label | e213b2b5-e881-55bd-b5de-08ba36967712 |  | note | Record documents - Stringsheet
label | d6c3875b-d9bb-5e37-bac2-1c4ffc331a50 |  | note | Responsibility - Contractor
label | cc03adf6-1a84-5443-848e-ec190cc845aa |  | note | Comments - Roughly to height with GAP 40 Hardfill, then can make up final prep height with max 50mm GAP/AP20 if required.
checkpoint-status |  |  | checkpoint | .23 - Industrial Vehicle Entrances/Driveways
label | 72fd03c0-f032-50f7-9b0d-1e8ce78d1c20 |  | note | Detail of Activity - Base Prep Testing
label | 2f928aba-1c39-54d8-9840-e94d81032d79 |  | note | Action - H
label | 83ae1d9d-69f3-5962-9d92-ea04b921b4c6 |  | note | Minimum Test Frequency - Once per 10m
label | 59b203e0-5bf6-5f34-9b63-54f3c83cb9c7 |  | note | Inspection / Test method - Clegg Hammer
label | d63f33e4-e422-5308-831c-c3031928cf2e |  | note | Acceptance Criteria - CIV ≥ 12
label | 9ee36b61-e113-54f4-b67c-fa5dec3cdecc |  | note | Record documents - QC Sheets
label | 18e64185-e727-517d-831a-5a903ffcdaf6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .21 - Industrial Vehicle Entrances/Driveways
label | 82aedfee-30ea-551b-aaa2-8441339ecd59 |  | note | Detail of Activity - Reinforcing
label | a4090f4b-d759-53fe-85b6-bf85abfa2adf |  | note | Action - W
label | 4ce893a4-1b99-5d5b-a4c4-0b552c3f24f6 |  | note | Minimum Test Frequency - Once per industrial driveway
label | 519be7e6-d587-53d6-8291-942468acc086 |  | note | Inspection / Test method - Visual Inspection
label | a902ea97-e7fd-5635-aadf-8653ccbb949c |  | note | Acceptance Criteria - Reinforcing as per Drawing D3.3.2 on RITS Case A
label | f3a26f75-5744-5622-a279-a91e4cd148aa |  | note | Record documents - QC Sheets/ photos
label | 61fcb003-4bd5-50a9-9e92-ab0b03c72611 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .20 - Industrial Vehicle Entrances/Driveways
label | 45a9d32d-a554-5314-9db2-019944d2a743 |  | note | Detail of Activity - Concrete Pours
label | 0075f8ad-e5d2-5145-a359-34f466c9c91b |  | note | Action - H
label | 91c5464e-51d1-5b27-8d68-5bcebf47cb91 |  | note | Minimum Test Frequency - All concrete orders
label | 748e4248-1093-52f7-9f3d-a41dc290ad44 |  | note | Inspection / Test method - Concrete Dockets
label | 1be6a055-70d2-526b-80e3-404d523b1786 |  | note | Acceptance Criteria - 175mm concrete strength 20MPa, 3% black oxide, at 28 days
label | 8b3014a7-30e4-5880-bedd-e1d161e84df1 |  | note | Record documents - Concrete Dockets
label | ad1ea6ea-1827-5066-aea2-92be164f8bf7 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .21 - Industrial Vehicle Entrances/Driveways
label | 33f7d1ec-aca4-5fb0-b672-ab1ddcec50c9 |  | note | Detail of Activity - Finish / Joints
label | f4b61302-7914-5b4f-afef-b52fc0afbd71 |  | note | Action - W
label | 04a91a1b-e843-51e1-b8ab-1cf3f0541ed7 |  | note | Minimum Test Frequency - 2
label | 880b7891-d72d-5840-87da-aa6c6a5ba5d0 |  | note | Inspection / Test method - Visual Inspection
label | 0c0f52c5-56ad-509c-b4b1-5d3c57893a52 |  | note | Acceptance Criteria - Smooth, broomed finish. No depressions for ponding to occur. Cut joints as appropriate.
label | 2fb184a1-13f4-5eb5-ae1d-ea21a1ffcd3a |  | note | Record documents - QC Sheets
label | 614149c4-237e-5224-b3ac-577fa5a02e60 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .22 - Concrete Island Infills
label | 96afed2b-c22c-59bc-8b2b-70d51d7ae176 |  | note | Detail of Activity - Base Prep Testing (GAP40)
label | 65f1579b-dd7d-5e48-96ba-9d139a6b5014 |  | note | Action - H
label | c90203b1-fd04-5374-aac4-6c6704531ca9 |  | note | Minimum Test Frequency - Once per 10m
label | 6e44dbc1-0889-53e7-9f53-08a71485f647 |  | note | Inspection / Test method - Clegg Hammer
label | 1a47a7eb-4f60-5209-886b-83ea6f5cf49f |  | note | Acceptance Criteria - CIV ≥ 12
label | bf2ac183-b73e-5e0e-b005-53f1472cd351 |  | note | Record documents - QC Sheets
label | 884e35c3-18bc-599e-aaa1-53a7a8ecc949 |  | note | Responsibility - Contractor
label | 50c20b97-791b-59c4-bb0a-0754caa46fda |  | note | Comments - GAP40 material to be used.
checkpoint-status |  |  | checkpoint | .23 - Concrete Island Infills
label | ae241010-8431-5d42-b9cb-20399055ece4 |  | note | Detail of Activity - Concrete Pours
label | 38af56b7-7986-550a-927d-2ccfc5ec5a08 |  | note | Action - H
label | 6cdfc31a-e5e7-5613-9fc7-5bf0bf8bcde7 |  | note | Minimum Test Frequency - All concrete orders
label | 91e902d7-c8c7-5897-b10a-c4e606e3c90a |  | note | Inspection / Test method - Concrete Dockets
label | 09ce59ec-8350-589a-aed4-f3ebeb286957 |  | note | Acceptance Criteria - 100mm concrete strength 20MPa, coloured "Indian Summer".
label | b5527ff3-0cbf-5650-9641-0f35f89ff8da |  | note | Record documents - Concrete Dockets
label | 680ed385-a755-5f6b-9111-c7ef1d52d819 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .23 - Concrete Island Infills
label | 2cf0313a-97b4-5a42-a745-1bdfd65fd6b5 |  | note | Detail of Activity - Finish / Joints
label | c20d41ed-06ad-5f35-84fe-b3e014e3a244 |  | note | Action - W
label | ef8be291-9d15-59a1-b707-c1811b90c787 |  | note | Inspection / Test method - Visual Inspection
label | 67dc5912-3054-5bb5-8634-08cd31591d4a |  | note | Acceptance Criteria - Smooth, broomed finish. No depressions for ponding to occur. Cut joints as appropriate.
label | 28fb46db-a4a7-5387-abc5-d016f5f43c62 |  | note | Record documents - QC Sheets
label | 41051d6a-82f4-5dc5-9c30-7b0fdd3a1e5d |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | .34 - Collate above documentation
label | 1b35b020-89d0-5d3d-8a63-e7770b9b00db |  | note | Detail of Activity - Document review
label | f50013f5-7e26-533a-91b3-d5d6dd84619b |  | note | Action - H
label | 8c042186-ea6e-5c7f-a722-7609b5eff72d |  | note | Minimum Test Frequency - Each ITP
label | a582139c-b29b-57af-a441-12e65e5aceda |  | note | Inspection / Test method - Review
label | 3d7def3d-9af1-5929-8107-215defcff183 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 7cf27542-56c9-5129-abe4-e5530f76768b |  | note | Record documents - Review
label | 0976ca14-36e4-5e45-aea8-5b611e5352c8 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .35 - As-built drawings
label | 3201b760-eabc-5fae-b581-d18fdf561c1f |  | note | Detail of Activity - Survey
label | 31bdd527-588a-5b04-84bc-6be572f7d09e |  | note | Action - H
label | 14c7c0a9-4063-5cf3-bed7-4adf2532a4a3 |  | note | Minimum Test Frequency - At completion of construction
label | 6367ca51-3f05-5cbf-a148-5bcb1e1b4cce |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | 95e20c7c-1177-531b-bf33-da80bed69f62 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 81f18eb5-afa3-53cb-a2fb-8b4f356433e4 |  | note | Record documents - In Eight record
label | d9cc23c7-9f94-5bb4-bd25-2d70a5be6a9a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | ff9cb0d1-a6f0-5ded-8c6b-27da5e68b596 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 6fe542a5-92c0-5d80-8d25-fe834d994d5b |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 84275209-4543-5e29-95b1-f7f5489cfdca |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 109a825f-9d1d-59ae-9b4d-8f67560f72bb |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Stormwater | itp |  |  |  | Yes | ITP - Stormwater | ef523cf2-7cfb-44bb-b47e-ee74f56151d0
checkpoint-group |  |  | section | 300 - Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 300.1 - Mark out works
label | 88f70b34-1144-5c98-810b-d0dd5cc8a36c |  | note | Detail of Activity - Set out and mark up proposed drainage features by surveyor
label | 1a5bff04-8b3f-5105-a750-616250815e91 |  | note | Action - H
label | 93a17f29-990c-5384-a652-d40ff24ee69d |  | note | Minimum Test Frequency - All drainage features
label | b664c61d-0add-5867-bff9-c0f755a7acc1 |  | note | Inspection / Test method - Visual Inspection
label | 792863ad-3413-58a1-a2d1-8383e99893fa |  | note | Acceptance Criteria - Completed
label | ecb55629-f50a-51f5-9eff-253e0a8f405e |  | note | Record documents - Contractor's site diary
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.2 - Underground services
label | 3f24e591-c19b-5e13-95db-2156a14f6be1 |  | note | Detail of Activity - Identify and positively locate services
label | 41d6845f-02d9-5de4-b0b0-977b87b35e23 |  | note | Action - H
label | 429d2dc0-43bf-541d-9812-7b75a4a95f2e |  | note | Minimum Test Frequency - All drainage features
label | 6cc8f3e9-e22b-5f98-bcdd-aaf9e710a598 |  | note | Inspection / Test method - Hydoexcavation / potholing
label | 53842e8b-4422-56fe-ad14-61daa48f2ee7 |  | note | Acceptance Criteria - Completed
label | 67b2b610-a74f-5684-a1b9-92bd8daa5c73 |  | note | Record documents - Ground Disturbance Permit
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.3 - Precast Concrete Pipes
label | e874887e-2982-5888-8bee-9bb635f507ba |  | note | Detail of Activity - Ensure all precast concrete pipes are Class 2 or Class 4 RCRRJ
label | fd187925-f642-5fbe-92f2-7078eeb120cc |  | note | Action - H
label | 72cc16ac-d630-59e5-8ed4-73049d7cd946 |  | note | Minimum Test Frequency - 1 per culvert size/type
label | b27efbd2-8762-515f-9c49-bd1de0731636 |  | note | Inspection / Test method - Supplier Docket
label | 1549bb42-fd9d-56d6-aff7-d679dea2f2b8 |  | note | Acceptance Criteria - Completed
label | 8daf4ad5-4a5d-57a5-8999-dfadbb183c8a |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.4 - Precast headwall/wingwall units
label | 006f792f-bc5f-5e01-b9b9-4caaa1082a4f |  | note | Detail of Activity - Ensure headwalls and wing walls are precast units
label | fbef72a2-b61f-5664-8438-b9a9d0de5682 |  | note | Action - H
label | 79eab5be-6ecf-53c6-af9c-209008a05e4b |  | note | Minimum Test Frequency - 1 per wingwall type
label | 52b2f07f-0f1d-5f97-9619-dfda8e2d4f91 |  | note | Inspection / Test method - Supplier Docket
label | 6375c19f-80a9-5cee-9ba4-5bfabcfa9be2 |  | note | Acceptance Criteria - Completed
label | c66df634-36e9-5eae-af7f-656dd3438e05 |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.5 - Precast manholes
label | d54b7681-5d29-559a-8f1f-6ec2b911baf8 |  | note | Detail of Activity - Ensure all stormwater manholes are precast and have hinged lids if in carrageway
label | 1aba234e-85fe-5814-9583-a09737f48876 |  | note | Action - H
label | 9d905ce8-0143-56d7-9ac8-c2eed128ae20 |  | note | Minimum Test Frequency - 1 per manhole size/type
label | 14ee4267-b946-54ce-a40c-717b0aa8be7c |  | note | Inspection / Test method - Supplier Docket
label | de4cc9c2-cf30-5877-be7d-f6ba2b83e1f1 |  | note | Acceptance Criteria - Completed
label | 784b8d9d-e0da-5525-a480-f877b0043401 |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.6 - PVC Pipes
label | 724add80-cc2b-57c8-9681-d6f8cddeefcc |  | note | Detail of Activity - Ensure all stormwater pipes with int dia. Smaller than 380mm are PVC-U SN16 to AS/NZS 1260
label | deab4497-9c33-5d75-8b94-915763b0271c |  | note | Action - H
label | 2ba7ff59-c423-5161-bde0-62b9f02fedfd |  | note | Minimum Test Frequency - 1 per culvert size/type
label | 60c55a2b-25ad-56a6-a60a-f86fa3ac4fdf |  | note | Inspection / Test method - Supplier Docket
label | 31406b82-99f1-5b2b-9f1f-1e369ad2f50d |  | note | Acceptance Criteria - Completed
label | 76fcb39e-ac58-54bd-904e-9755c4193776 |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.7 - Precast catchpit
label | a3be36cc-6484-5027-b0b7-5fbe5a8ec7d1 |  | note | Detail of Activity - Ensure all catchpits are pre cast and class D rating.
label | 346d5656-4e8f-5e0b-9ac6-d3d95a2f2efb |  | note | Action - H
label | 151def1e-b814-5b63-b2ea-5ab573903a61 |  | note | Minimum Test Frequency - 1 per catchpit size/type
label | 2d0d6dbb-4516-5ffc-a376-2dfbf020f4c2 |  | note | Inspection / Test method - Supplier Docket
label | d0bd4ad9-529a-5572-836c-d62d9db2fc42 |  | note | Acceptance Criteria - Completed
label | e704d776-afbe-5549-805d-a8a41286bf5f |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.8 - Drainlayer Qualification
label | 827bbe8c-3b6e-5d91-8e89-53cba1dbb4ce |  | note | Detail of Activity - Drainlayer to be appropriately registered and skilled to undertake the work.
label | 730fb8fa-6e09-582e-975e-df0b327e5706 |  | note | Action - H
label | bf3e8c36-3ff5-5f59-9e50-286da5d91ecf |  | note | Minimum Test Frequency - Once at start of the project
label | 9b1ff3ca-3b30-5316-a1a8-ffdbdb1461a7 |  | note | Inspection / Test method - Drainlayer Cert
label | 44322fff-5179-517a-8dd0-72ac50b11e45 |  | note | Acceptance Criteria - Current certificate
label | 49e8d0f4-02c5-5634-beb4-7adde2cdf941 |  | note | Record documents - Drainlayer Cert
label | c3cbc47c-dfb7-5f03-995e-b981b34cbfbb |  | note | Comments - Ensure the supplier has a current drainlaying certificate prior to starting works
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction and Finishing - Pipes
checkpoint-status |  |  | checkpoint | 300.9 - Determine Subgrade Strength
label | 21e62a35-8603-568e-bde4-3626ce925550 |  | note | Detail of Activity - Determine bearing strength of subgrade
label | 0ff97b87-71db-5289-b96a-a7826453d39f |  | note | Action - H
label | 3764217c-14a0-5ad3-8fd4-90c5c0d267e4 |  | note | Minimum Test Frequency - 1 per 6m length of trench base; or 1 per drainage structure
label | 95f7dd7d-7eff-5fb9-b5e5-c5ee2fbe88f3 |  | note | Inspection / Test method - Scala Penetrometer (NZS 4402.6.5.2).
label | dc0d3887-d8ec-5472-a772-d56ef01bc163 |  | note | Acceptance Criteria - Scala to 300mm depth:
label | fcf8a48d-3140-51a1-b61f-de5ebdf9e2bf |  | note | - 3 blows per 100mm = no undercut
label | 7c3e02ea-8587-52fe-beff-85278dadbc4a |  | note | - 2 blows per 100mm = undercut 200mm and replace with GAP40 hardfill
label | 4b637749-225d-5b34-b3f1-b9c4ccb962fe |  | note | - 1 blow per 100mm = undercut 300mm and replace with GAP40 hardfill
label | 5138f154-5198-58dc-b401-f227c336ddc3 |  | note | - <1 blow per 100mm = undercut 450mm and replace with GAP40 hardfill
label | c9c3df5a-226e-5042-b965-bdd7d859f67a |  | note | Undercut to be lined with Bidum A29 or similar approved.
label | b019aee6-2a73-5afb-b026-4c81e1632be5 |  | note | Record documents - QC sheet
label | 4a94b457-1e9a-5f27-abdf-98a45b1f3c65 |  | note | Comments - Note: this supersedes 18.3.6 in specification
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.1 - Pipe bedding
label | 6be56150-fa41-5658-9cb7-ec0a4e21dae5 |  | note | Detail of Activity - Bedding
label | c09cbcdf-dd89-55f0-bbea-69e4e5b8ad96 |  | note | Action - M
label | 78cbc979-34b4-5918-bc3c-5b0aeddbc3d0 |  | note | Minimum Test Frequency - 1 per 6m trench
label | 48d26c33-b15d-5871-81bb-73b0c133e366 |  | note | Inspection / Test method - NZS 3725:2007
label | 5fa5db33-2cd6-5a4d-92e2-805befbe9e66 |  | note | Acceptance Criteria - In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | b0aa0258-0d9c-5058-b6be-81fda2b7aa8d |  | note | Record documents - QC sheet
label | 595c83df-32c0-5425-a157-90d387917cce |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.11 - Pipe installation
label | b9a4fcec-31cf-540c-8bde-e308ddd8943c |  | note | Detail of Activity - Installation tolerance
label | 6e5f94ce-0ef1-5d1e-b6bf-f1339e84ee54 |  | note | Action - M
label | 4b37075e-eeed-5190-b54e-7a6623afa3c8 |  | note | Minimum Test Frequency - Each SW line
label | e7dbea3d-c366-55d0-9d59-3abc03ddf410 |  | note | Inspection / Test method - As Builts
label | e2514f1a-bb8b-54b8-9780-5da3e6c03a69 |  | note | Acceptance Criteria - ±10mm of invert level and ±50mm of Horizontal Alignment
label | 0e842997-0d90-594c-acf6-63b7e4738183 |  | note | Record documents - As Built survey
label | cde2df4c-db88-53ba-93cd-db25a0127d88 |  | note | Comments - There needs to be a rule developed with min and max grades to allow working around existing services. (Stage 1 was min 0.5%, max 10%)
checkpoint-status |  |  | checkpoint | 300.12 - Pipe haunching
label | 2945c7bf-fc32-51ae-be4a-94ec70ebf10e |  | note | Detail of Activity - Haunching
label | aedc18f5-273a-5de9-88e3-53b948bedf0f |  | note | Action - M
label | 8bd15e4b-bfd9-5ba0-b703-29d055c50f18 |  | note | Minimum Test Frequency - 1 per 6m trench
label | 1020e807-57a3-51d3-83e5-8a9a4048bc6c |  | note | Inspection / Test method - NZS 3725:2007
label | 4bd56b4e-ca97-58d5-ab32-4b0e47c38fe9 |  | note | Acceptance Criteria - In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching ≥ 15
label | 2516054b-1b5b-535d-80d7-0d46366d12ef |  | note | Record documents - QC sheet
label | 20da5508-ce89-5984-8b4c-696b5d7daaf3 |  | note | Comments - GAP 40 hardfill to be used
checkpoint-status |  |  | checkpoint | 300.13 - Trench backfill
label | e0a29964-76c6-529c-a484-534027ebdcb9 |  | note | Detail of Activity - Backfilling in berm
label | 8fad556f-ce5a-5550-9ef2-c01b2acf3859 |  | note | Action - M
label | 6abc67b6-4ef4-5f1e-9785-cee7d2d55d2f |  | note | Minimum Test Frequency - 1 per 6m trench
label | 249cd8be-6936-5b2a-ae90-1efae2ac268a |  | note | Inspection / Test method - Clegg Hammer
label | bc4e3b81-7b4e-54d0-a98c-871908967ef4 |  | note | Acceptance Criteria - Top of trench in berm. CIV ≥ 15.
label | a102512b-4e70-5936-8087-bd4b6b24a26b |  | note | Record documents - QC sheet
label | 7af6e72c-dfd3-55f8-84c2-cfec902074d2 |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.14 - Pavement Layer Construction if in road.
label | e23626e8-04f9-5026-b09c-68aa295403da |  | note | Detail of Activity - Subbase
label | abc01643-9ba1-5382-af62-29208f664325 |  | note | Action - M
label | 4b8bac94-03ef-57ca-852b-df407c852aef |  | note | Minimum Test Frequency - 1 per 6m trench
label | ac19a542-e14f-51df-82a2-4ee7cc8c129a |  | note | Inspection / Test method - Clegg Hammer
label | e36476db-4a0e-5eb2-97af-dd3f4d9c4f6a |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 20.
label | cd2b38ed-5bc8-559d-8e64-a7d82d7f79fe |  | note | Record documents - QC sheet
label | bdf237f8-6a1e-59c5-90d2-a7ee5a669d56 |  | note | Comments - GAP 65 to be used
checkpoint-status |  |  | checkpoint | 300.14 - Pavement Layer Construction if in road
label | 9192d116-d610-5910-9907-e37c9de76eb9 |  | note | Detail of Activity - Basecourse
label | 25a5e423-f048-5b0d-8aa6-1d35d80dcc3e |  | note | Action - M
label | e122fe04-bc31-516a-80bb-f302e2d0db66 |  | note | Minimum Test Frequency - 1 per 6m trench
label | 5bf165c4-5709-5653-8398-cdfe143a75ec |  | note | Inspection / Test method - Clegg Hammer
label | 74dd4d0d-0723-50ea-8cdb-bb5adb64751e |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 35.
label | 4b2fd817-0b07-51e3-b697-11ce3ff96ec1 |  | note | Record documents - QC sheet
label | e7bed752-f7f2-57e4-be17-1eb724e4c1fe |  | note | Comments - AP 40 to be used
checkpoint-status |  |  | checkpoint | 300.15 - CCTV Inspection
label | b9d5f6d4-5afe-5c84-9c75-be1bd15ffb84 |  | note | Detail of Activity - Visual record of Existing works
label | 771d0134-d237-583d-87cd-86e05dacfd05 |  | note | Action - W
label | 0f1c0f87-9b5c-530f-b202-199f4f9a1c5d |  | note | Minimum Test Frequency - All drainage pipelines
label | e5844215-ee7c-5c2b-b4d0-6575839c1a29 |  | note | Inspection / Test method - CCTV Inspection
label | 06914a51-2615-5bc2-a487-109397b6aa84 |  | note | Acceptance Criteria - No significant cracks, level deformation, faulty joints
label | 18caad08-c21a-539c-8b61-b6b267bbe76a |  | note | Record documents - CCTV Footage
label | f2b14d79-144b-5312-bda8-150f8fedc9c5 |  | note | Comments - CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practical Completion
checkpoint-group |  |  | section | Construction and Finishing - Structures (manholes, head walls, catchpits etc.)
checkpoint-status |  |  | checkpoint | 300.16 - Determine Subgrade Strength
label | 7683217d-9a44-5b64-9a65-e35794a32cac |  | note | Detail of Activity - Determine bearing strength of subgrade
label | a11bd312-fb05-5542-8310-967e9857ce65 |  | note | Action - H
label | d71ed650-7b5a-5630-9b99-6a9b480c1ba8 |  | note | Minimum Test Frequency - 1 per structure
label | 4c9fc981-a103-537c-9472-87314ec05f4d |  | note | Inspection / Test method - Scala Penetrometer (NZS 4402.6.5.2).
label | 81658df7-d459-51e4-a9d0-585ac47c47d0 |  | note | Acceptance Criteria - Scala to 300mm depth:
label | af150453-cf6e-5448-9886-7ce87d839d9e |  | note | - 3 blows per 100mm = no undercut
label | 8a9d907a-c73b-522c-be08-0aae3fd1b983 |  | note | - 2 blows per 100mm = undercut 200mm and replace with GAP40 hardfill
label | 266e875d-ec4d-508f-884e-78ef632920ca |  | note | - 1 blow per 100mm = undercut 300mm and replace with GAP40 hardfill
label | d338f3f0-5ecc-5559-810e-e08a2760335a |  | note | - <1 blow per 100mm = undercut 450mm and replace with GAP40 hardfill
label | e6d83e53-bf79-525f-aee1-8f92520856a9 |  | note | Undercut to be lined with Bidum A29 or similar approved.
label | 2cb05704-910a-5974-8301-d5417b685ae7 |  | note | Record documents - QC sheet
label | 5fbc24f1-387b-5884-bd84-d5cf1bb4b4f0 |  | note | Comments - Note: this supersedes 18.4.2 in specification
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.17 - Structures (manholes, head walls, catchpits etc.)
label | 0a395c56-b416-526a-9cbb-e6e513dad176 |  | note | Detail of Activity - Visual inspection of concrete components
label | 57e3a55e-4716-504a-b7a4-fa85ab4e2803 |  | note | Action - W
label | b450388a-3250-56d4-a126-c294bca9ddc6 |  | note | Minimum Test Frequency - 1 per structure
label | 5a0f2836-2024-5c1b-a1d4-5eecbb1b81a5 |  | note | Inspection / Test method - Visual Inspection
label | 3dbfa385-e781-5079-b1fa-3f13447aea78 |  | note | Acceptance Criteria - No visible damage, especially around collars and joints
label | bc3d7e92-ac4a-5ecf-9863-c383db3632ea |  | note | Record documents - QC Sheet
checkpoint-status |  |  | checkpoint | 300.19 - Structures (manholes, head walls, catchpits etc.)
label | 4af9c0b1-3429-565b-9a8b-2d78c54e179c |  | note | Detail of Activity - Bedding
label | 7d77c28a-e94b-5824-b196-7f747d0db3f2 |  | note | Action - M
label | 085aa586-9dbc-5a81-83ad-ebded7033e58 |  | note | Minimum Test Frequency - 1 per structure
label | d7d52274-2590-561f-a7c4-b970f62823d7 |  | note | Inspection / Test method - NZS 3725:2007
label | 66d5c860-3bbe-5919-baae-ec70b7483a2f |  | note | Acceptance Criteria - In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 63f4b123-74fb-595b-a3ae-20f73e36f6dd |  | note | Record documents - QC sheet
label | 6228c143-d103-594f-bcd3-5c69ff4252e3 |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.2 - Structures (manholes, head walls, catchpits etc.)
label | 0496b91e-7880-5019-a760-c520c6a26b5c |  | note | Detail of Activity - Backfilling in berm
label | f7b77d14-65b4-55d9-bd3d-a702d7ae2266 |  | note | Action - M
label | ade208e1-abcd-57a1-93d1-1f81513ec8e7 |  | note | Minimum Test Frequency - 1 per structure
label | 20ccda2f-bf9b-5037-8b4c-0a6871590a86 |  | note | Inspection / Test method - Clegg Hammer
label | 420bf99e-86a2-55c8-859b-c131bec57d08 |  | note | Acceptance Criteria - Top of trench in berm. CIV ≥ 15.
label | 0c5c2f8b-ce4d-587a-92e6-afaf4857386a |  | note | Record documents - QC sheet
label | 727b0cb6-6458-59de-93ad-8c4193a949b3 |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.21 - Structures (manholes, head walls, catchpits etc.) Pavement Layer Construction if in road.
label | 210f74b4-8a5c-58ab-8adb-bf539f5b1e0d |  | note | Detail of Activity - Subbase
label | 7adbe8db-2432-5899-9cbc-0ab2384f5396 |  | note | Action - M
label | 3cf828ae-6e4f-5c7b-9800-6f1b94a07653 |  | note | Minimum Test Frequency - 1 per structure
label | c62e2fc4-c3a3-5f02-ac32-d89233d848eb |  | note | Inspection / Test method - Clegg Hammer
label | a9eb44f7-26a1-5be2-9bff-e1ba60938ff3 |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 20.
label | 8cd543d8-22b3-5e36-b8dc-8a12fb039560 |  | note | Record documents - QC sheet
label | abaa892f-17d4-5a7f-b520-a7a60eed67df |  | note | Comments - GAP 65 to be used
checkpoint-status |  |  | checkpoint | 300.21 - Structures (manholes, head walls, catchpits etc.) Pavement Layer Construction if in road
label | e8a25cfc-566b-57e1-be91-547c5adbc969 |  | note | Detail of Activity - Basecourse
label | 6c056e27-f909-5c54-af95-d99c48fce009 |  | note | Action - M
label | e187959e-c613-5122-abc5-c76cabdbb410 |  | note | Minimum Test Frequency - 1 per structure
label | 6ec2708e-be65-513d-b923-479e5fd27fcb |  | note | Inspection / Test method - Clegg Hammer
label | 0c8a74ec-4f02-5856-9ed6-5bbe05f10555 |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 35.
label | 69e97259-b782-5b5e-9c79-fe326b0830fa |  | note | Record documents - QC sheet
label | ef162a32-d651-514a-a9d9-0b3e14166be5 |  | note | Comments - AP 40 to be used
checkpoint-status |  |  | checkpoint | 300.22 - Structures (manholes, head walls, catchpits etc.)
label | 60af820c-852a-5acf-8461-96ba79b049d9 |  | note | Detail of Activity - Installation tolerance
label | 3cf1ac13-4638-5b6d-b21b-5a1f40519806 |  | note | Action - M
label | 18885689-658d-5577-8839-79e5b86c7942 |  | note | Minimum Test Frequency - 1 per structure
label | 2519f021-0f1c-520a-983d-112b9359cbc7 |  | note | Inspection / Test method - As Builts
label | fd2d5178-162d-552e-b6ef-e3e8c020960c |  | note | Acceptance Criteria - All MH lids and grates to be flush with the surrounding finished ground level.
label | fffdc858-84e6-50f7-8427-523b091fab04 |  | note | Tolerances: ±Half a pipe length longitudinally and ±150mm laterally.
label | df0c03c1-7260-55c6-b6e2-f1144674f26e |  | note | Record documents - QC sheet
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 300.23 - Collate above documentation
label | 019b0429-c7ee-5e91-91b4-3139064811b8 |  | note | Detail of Activity - Document review
label | 585929dd-d5d0-5d99-b1d9-0c361042b01d |  | note | Action - H
label | 38faefd3-198d-510e-b006-2fd3513242b1 |  | note | Minimum Test Frequency - Each ITP
label | 2728af98-5d30-5392-a01c-d5f80190e5e4 |  | note | Inspection / Test method - Review
label | 5e5fedf4-e95f-55c5-8bc5-f01c4d2c4ff4 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | e59302e7-c569-59dd-8759-7c6a92ecb837 |  | note | Record documents - Review
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.24 - As-built drawings
label | 90d42a18-3fd3-597b-b219-1a0f6bc3ba49 |  | note | Detail of Activity - Survey
label | c9303ebd-cb87-57a6-af53-8b73009acb51 |  | note | Action - H
label | 67647060-391d-5850-9795-6449ef2db7c0 |  | note | Minimum Test Frequency - At completion of construction
label | 10b312c5-e1d2-5f09-9451-2c03522ea4cd |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | 4ef7d12e-f846-5789-bb07-569e03de6fe0 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 0bf1cb7d-3d0d-584f-a0b3-3572a6145ad4 |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | e05be1e4-0c07-5896-b15a-f263dae8a94d |  | textbox | Contractor's Rep Name:
text | cdf70162-ee8e-5a48-9670-0f5991060812 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Type A Pavement |  |  |  |  | Yes | ITP - Type A Pavement | fb34c0f5-281f-4e52-be05-c8346d70ed7a
checkpoint-group |  |  | section | Pre-construction / Preliminary Compliance Requirements
checkpoint-status |  |  | checkpoint | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | c2726a76-e489-5811-81fa-6381c667d214 |  | note | H
label | 6c202b21-7a90-52db-8a6a-946fe8f21b1d |  | note | Minimum Test Frequency - Prior to Construction
label | 25e50b94-4d23-5319-9599-c9c3bfd9612b |  | note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | 8617fcb5-0bae-535b-b506-0eabe7c113d2 |  | note | Responsibility - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.2 - Drawings and Specification
label | f37ad9ba-6446-551a-ab01-1daa780a9804 |  | note | H
label | c686c92a-bfd6-5604-9872-127e10c6becb |  | note | Minimum Test Frequency - Prior to Construction
label | 6c05991c-54d1-5bbe-a717-127427f58f19 |  | note | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | 65e82b76-7aca-5f81-a594-4604fa170302 |  | note | Responsibility - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.3 - Set out
label | ce150c01-94aa-5bb7-ac6c-cde88c704970 |  | note | H
label | b7438cf7-075c-5e71-82e9-3c19913a4efb |  | note | Minimum Test Frequency - Prior to Construction
label | a2d18603-e8c3-5c82-9e00-17f37fe86f31 |  | note | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | bd8f68ea-49af-5467-a793-d271e24782e6 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.4 - Material Approvals
label | a3f8087d-91fb-5f8a-b7fc-084e39b06ea3 |  | note | Detail of Activity - Submit testing data fir the following materials: - AP65 -GAP 40 -GAP 20 -Hardfill
label | 7f808833-a3a8-5ca3-a200-0e5f94cc8aff |  | note | H
label | 0c35a99c-aa92-5477-9bf9-acc1b04e4818 |  | note | Minimum Test Frequency - Prior to Construction
label | 20a08ccd-dd0f-5984-967f-272e24990df8 |  | note | Inspection / Test method - Quarry Testing Data
label | 90da3ed3-3128-5afb-aa86-e3f0f590183a |  | note | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | 9b9746ed-52f6-50c0-b532-4ad76f46b2a2 |  | note | • Recycled Pavement/Subgrade Improvement Material:
label | e547f80c-bad3-5eb2-a5d1-38a2bc1a55dd |  | note | • AP40:
label | bff3b4cc-b4ed-50f1-99ed-7b14f39b3c06 |  | note | ○ CBR >20%
label | f2c0725f-acc1-5de0-8573-54bcd3885ae8 |  | note | ○ Sand Equivalent > 20
label | bf956759-a273-5053-8784-e9964e4e1a68 |  | note | ○ Grading < 35% passing 75um sieve
label | 4b6ebc20-7c54-5a24-b848-3b0ab0e47ac5 |  | note | • AP65:
label | 546e6e42-3415-5afc-97b0-5fd7463adf77 |  | note | ○ Crushing Resistance < 100kN
label | 49824382-d39f-5502-a082-9b8b4b2a79cc |  | note | ○ Weathering Quality Index of A,AB, AC, BA, BB or CA
label | 6622a025-494f-582c-b095-badf1cadd856 |  | note | ○ Sand Equivalent ≥ 25 if > 4% passing 75um sieve
label | 51fa911d-1487-5896-8e38-96ae370ab4ac |  | note | ○ CBR minimum 40 using heavy compaction
label | 3db17ce3-8792-53c5-bfaa-4f238093e599 |  | note | ○ Grading
label | f3368bd7-d9da-53e6-a048-900cfb94c807 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.5 - Materials Approvals
label | 225acce5-118d-5209-a0c1-b1fb0eeeb344 |  | note | H
label | e45761f1-d936-5fa6-b1e8-17635bfd850b |  | note | Minimum Test Frequency - Prior To Construction
label | 23e3e9c0-9326-584e-a770-f2c141f1e6c0 |  | note | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
label | 56e02775-1973-5fb7-b50d-6b24b7dd0b94 |  | note | Record documents - InEight Records
label | e238120d-130b-58cb-b651-e07c89493f62 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 600.6 - Existing Pavement Assessment
label | 32e55853-8c6d-502b-81d1-fa626f6d489a |  | note | Detail of Activity - Confirm Pavement Depth
label | 57f68769-26f7-5a02-8ceb-583beeae8919 |  | note | H
label | a08cf6ba-569f-5e20-8e94-7e43a38848fa |  | note | Minimum Test Frequency - 50m centres
label | 1bdc1645-7fff-58d0-af89-8c5be4f89fb1 |  | note | Inspection / Test method - Test Pits / Visual Inspection
label | d6bec85d-2fcc-5585-9033-d677cdd1aebd |  | note | Acceptance Criteria - Mill 200mm. Dig/core test pits to confirm if existing pavement:
label | d809f270-cb9d-5cfe-9c0e-6be57a18a358 |  | note | – If existing underlying pavement is of sufficient depth (i.e. ≥250mm below mill surface/≥450mm below finished level), continue with "Existing Pavement" steps below (light green rows).
label | 3eaa8688-ada0-5c2a-bf33-f40b9e080234 |  | note | – If insufficient depth or poor quality, advise WSP Engineer, mill/excavate to 450mm from FL, and complete "Full New Pavement" requirements below (light blue rows for Recycled or Mixed Materials, light yellow rows for Engineered Material only - i.e. AP65,).
label | 11e68513-9e6f-5777-8ea6-ddcac301e572 |  | note | Record documents - QC Sheets
label | e0601623-140e-5939-80ab-279f6227713f |  | note | Responsibility - Contractor
label | c95065cb-d769-5b23-b5f9-bec7d038e5b8 |  | note | Comments - Existing pavement to measure 450mm from finished level (minimum). If not "Full New Pavement" requirements are to be followed.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.7 - Existing Pavement Assessment
label | 289549a8-f1fb-504b-9592-fc4919cc3eda |  | note | Detail of Activity - Beam Test
label | e3b6a946-c346-5417-92e1-9368603627c2 |  | note | H
label | dd53caed-8696-5481-80fc-e7f9a4559e6d |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | 2a6762fd-d9fa-534e-b545-19445d1366a1 |  | note | Inspection / Test method - Beam Testing
label | e74cd12e-8316-5c58-aa44-ca8bea169a01 |  | note | Acceptance Criteria - Review beam test results to determine if undercuts are required.
label | 889d8e53-f553-5588-8fb5-2f6daba79bd2 |  | note | <1mm:
label | 0b858ec3-f509-571e-b54d-df42b48ab118 |  | note | – No Undercut
label | b437824e-e2cb-5c07-9a81-78ebb195b4a5 |  | note | 1 - 2.5mm Beam Deflection:
label | 39aca4ef-dec8-5562-9e1f-66da60b5bf99 |  | note | – Undercut 50mm
label | 4c2c4247-e0c3-5fef-9da8-875bc11697c0 |  | note | – Backfill with 20/40 drainage aggregate
label | fcd76ec6-6277-5c2a-a837-61a71132ab7f |  | note | 2.5 - 5mm Beam Deflection:
label | 51b14359-f0b1-56b8-a61b-8b78da2ab05a |  | note | – Undercut 100mm
label | 493d7011-6072-520e-8e72-caa0e189d582 |  | note | – Backfill with AP65
label | 47d09477-1a47-50fc-8779-01a0ee52b386 |  | note | 5+ mm Beam Deflection:
label | 96a3e932-b7dd-5313-bc01-41ba23692d67 |  | note | – Undercut 200mm
label | 1f4c2c03-3045-59d4-827f-f546086dd813 |  | note | – Backfill with AP65
label | c7e88eb9-4389-58da-95d7-06571d12563e |  | note | Record documents - QC Sheets / Lab Result Sheet
label | d07d8783-dbed-5fb1-b11d-94bdfc0d14c2 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.8 - Existing Pavement Assessment
label | 7b1467ff-cfd8-5a19-83c5-961205c104f4 |  | note | Detail of Activity - Milled Surface Stringlines
label | aee57e4a-91bb-5194-8808-842c19b9280a |  | note | M
label | 11fa1042-4a97-5f74-9227-ceae6349ccac |  | note | Minimum Test Frequency - 20m centres
label | f5f1fb85-49de-50c7-8392-58ae5d619db6 |  | note | Inspection / Test method - Visual Inspection
label | 5b772d74-24b0-5b8b-b8bf-87d66d02fb48 |  | note | Acceptance Criteria - Finished Level – String Line, +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | a992b9c9-59c5-57fe-bd75-21cc186efff9 |  | note | Record documents - QC Sheets (String Sheet)
label | c66754fb-9ea8-5948-b1a7-d902f8dbc809 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.9 - Existing Pavement - Subbase Stabilising (During Construction)
label | f459813d-fc8d-5ffc-a511-641c34d8e947 |  | note | Detail of Activity - Mat Samples (1m2 canvas)
label | b7701ea5-dd55-57a7-9b17-dbd723324107 |  | note | W
label | 900f9d82-5b6c-50d3-9a8b-57e548eddda5 |  | note | Minimum Test Frequency - 1 mat weighed every 400m2
label | fb5accd6-2f9b-5bbd-be05-9e90616bedb2 |  | note | Inspection / Test method - Mat Samples
label | d1106c0f-a56e-5226-a978-d44d4f4a2ed6 |  | note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | 5762c107-f5c4-5946-ac64-4581529c4e92 |  | note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | 8bf79774-6e6d-59db-b781-a042e5c06d47 |  | note | Record documents - QC Sheets
label | 34e4b454-ce41-505b-84f7-15cda6c90968 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.10 - Existing Pavement - Subbase Stabilising (During Construction)
label | 8bd3ba31-0e39-5953-9bbd-8d83c5eb13d6 |  | note | Detail of Activity - Plateau Density Test
label | ff5bb237-0dec-5443-88d9-8162ab8169d4 |  | note | W
label | 2cc2fab2-f3bf-505f-b29b-c2fcbd3d0bb1 |  | note | Minimum Test Frequency - 1 Plateau Density Test per lot
label | 44ff7ec6-7ffd-555d-9904-94480ec6fd4a |  | note | Inspection / Test method - NDM
label | a3362cdf-d355-5947-95e7-db51794201ae |  | note | Acceptance Criteria - Determine minimum number of roller passes required to reach peak compaction strength using both primary compaction and finishing compaction rollers.
label | 4a147b44-d354-5969-be85-dd8f9f41451b |  | note | Record documents - QC Sheets
label | 9d6bd9e9-803a-5a0f-b8a9-0936e278ae27 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.11 - Existing Pavement - Subbase Stabilising (During Construction)
label | e1e354af-ae20-568f-a985-d25b4c21eb31 |  | note | Detail of Activity - Stabilisation Depth
label | 836186d0-5f48-548f-bbe0-f21c78828962 |  | note | M
label | 2c9b6581-d832-5fdb-8c64-47ad63e682d5 |  | note | Minimum Test Frequency - Once per lot
label | e97a753e-2c43-5100-9b57-f5ecc93394be |  | note | Inspection / Test method - Visual Inspection (with tape measure)
label | 3a5f0161-073a-5e64-8819-63fca98ce742 |  | note | Acceptance Criteria - Stabilised to 200mm depth.
label | edf774f4-75cf-5bc6-813e-5b41808c171b |  | note | Record documents - QC Sheets (Photos)
label | 0d9b713d-c5d6-56af-836d-a3d606bea253 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.12 - Existing Pavement - Subbase Stabilising (Post Construction)
label | f389d0f1-7737-5d9f-969c-145e7604119a |  | note | Detail of Activity - Beam Test
label | e18dda01-84bc-5132-9a28-d0e568232ec0 |  | note | H
label | f6edc709-649a-5c2f-871e-bc08ef292cb9 |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | f94406e2-0275-510d-a4d3-3f73c42b1c81 |  | note | Inspection / Test method - Benkleman Beam
label | 69eeadb5-2e10-5a90-808a-b0f2783f2450 |  | note | Acceptance Criteria - ≤ 2mm deflection
label | ab50706e-57ca-5e98-9513-3d5fa9db1a33 |  | note | Record documents - IANZ Accredited Lab Results
label | 346b2b5c-e89e-5dfd-8a69-51586d143315 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.13 - Existing Pavement - Subbase Stabilising (Post Construction)
label | 0f7ad1b3-d6e9-5d9c-8a75-e4aa333bc9d4 |  | note | Detail of Activity - Stabilised Depth
label | 73934d22-325f-5f82-8079-39ffa94a55a5 |  | note | M
label | a9dde6a0-8365-54e1-a77a-cce8483e65dc |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 56d89fd2-df8e-5404-8266-40d7144e7fda |  | note | Inspection / Test method - Core Visual Inspection
label | 8580a489-7892-5280-ae5e-44a1f55d5b47 |  | note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | cb538501-5718-58d7-a8b4-3cdd9504dd24 |  | note | • Grading of aggregate (i.e. good mix of different stone sizes)
label | 196fe2b3-142a-5b2f-ab3c-daa7cd2e33de |  | note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | 019f6a44-f75a-523f-9c18-bd0c20eee380 |  | note | Record documents - QC Sheets (Photos / Coring Report)
label | a3cd9b6f-f815-5eb9-a174-b0731d516d07 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.14 - Existing Pavement - Subbase Stabilising (Post Construction)
label | f97701ac-ed81-5c3b-9c4f-20408c4141ea |  | note | Detail of Activity - Stringlines
label | c2139d7b-ecfa-5553-ba5e-a9e9fa75a95f |  | note | H
label | f21b8b3c-ad72-55fc-93cd-fa9eb9578048 |  | note | Minimum Test Frequency - Every 10m
label | 5c3d3c06-de26-54b7-9762-22b7424828d9 |  | note | Inspection / Test method - Visual Inspection
label | 95c95098-9f49-5e30-b27f-a891f17b5e6e |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | 84ea6fa7-5c7c-5a7c-a511-85a396d52c4c |  | note | Tolerance: +10mm/-30mm
label | 944110a5-f9d2-54ef-9010-2d5788bc0b9a |  | note | Record documents - QC Sheets
label | bcc93889-2032-565f-ae66-4d12af9e2278 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.15 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | 2c61409f-c598-5c86-8cb9-0b04384642f9 |  | note | Detail of Activity - Subgrade Levels
label | 811ebe5d-d1d5-5403-bc8e-866fc8fdab6e |  | note | H
label | 37f8140b-8ba7-5b3f-8658-04c847f4137a |  | note | Minimum Test Frequency - 20m centres
label | 44479b73-c4b7-5195-bc06-c9c33b0f0d8f |  | note | Inspection / Test method - Visual Inspection
label | 2fe8c885-245c-50f3-b735-b4666052b2a3 |  | note | Acceptance Criteria - Cut subgrade to 450mm below finished level.
label | 39397a02-ec1e-5174-9099-f3364d57d570 |  | note | • String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | 56686a5b-16b1-52ad-b0a7-bf7d781f3042 |  | note | Record documents - QC Sheets
label | f634e72d-235c-5eaa-938f-ca3f04f46c2c |  | note | Responsibility - Contractor
label | de7eb29a-ccb6-55b9-b4b4-1b63702c6ca2 |  | note | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.16 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | f3b153cd-dd08-5304-8fa1-c84ec2bd427a |  | note | Detail of Activity - Scala Penetrometer
label | c732e24d-de06-52c5-b5a2-8669656ab446 |  | note | H
label | 6f1b8ca1-9c70-5ecb-8fd2-a616ef4a1787 |  | note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | b778f1a3-b74e-5a5c-a9bd-98ab8e455dd3 |  | note | Inspection / Test method - Scala Penetrometer
label | 2b8437fb-8e32-5468-bde6-f940c805ed5b |  | note | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | cd559a83-240f-5eb5-9fbd-4e63aa95509c |  | note | • ≥ 3 blows per 100mm - No Undercut
label | 790cbf47-c766-5041-bba4-a2824c8d1151 |  | note | • 2-3 blows per 100mm - 200mm Undercut
label | 30e223ea-f6b6-597d-affe-2d5e8fdc7650 |  | note | • 1-2 blows per 100mm - 300mm Undercut
label | 365a7431-10ee-518c-9bdd-dbe66890084b |  | note | • <1 blow per 100mm - 450mm Undercut
label | 2addff43-c41e-5ee9-afcb-2ab076c4bf84 |  | note | Record documents - QC Sheets (Scala Sheet)
label | c7284a96-c3f9-5e3f-8969-885c0f8e54d9 |  | note | Responsibility - Contractor
label | 2f92d505-71d6-5cb0-8c37-b7330f226d67 |  | note | Comments - Scala results to meet or exceed per below:
label | 78bd1836-3049-57df-a66b-b3f79e0e93bb |  | note | • 0mm - 100mm - ≥ 3 blows per 100mm
label | 01b55db5-718e-5295-ae6d-b02f24aaece6 |  | note | • 100mm - 200mm - ≥ 2 blows per 100mm
label | e29fd9c8-431f-576a-9b61-7441c30c034a |  | note | • 200mm - 300mm - ≥ 2 blows per 100mm
label | 11545e1b-bb72-592e-bfc8-4fecf81e15df |  | note | • 300mm - 400mm - ≥ 1 blow per 100mm
label | 23f906a3-402c-5d6b-8819-9c0a7f3994b7 |  | note | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.17 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | 65cf9cc1-403c-5f3f-9b66-1f614cedf9a5 |  | note | Detail of Activity - Proof Roll
label | b6f13b49-6648-5e43-97f7-fb8910ab7970 |  | note | H
label | 71d577c1-d684-5fb7-89a7-893ecededdca |  | note | Minimum Test Frequency - One per lot
label | 7e50b913-fcb1-5f62-90fc-ba090d7941ce |  | note | Inspection / Test method - Visual Inspection
label | 712dd514-4a84-5153-9e0c-0a6813bd41d2 |  | note | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut
label | 169ec0c0-9fae-5e77-b5d1-e7bd897fcb9d |  | note | • 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | bdd6dd6d-0187-5f97-a3f5-282abad53282 |  | note | Record documents - QC Sheets/Site records
label | 1cd4b33a-b394-58a4-a5d6-a6064bd2d49d |  | note | Responsibility - Contractor
label | 7c2ef8fc-40d4-54da-beec-6f43e481fb7c |  | note | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.18 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | ce78968c-38c5-5a06-a8d5-a4ad142273c3 |  | note | Detail of Activity - Undercut Measurements
label | 22a204ac-505c-5a41-8804-f79d144f0019 |  | note | M
label | de85dad5-fc5a-59b1-8717-0e65c5eabab6 |  | note | Minimum Test Frequency - Every undercut section
label | 941b4870-1dc1-5ffa-9268-8eadea39fced |  | note | Inspection / Test method - Visual Inspection
label | 85baeb5d-2807-5f32-bfce-59c21ef730e8 |  | note | Acceptance Criteria - Measure and record undercut area and depth
label | 2cd50e0b-bc92-50be-80d8-4d5a03edfade |  | note | Record documents - QC Sheets/Site records
label | 7e79c4ac-2cbd-5f5e-b616-952cbcf9a499 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.19 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | 2d304fd1-1b1c-5e0f-aed3-daf5a89252f5 |  | note | Detail of Activity - Backfill Layers
label | 3f3427f1-b10c-5e4c-a0a8-5098712a6d55 |  | note | M
label | 18d4efb5-ff93-5c1b-b54f-882d8ca4ae6e |  | note | Minimum Test Frequency - Every 20m
label | 910cf240-e588-51a3-9fcd-1bfd93d241f8 |  | note | Inspection / Test method - Visual Inspection
label | 2207d305-b90b-5fe1-a70e-1160615beeaf |  | note | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | e00d99a1-32a1-5c7f-b783-e815e86e92af |  | note | Record documents - QC Sheets
label | 6a7cca46-43d0-59af-8fc2-a1c643958f96 |  | note | Responsibility - Contractor
label | fc049960-3be1-523a-90a5-de9c194005e5 |  | note | Comments - Use recycled pavement (millings), Hardfill or AP65 if available.
label | 7b914c96-9e50-53f4-a19c-866581ab8940 |  | note | • We propose to use proof roll instead of NDM testing because of the variablity of the recycled material and the bitumen content in it making it hard to test. This supersedes clause 22.2.1 in the project Specification.
checkpoint-status |  |  | checkpoint | 600.20 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Layer
label | b2ee98b2-49ae-5b85-8163-cce276883ce0 |  | note | Detail of Activity - Construct Subbase
label | 0bff48b5-1fac-5b2c-8869-2752ad7e87d1 |  | note | M
label | bd9a3d70-9396-53fb-be4d-7fad4ca6ce6d |  | note | Minimum Test Frequency - Per Lot
label | ab338bdd-3822-5c80-8d67-ca542700085e |  | note | Inspection / Test method - Visual Inspection
label | 80567def-9a4a-5382-a039-956b93188964 |  | note | Acceptance Criteria - Construct subbase with 200mm of millings and top up with AP65 if needed. (330mm below TOK)
label | f867ba57-a998-595f-8827-2e657b31f47b |  | note | • Add 50mm of 20-40 drainage material. (280mm below TOK)
label | e4f2af8e-4080-5f24-a062-1c9d968ec9c0 |  | note | • Ensure material is compacted and enough volume to be stabilised.
label | 9300cf89-e5e4-54b1-9494-47d975fe4cc3 |  | note | Record documents - QC Sheets
label | 91cecc92-2ef1-577f-a8f4-375877955ea1 |  | note | Responsibility - Contractor
label | 51edae0b-0da9-5845-afdd-b4959cc21a25 |  | note | Comments - Check each layer with strings
checkpoint-status |  |  | checkpoint | 600.21 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | 291d25db-14fb-5915-bcf7-e6d99bbf1d5d |  | note | Detail of Activity - Mat Samples (1m2 canvas)
label | e5b46503-210f-57d3-bf90-621f46107aa1 |  | note | W
label | aad514bc-6fcb-56a0-a1ae-1559cdd96189 |  | note | Minimum Test Frequency - 1 mat weighed every 400m2
label | 72d4babb-669b-5adb-8a98-c169a4ece187 |  | note | Inspection / Test method - Mat Samples
label | db5f6844-1676-5951-98ea-9f4bb6597da3 |  | note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | 70cb22e4-04a1-56d2-ad60-891d8011c46c |  | note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | 30338469-115d-5ef5-89ee-cd821ee6ea7e |  | note | Record documents - QC Sheets
label | f7ba0100-89ff-5694-b9f0-8642578baf79 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.22 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | 64bd6246-a993-5c9e-8870-bcc425e45fb4 |  | note | Detail of Activity - Plateau Density Test
label | e67ee3ed-4364-5a79-b786-4591a9e60793 |  | note | W
label | 418fb241-5dc3-5c6e-8224-ef9ea6f0d95c |  | note | Minimum Test Frequency - 1 Plateau Density Test per lot
label | ce31d987-98f9-587d-b2f6-9cb46d750f3f |  | note | Inspection / Test method - NDM
label | f10313f8-3356-5419-9a90-169d391dafeb |  | note | Acceptance Criteria - Determine minimum number of roller passes to achieve peak/maximum density using both primary compaction and finishing compaction rollers.
label | e4c02d52-5de4-5746-9f59-32b28a015fb0 |  | note | Record documents - QC Sheets
label | e0170402-87b7-588b-8e66-480a6a9f97f9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.23 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | e98e7922-0f6f-5456-aa5c-243adab143db |  | note | Detail of Activity - Stabilisation Depth
label | f0c391cc-fbc6-5bdf-89cb-a48e55626da8 |  | note | M
label | 588d7e81-6707-500c-a8dc-40de485b8c31 |  | note | Minimum Test Frequency - Once per lot
label | d1b7bd79-862a-5f7c-9dbb-92172bc6a17e |  | note | Inspection / Test method - Visual Inspection (with tape measure)
label | 51256104-74f8-5a14-97ba-68130a09e21e |  | note | Acceptance Criteria - Stabilised to 200mm depth.
label | 7b0b4cfc-38d9-5a08-9b0c-d75a4f3198f9 |  | note | Record documents - QC Sheets (Photos)
label | e31973ed-961b-519c-81d3-6459ed3c509e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.24 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | 36311214-fff9-5e67-af41-ec117e443275 |  | note | Detail of Activity - Beam Test
label | 6f86a5a1-c6ac-58d5-8cab-cabc30d33895 |  | note | H
label | e52f80d0-f01d-5040-9884-88462fb4b6a9 |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | a5c73744-e49e-58bc-8a33-ba4287ec26be |  | note | Inspection / Test method - Benkleman Beam
label | 44ff8de8-8ae8-5509-9a94-64ad459a8071 |  | note | Acceptance Criteria - ≤ 2mm deflection
label | fe2f3a01-ec66-5d3a-86e6-c2059e67f84b |  | note | Record documents - IANZ Accredited Lab Results
label | 887bbf20-1031-5508-8913-254a65cb28d6 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.25 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | 7e221ecc-4dd6-5e22-8ccd-928220b604a9 |  | note | Detail of Activity - Stabilised Depth
label | 1d878bb6-d355-58e4-ac81-27c5d7ab91c7 |  | note | M
label | 8c5ba6cd-d97e-5bb3-b930-658d304765a2 |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 12b79692-bc73-5e27-b7fa-4dd8e3ce2b7d |  | note | Inspection / Test method - Core Visual Inspection
label | bf0a2530-7235-5644-be69-71bd109076dc |  | note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | ec30ebff-bab6-507f-84ce-c14f6bd2f5b7 |  | note | • Grading of aggregate (i.e. good mix of different stone sizes)
label | e701733d-2d0e-5d61-9673-2d70ac53025e |  | note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | 6950abe1-d96b-5509-8d0f-6624479bf325 |  | note | Record documents - QC Sheets (Photos / Coring Report)
label | 777fbde1-7ce1-5a62-bcc6-00e1a915f631 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.26 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | 35e56896-9bd0-5593-9501-99b03a361a73 |  | note | Detail of Activity - Stringlines
label | 219afd89-8058-5741-825b-1860cdf3953b |  | note | H
label | 0ae28c80-8fb7-55e6-b0f3-d28b0d2c67c8 |  | note | Minimum Test Frequency - Every 10m
label | d28376c5-63f1-5880-add7-133dd82745ed |  | note | Inspection / Test method - Visual Inspection
label | 43c58c1a-9030-58c8-8241-aef1c79aaacb |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane. Tolerance: +10mm/-30mm
label | 9406f1ce-fe7a-51ab-b579-96eb00e06704 |  | note | Record documents - QC Sheets
label | 2258bd90-4ae1-5c72-a554-7dac133949b5 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.27 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | 3875069f-ed3f-5819-8333-6ba0ca2a1502 |  | note | Detail of Activity - Subgrade Levels
label | 1a62f0a1-ebea-57c9-8974-1575c99aae09 |  | note | H
label | 368cf98a-256b-564b-9cb9-a967221b2f15 |  | note | Minimum Test Frequency - 20m centres
label | 18b2356e-2a7f-51a0-84f8-1e3a99e950d7 |  | note | Inspection / Test method - Visual Inspection
label | 056154ab-edf3-56fc-89f6-733f1966927a |  | note | Acceptance Criteria - Cut subgrade to 450mm below finished level.
label | 77c4ea6c-efff-5db9-9b62-c1666deebbfc |  | note | • String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | 082b8aae-0fde-5399-b89b-dab6ea4be8ce |  | note | Record documents - QC Sheets
label | 0faf8872-6196-5a8f-bf81-f610e5242401 |  | note | Responsibility - Contractor
label | 92f46203-1399-5e60-be15-355845640df4 |  | note | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.28 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | 2dca50a8-6e32-5f4d-a9da-38282ab7b02b |  | note | Detail of Activity - Scala Penetrometer
label | 930680e5-0465-59f6-8071-6942c13af4ab |  | note | H
label | 7b4ca272-8adf-52e0-adc0-fac0cc9c9722 |  | note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | 5ea7ea4d-8967-5713-b22a-3ddee2eb24bb |  | note | Inspection / Test method - Scala Penetrometer
label | bbc026bb-894a-5765-97db-c8ae7faefa73 |  | note | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | 5e34d0c4-efb0-5781-8f7d-2903640d22ba |  | note | • ≥ 3 blows per 100mm - No Undercut
label | edcbd633-cb75-58b4-a0a1-789fc1edc611 |  | note | • 2-3 blows per 100mm - 200mm Undercut
label | 7f05089e-fed8-5823-81e6-5f63aeccfe0b |  | note | • 1-2 blows per 100mm - 300mm Undercut
label | 93f194ae-cdff-5993-aae5-584db53f0208 |  | note | • <1 blow per 100mm - 450mm Undercut
label | 16114f72-904d-5c31-89c5-df3d77c00dfe |  | note | Record documents - QC Sheets (Scala Sheet)
label | 8c882115-3393-51cd-8aa7-958212c7bc9f |  | note | Responsibility - Contractor
label | a53f33ae-2b7e-5719-b301-ce4da1acdc32 |  | note | Comments - Scala results to meet or exceed per below:
label | ca7edc00-a412-5544-b494-a11db9cdbfc0 |  | note | • 0mm - 100mm - ≥ 3 blows per 100mm
label | dc71d952-df41-5e37-bd5f-aee93b3a2fba |  | note | • 100mm - 200mm - ≥ 2 blows per 100mm
label | 84fdda87-4fea-5623-a914-7fceb5d41f8e |  | note | • 200mm - 300mm - ≥ 2 blows per 100mm
label | 740385c4-6578-5aa2-a26a-e6dc3e5d9064 |  | note | • 300mm - 400mm - ≥ 1 blow per 100mm
label | cc921e6f-d6ca-546b-aba0-bfa0a9d07f71 |  | note | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.29 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | 42bfd64d-a7fd-5e86-90d4-30ed4a3b0f2b |  | note | Detail of Activity - Proof Roll
label | 7768ddc1-4d60-56ca-a62c-950d74d773b4 |  | note | H
label | 4198515f-8fcb-5ebe-a751-4b62f2efb21c |  | note | Minimum Test Frequency - One per lot
label | ef6bebc9-c16b-50e6-9487-3014b60de7e7 |  | note | Inspection / Test method - Visual Inspection
label | 32b0e7d0-ff1c-58de-a15d-3a0cb8420635 |  | note | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | 614d8f76-b10f-5c8d-a6b9-f448d0e30b26 |  | note | Record documents - QC Sheets/Site records
label | 1c21c9f2-0a2b-5c93-8217-cfc2a6185b72 |  | note | Responsibility - Contractor
label | de564291-630a-5e3e-87e1-91e30983e46c |  | note | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.30 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | 4a1fd2e3-b1bc-5495-92b3-6c645f8640eb |  | note | Detail of Activity - Undercut Measurements
label | 6f080aad-5d83-5324-9dc1-47d69b639a58 |  | note | M
label | 640d23bd-f820-59f3-9954-923484b1fa06 |  | note | Minimum Test Frequency - Every undercut section
label | 5ef390cb-0e77-519d-9776-08c08854c19e |  | note | Inspection / Test method - Visual Inspection
label | c3443b16-9176-5def-9f71-be027a0ac8b1 |  | note | Acceptance Criteria - Measure and record undercut area and depth
label | 3f8c352e-40b6-5e22-a42d-5069af79e9f8 |  | note | Record documents - QC Sheets/Site records
label | f14ffdb0-ac52-569b-9559-00ba8554d54d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.31 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | d15377fa-c605-5152-8155-0e59095768f8 |  | note | Detail of Activity - Backfill Layers
label | 465f1a02-7a56-5dd0-b457-7b08630296b1 |  | note | M
label | 744072f1-14d4-5f15-a2b6-4eb39b4f6568 |  | note | Minimum Test Frequency - Every 20m
label | 19f4f0bf-f6b4-534a-9720-96a86c9597d9 |  | note | Inspection / Test method - Visual Inspection
label | d0688353-5ab0-5ac8-9891-cb0941c2962f |  | note | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | d0fa40a8-8c96-519f-bc88-154a495a9518 |  | note | Record documents - QC Sheets
label | 9ccee945-4d8b-5c2a-90b7-ed53e02367ca |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.32 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | b69bfe85-c15d-5239-9dac-e3a8ffcc204d |  | note | Detail of Activity - MDD and OWC
label | 2ccb2d3a-57f8-5330-ac35-8991ea47c78b |  | note | M
label | 69264776-672c-5e0a-8b75-6d126a9b1874 |  | note | Minimum Test Frequency - MDD and OWC 1 test per 5000m² laid
label | 333d3c1c-a306-589f-9ca4-006876c6392b |  | note | Inspection / Test method - Laboratory Test
label | 5154171a-da4c-5e18-8ffc-22f41ea54b8e |  | note | Acceptance Criteria - Report value only
label | df951ebf-af08-5d68-9577-ab99b8e91f7f |  | note | Record documents - IANZ Accredited Lab Results
label | 7dd31d88-32c5-57a3-90d2-a0d861b77814 |  | note | Responsibility - WSP Laboratory
checkpoint-status |  |  | checkpoint | 600.33 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | cd837f7f-09b4-520a-a276-d7e76404915b |  | note | Detail of Activity - Mat Samples (1m2 canvas)
label | b221f0db-7b0e-50cf-a370-d8d5b4d818c9 |  | note | W
label | 08cbc2b0-7cf8-518e-b3c2-7e3491a5f329 |  | note | Minimum Test Frequency - 1 mat weighed every 400m2
label | 3ef20e0a-c5ed-5e95-b9f4-e5dbbfcc4e99 |  | note | Inspection / Test method - Mat Samples
label | 7961a2ed-1532-5702-b596-de83b393e4ec |  | note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | f2a39ec2-a88d-5a9f-848e-6f2ca6aec729 |  | note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | 958c08e4-c7d9-50dd-8a0e-c2f9e805172f |  | note | Record documents - QC Sheets
label | 2b979589-9075-587a-b106-98f1cec17f51 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.34 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | 618ae097-3a73-5e46-9148-d37f8ef82901 |  | note | Detail of Activity - Plateau Density Test
label | 6b8a82a4-49f7-5906-9d70-3aed6424a643 |  | note | W
label | 8cda657c-ca77-5519-aaa7-48c0c964ebac |  | note | Minimum Test Frequency - 1 Plateau Density Test per lot (take samples from behind stabiliser as required - min 3 - for lab testing to determine moisture correction)
label | 9f1ed805-f1a0-5573-8278-abfecc196b8c |  | note | Inspection / Test method - NDM
label | 9538c244-deb8-5f03-a78d-c1dfb73f8007 |  | note | Acceptance Criteria - Determine minimum number of roller passes required to meet 95% MDD using both primary compaction and finishing compaction rollers. Report values. Used for moisture contect correction
label | e318d436-0b25-5f89-96ba-60ca2f42c07b |  | note | Record documents - QC Sheets
label | 32d01e67-657b-5431-905f-a0ba3df5fa11 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.35 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | 6cb3c12b-5732-5953-b845-470520e21d97 |  | note | Detail of Activity - Stabilisation Depth
label | a8ba2e8a-b3e5-54d0-ad51-050cd0374b05 |  | note | M
label | 3ce86450-9e3d-5620-ae93-1cd40b70e047 |  | note | Minimum Test Frequency - Once per lot
label | 2e523c7f-a08f-51e6-ad9e-b3f6319409ee |  | note | Inspection / Test method - Visual Inspection (with tape measure)
label | 2e920809-349c-581f-80a6-99603dfe5923 |  | note | Acceptance Criteria - Stabilised to 200mm depth.
label | 55ec50d8-9838-5ace-adaf-9fe009526824 |  | note | Record documents - QC Sheets (Photos)
label | e2dccbc2-ea4a-51cc-8cd4-42872cfaf9e0 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.36 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | fa1802dd-851a-55c3-81a4-5f5cfd5ba497 |  | note | Detail of Activity - Indirect Tensile Strength (ITS)
label | 7f75416d-b626-52c2-9512-59b432c85713 |  | note | H
label | d1629ceb-3318-5b00-848b-4f9e8a6e0a9c |  | note | Minimum Test Frequency - Two (2) soaked & two (2) dry ITS - taken by IANZ accredited lab technician behind hoe
label | 9fd2f2d9-a4fe-5e0b-ab3a-3973317aa7dd |  | note | Inspection / Test method - Laboratory Test
label | dd6f903d-3722-5899-819e-4ae24f1d8bec |  | note | Acceptance Criteria - Dry ITS > 500 Kpa
label | 10cb1fc3-d267-5b10-b4f9-080c5adbfd09 |  | note | • Soaked ITS >450 Kpa
label | f1b28e45-38fa-5658-bf59-a6c951f95a1d |  | note | Record documents - IANZ Accredited Lab Results
label | 51f4fd9d-65c5-59f3-9ca6-5f90de347af4 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.37 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 90390d05-7389-5b33-899c-98601f38f867 |  | note | Detail of Activity - Stabilised Subbase Compaction
label | 16183671-2630-527c-ac15-3ff7a83be209 |  | note | H
label | 84c7be24-1d08-531a-b539-baa36cc7b669 |  | note | Minimum Test Frequency - Backscatter NDM (1 per 200m2)
label | 361c81d2-7223-5bb3-8c1a-1bc69b54aa7b |  | note | Inspection / Test method - NDM
label | 17de9454-97df-5019-8269-ab51583652d4 |  | note | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥ 92%
label | 28b6d2ca-d16d-5604-95d1-4b07e6a3b5ac |  | note | Record documents - IANZ Accredited Lab Results
label | 8479ffbf-a885-5912-a0fc-12f9d24ab2ed |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.38 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 4929b0bf-de10-59ec-a98f-30fb30d72ee3 |  | note | Detail of Activity - Stabilised Subbase Compaction
label | d5e4a247-8577-512d-b6f5-3034905cfe49 |  | note | H
label | bff185b8-7cdc-578d-8401-411341294394 |  | note | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | 37caa3d2-562c-58e5-8181-773a131547eb |  | note | Inspection / Test method - NDM
label | bfacafcb-2beb-55f2-9338-280e11ff4427 |  | note | Acceptance Criteria - Tests to be completed at 100mm depth increments starting at 200mm depth. Check for consistency/uniformity in test results.
label | 500f4c06-41fe-5848-baf5-d1a440c9b931 |  | note | Record documents - IANZ Accredited Lab Results
label | 45599dc7-f66a-516e-83a1-c8f648921e05 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.39 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 9625e209-e457-56c7-aedb-2228356a67e5 |  | note | Detail of Activity - Stabilised Depth
label | ed72c5eb-51ef-5b05-ab9f-66a00c80ea90 |  | note | M
label | 9f2824a5-3527-5c5a-90a0-659386edd1fc |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 2be55372-69eb-5380-a96a-4ba52091d811 |  | note | Inspection / Test method - Core Visual Inspection
label | 3b6da5e7-f7a0-5e63-82d8-6e5bb486bd4f |  | note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | aae78294-eb06-5209-b312-e09fbc128874 |  | note | • Grading of aggregate (i.e. good mix of different stone sizes)
label | 3db68ab6-6eee-56cd-bf37-7cb8982d014b |  | note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | a2c6da8a-40bb-5731-b318-b17e6e33adb6 |  | note | Record documents - QC Sheets (Photos / Coring Report)
label | e0a381c8-0752-5871-8249-6655b282ff16 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.40 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 81aa6ae4-7a66-53bf-8b12-66eff52c8b83 |  | note | Detail of Activity - Indirect Tensile Strength (ITS)
label | 324ac552-991e-51a0-b11a-b30dbe32ac78 |  | note | H
label | 621dcb7a-9c66-5120-8503-68cbb4b19eb5 |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | dc0aa6dd-1efe-5aad-bb03-72c38f86afa2 |  | note | Inspection / Test method - Laboratory Test
label | efde717e-670b-5a52-b57b-b57efe014712 |  | note | Acceptance Criteria - Target lab results.
label | 187aa51d-5698-5f73-88fc-02a95cb194ad |  | note | Tolerance: Lab result +/- 25%
label | f43a83d5-a495-572e-ab15-ad492de9e3bd |  | note | Record documents - IANZ Accredited Lab Results
label | baef51f7-0c8f-5a45-b536-151b293d07fa |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.41 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 7db767c6-da8f-58cf-bcd3-885d550be96d |  | note | Detail of Activity - Stringlines
label | bca86924-9eb7-52a2-b8eb-3bb021dcaf09 |  | note | H
label | f395fefb-9e45-5d01-80cd-7264aff5f8be |  | note | Minimum Test Frequency - Every 10m
label | 5124546f-3e1f-59c9-82d5-24a6b5a15f15 |  | note | Inspection / Test method - Visual Inspection
label | f48e00d6-fbab-503d-8e67-30a9f04e03a5 |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | 2abc3b19-2ed4-5648-a1fd-7f0e10dee4fc |  | note | Tolerance: +10mm/-30mm
label | f9409159-a61c-55aa-9b3b-008b629ad68e |  | note | Record documents - QC Sheets
label | e09691de-9b68-50ae-a690-e01a8a5638a2 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 600.27 - Collate above documentation
label | 8c00f146-043c-5461-b4ed-a20ef49f6f34 |  | note | Detail of Activity - Document review
label | 3d7e0f49-a08f-5c4f-bb84-fcbb73f22175 |  | note | H
label | ec20ef89-156b-5ed6-bc08-ec43c9a0aa42 |  | note | Minimum Test Frequency - Each ITP
label | 2044eaaa-b53a-58fd-a0a1-1b0ad70a88b9 |  | note | Inspection / Test method - Review
label | 310fc3ff-c2fa-5e39-a292-c05f5778f2d9 |  | note | Record documents - N/A
label | f5cef2b6-27f4-52df-81b5-c343ea901b39 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.28 - As-built drawings
label | 55ffdd7d-96d8-57f8-a8b2-1a02e73f1393 |  | note | Detail of Activity - Survey
label | 7b0b220c-09ff-5c3a-8d0d-f99360046934 |  | note | H
label | 340175bc-3360-59ff-8225-0c4e15a94458 |  | note | Minimum Test Frequency - At completion of construction
label | f4b62825-2235-585d-a636-56511b776fc8 |  | note | Inspection / Test method - As-built to be submitted at the completion of construction
label | 65b9fcca-9e4c-5105-bbc1-636464c65d4a |  | note | Acceptance Criteria - As-built to be submitted at the completion of construction
label | fa0344f0-9df9-52e1-96bc-e8c2fed3aa4a |  | note | Information to be captured: Maintain Redline drawings through works.
label | 4e46fbff-85b6-5ed7-90db-b2ae44a3be69 |  | note | Record documents - N/A
label | 1b1a6f25-3ab9-5fec-9723-c54b92eb3a38 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.29 - RAMM Data
label | 0e996535-e545-54e2-aa3e-e6150516b186 |  | note | H
label | 27bc3fc8-f84c-579e-a290-1569135d90af |  | note | Inspection / Test method - Info to be submitted by the completion of project construction
label | 6d225c4d-ebad-5685-bb57-e363bbd154e6 |  | note | Acceptance Criteria - Information to be captured:
label | 5f47788f-fb02-5b6f-a844-97783b469cce |  | note | Record documents - N/A
label | c81f7858-9e43-53b3-b486-2583772f9afe |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 33457026-5890-5eb9-a3ce-ebba6f05faf5 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 2e4c11e4-01e8-56df-94f9-b62ff23dd355 |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 8800c338-fcb8-51e2-832e-8a8d72db8d27 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | a208933b-a537-5efc-82c0-cfe89b2b0f42 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature