## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Type A Pavement |  |  |  |  | Yes | ITP - Type A Pavement | fb34c0f5-281f-4e52-be05-c8346d70ed7a
section | Pre-construction / Preliminary Compliance Requirements
checkpoint | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | Responsibility - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.2 - Drawings and Specification
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | Responsibility - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.3 - Set out
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.4 - Material Approvals
label | Detail of Activity - Submit testing data fir the following materials: - AP65 -GAP 40 -GAP 20 -Hardfill
label | H
label | Minimum Test Frequency - Prior to Construction
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | • Recycled Pavement/Subgrade Improvement Material:
label | • AP40:
label | ○ CBR >20%
label | ○ Sand Equivalent > 20
label | ○ Grading < 35% passing 75um sieve
label | • AP65:
label | ○ Crushing Resistance < 100kN
label | ○ Weathering Quality Index of A,AB, AC, BA, BB or CA
label | ○ Sand Equivalent ≥ 25 if > 4% passing 75um sieve
label | ○ CBR minimum 40 using heavy compaction
label | ○ Grading
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.5 - Underground Service Identification
label | H
label | Minimum Test Frequency - Prior To Construction
label | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
label | Record documents - InEight Records
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Construction and Finishing
checkpoint | 600.6 - Existing Pavement Assessment
label | Detail of Activity - Confirm Pavement Depth
label | H
label | Minimum Test Frequency - 50m centres
label | Inspection / Test method - Test Pits / Visual Inspection
label | Acceptance Criteria - Mill 200mm. Dig/core test pits to confirm if existing pavement:
label | – If existing underlying pavement is of sufficient depth (i.e. ≥250mm below mill surface/≥450mm below finished level), continue with "Existing Pavement" steps below (light green rows).
label | – If insufficient depth or poor quality, advise WSP Engineer, mill/excavate to 450mm from FL, and complete "Full New Pavement" requirements below (light blue rows for Recycled or Mixed Materials, light yellow rows for Engineered Material only - i.e. AP65,).
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Existing pavement to measure 450mm from finished level (minimum). If not "Full New Pavement" requirements are to be followed.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.7 - Existing Pavement Assessment
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Beam Testing
label | Acceptance Criteria - Review beam test results to determine if undercuts are required.
label | <1mm:
label | – No Undercut
label | 1 - 2.5mm Beam Deflection:
label | – Undercut 50mm
label | – Backfill with 20/40 drainage aggregate
label | 2.5 - 5mm Beam Deflection:
label | – Undercut 100mm
label | – Backfill with AP65
label | 5+ mm Beam Deflection:
label | – Undercut 200mm
label | – Backfill with AP65
label | Record documents - QC Sheets / Lab Result Sheet
label | Responsibility - Contractor
checkpoint | 600.8 - Existing Pavement Assessment
label | Detail of Activity - Milled Surface Stringlines
label | M
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Finished Level – String Line, +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | Record documents - QC Sheets (String Sheet)
label | Responsibility - Contractor
checkpoint | 600.9 - Existing Pavement - Subbase Stabilising (During Construction)
label | Detail of Activity - Mat Samples (1m2 canvas)
label | W
label | Minimum Test Frequency - 1 mat weighed every 400m2
label | Inspection / Test method - Mat Samples
label | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.10 - Existing Pavement - Subbase Stabilising (During Construction)
label | Detail of Activity - Plateau Density Test
label | W
label | Minimum Test Frequency - 1 Plateau Density Test per lot
label | Inspection / Test method - NDM
label | Acceptance Criteria - Determine minimum number of roller passes required to reach peak compaction strength using both primary compaction and finishing compaction rollers.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.11 - Existing Pavement - Subbase Stabilising (During Construction)
label | Detail of Activity - Stabilisation Depth
label | M
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - Visual Inspection (with tape measure)
label | Acceptance Criteria - Stabilised to 200mm depth.
label | Record documents - QC Sheets (Photos)
label | Responsibility - Contractor
checkpoint | 600.12 - Existing Pavement - Subbase Stabilising (Post Construction)
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Benkleman Beam
label | Acceptance Criteria - ≤ 2mm deflection
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.13 - Existing Pavement - Subbase Stabilising (Post Construction)
label | Detail of Activity - Stabilised Depth
label | M
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Core Visual Inspection
label | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | • Grading of aggregate (i.e. good mix of different stone sizes)
label | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | Record documents - QC Sheets (Photos / Coring Report)
label | Responsibility - Contractor
checkpoint | 600.14 - Existing Pavement - Subbase Stabilising (Post Construction)
label | Detail of Activity - Stringlines
label | H
label | Minimum Test Frequency - Every 10m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | Tolerance: +10mm/-30mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.15 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | Detail of Activity - Subgrade Levels
label | H
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Cut subgrade to 450mm below finished level.
label | • String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.16 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | Detail of Activity - Scala Penetrometer
label | H
label | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | Inspection / Test method - Scala Penetrometer
label | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | • ≥ 3 blows per 100mm - No Undercut
label | • 2-3 blows per 100mm - 200mm Undercut
label | • 1-2 blows per 100mm - 300mm Undercut
label | • <1 blow per 100mm - 450mm Undercut
label | Record documents - QC Sheets (Scala Sheet)
label | Responsibility - Contractor
label | Comments - Scala results to meet or exceed per below:
label | • 0mm - 100mm - ≥ 3 blows per 100mm
label | • 100mm - 200mm - ≥ 2 blows per 100mm
label | • 200mm - 300mm - ≥ 2 blows per 100mm
label | • 300mm - 400mm - ≥ 1 blow per 100mm
label | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.17 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | Detail of Activity - Proof Roll
label | H
label | Minimum Test Frequency - One per lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut
label | • 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
label | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.18 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | Detail of Activity - Undercut Measurements
label | M
label | Minimum Test Frequency - Every undercut section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Measure and record undercut area and depth
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
checkpoint | 600.19 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | Detail of Activity - Scala Penetrometer
label | H
label | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | Inspection / Test method - Scala Penetrometer
label | Acceptance Criteria - No Target required, For Record purpose only
label | Record documents - QC Sheets (Scala Sheet)
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.20 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | Detail of Activity - Backfill Layers
label | M
label | Minimum Test Frequency - Every 20m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Use recycled pavement (millings), Hardfill or AP65 if available.
label | • We propose to use proof roll instead of NDM testing because of the variablity of the recycled material and the bitumen content in it making it hard to test.
label | • This supersedes clause 22.2.1 in the project Specification.
checkpoint | 600.21 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Beam Testing
label | Acceptance Criteria - ≥ 2 mm
label | Record documents - QC Sheets / Lab Result Sheet
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.22 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Layer
label | Detail of Activity - Construct Subbase
label | M
label | Minimum Test Frequency - Per Lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Construct subbase with 200mm of millings and top up with AP65 if needed. (330mm below TOK) Add 50mm of 20-40 drainage material.
label | • (280mm below TOK) Ensure material is compacted and enough volume to be stabilised.
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Check each layer with strings
checkpoint | 600.23 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Mat Samples (1m2 canvas)
label | W
label | Minimum Test Frequency - 1 mat weighed every 400m2
label | Inspection / Test method - Mat Samples
label | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.24 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Plateau Density Test
label | W
label | Minimum Test Frequency - 1 Plateau Density Test per lot
label | Inspection / Test method - NDM
label | Acceptance Criteria - Determine minimum number of roller passes to achieve peak/maximum density using both primary compaction and finishing compaction rollers.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.25 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Stabilisation Depth
label | M
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - Visual Inspection (with tape measure)
label | Acceptance Criteria - Stabilised to 200mm depth.
label | Record documents - QC Sheets (Photos)
label | Responsibility - Contractor
checkpoint | 600.26 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Benkleman Beam
label | Acceptance Criteria - ≤ 2mm deflection
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.27 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Depth
label | M
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Core Visual Inspection
label | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | • Grading of aggregate (i.e. good mix of different stone sizes)
label | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | Record documents - QC Sheets (Photos / Coring Report)
label | Responsibility - Contractor
checkpoint | 600.28 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stringlines
label | H
label | Minimum Test Frequency - Every 10m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | • Tolerance: +10mm/-30mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.29 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | Detail of Activity - Subgrade Levels
label | H
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Cut subgrade to 450mm below finished level. String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.30 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | Detail of Activity - Scala Penetrometer
label | H
label | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | Inspection / Test method - Scala Penetrometer
label | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | • ≥ 3 blows per 100mm - No Undercut
label | • 2-3 blows per 100mm - 200mm Undercut
label | • 1-2 blows per 100mm - 300mm Undercut
label | • <1 blow per 100mm - 450mm Undercut
label | Record documents - QC Sheets (Scala Sheet)
label | Responsibility - Contractor
label | Comments - Scala results to meet or exceed per below:
label | • 0mm - 100mm - ≥ 3 blows per 100mm
label | • 100mm - 200mm - ≥ 2 blows per 100mm
label | • 200mm - 300mm - ≥ 2 blows per 100mm
label | • 300mm - 400mm - ≥ 1 blow per 100mm
label | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.31 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | Detail of Activity - Proof Roll
label | H
label | Minimum Test Frequency - One per lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
label | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.32 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | Detail of Activity - Undercut Measurements
label | M
label | Minimum Test Frequency - Every undercut section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Measure and record undercut area and depth
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
checkpoint | 600.33 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | Detail of Activity - Backfill Layers
label | M
label | Minimum Test Frequency - Every 20m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.34 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - MDD and OWC
label | M
label | Minimum Test Frequency - MDD and OWC 1 test per 5000m² laid
label | Inspection / Test method - Laboratory Test
label | Acceptance Criteria - Report value only
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
checkpoint | 600.35 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Mat Samples (1m2 canvas)
label | W
label | Minimum Test Frequency - 1 mat weighed every 400m2
label | Inspection / Test method - Mat Samples
label | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.36 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Plateau Density Test
label | W
label | Minimum Test Frequency - 1 Plateau Density Test per lot (take samples from behind stabiliser as required - min 3 - for lab testing to determine moisture correction)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Determine minimum number of roller passes required to meet 95% MDD using both primary compaction and finishing compaction rollers. Report values. Used for moisture contect correction
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.37 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Stabilisation Depth
label | M
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - Visual Inspection (with tape measure)
label | Acceptance Criteria - Stabilised to 200mm depth.
label | Record documents - QC Sheets (Photos)
label | Responsibility - Contractor
checkpoint | 600.38 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Indirect Tensile Strength (ITS)
label | H
label | Minimum Test Frequency - Two (2) soaked & two (2) dry ITS - taken by IANZ accredited lab technician behind hoe
label | Inspection / Test method - Laboratory Test
label | Acceptance Criteria - Dry ITS > 500 Kpa
label | • Soaked ITS >450 Kpa
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.39 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Subbase Compaction
label | H
label | Minimum Test Frequency - Backscatter NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥ 92%
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.40 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Subbase Compaction
label | H
label | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Tests to be completed at 100mm depth increments starting at 200mm depth. Check for consistency/uniformity in test results.
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.41 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Depth
label | M
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Core Visual Inspection
label | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | • Grading of aggregate (i.e. good mix of different stone sizes)
label | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | Record documents - QC Sheets (Photos / Coring Report)
label | Responsibility - Contractor
checkpoint | 600.42 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Indirect Tensile Strength (ITS)
label | H
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Laboratory Test
label | Acceptance Criteria - Target lab results.
label | • Tolerance: Lab result +/- 25%
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.43 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stringlines
label | H
label | Minimum Test Frequency - Every 10m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | • Tolerance: +10mm/-30mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Close Out
checkpoint | 600.44 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Record documents - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.45 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - As-built to be submitted at the completion of construction
label | Acceptance Criteria - As-built to be submitted at the completion of construction
label | Information to be captured: Maintain Redline drawings through works.
label | Record documents - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.46 - RAMM Data
label | H
label | Inspection / Test method - Info to be submitted by the completion of project construction
label | Acceptance Criteria - Information to be captured:
label | Record documents - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | Contractor's Rep Name:
holdpoint | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | BBO Engineers Rep Name:
holdpoint | Add Signature