## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Stair - Ref: |  |  |  |  | Yes | ST - S - Stair Installation | 122f0f66-a271-43f0-85b7-5c1e87f49314
checkpoint-status |  |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Grid Set-out offset and level correct
checkpoint-status |  |  | checkpoint | Joints scabbled and acceptable
checkpoint-status |  |  | checkpoint | All setout completed correctly and approved
checkpoint-status |  |  | checkpoint | Temporary support installed and approved
checkpoint-status |  |  | checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Windows, Sliders and Sealants - Ref: |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | 23be709e-28e6-495f-8369-d4df84b538b2
checkpoint-status |  |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status |  |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status |  |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status |  |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status |  |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 3f208980-dd95-491b-b6cf-de19a73f830a
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | e7281e1a-fff3-5c20-92a4-8ba7ccdbc79b |  | tickbox | LBP Memorandum/ Record of works filled out, signed and attached
boolean | 119750bc-b02f-5337-9d14-8ca9c0bbe792 |  | tickbox | Any Additional Compliance Documentation - Completed and Attached
label | 014eab8e-c6ef-5946-9bd2-d7a399006263 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Structure Timber Framing - Ref: |  |  |  |  | Yes | ST - S - Timber Framing | 4150dab4-0689-4a42-97e6-dd59de7b753d
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square / Frames are plumb and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Reinforcing - Ref: |  |  |  |  | Yes | ST - S - Concrete Reinforcing | 525aed4b-a0ee-4d0c-a6d2-03c2b0a97481
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 9fedeb8a-4eaf-528c-a5f1-ffdb049e7868 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | f090acd7-6fb4-5d0c-b8bf-85dd377a8053 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Beam - Ref: |  |  |  |  | Yes | ST - S - Precast Beam Installation | 61076594-0cb4-4b1c-8e27-ed1985e8ecd2
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | RAB - Ref: |  |  |  |  | Yes | FC - S - RAB | 659a6199-c82d-4385-ba3d-1b0db886b3f5
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status |  |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status |  |  | checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint-status |  |  | checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint-status |  |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status |  |  | checkpoint | Batten on RAB Board for cladding fixings
checkpoint-status |  |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | FC - S - Tapes |  |  |  |  | Yes | FC - S - Tapes | 9322ff74-a7cd-46c7-bfb5-6b9e2b9a90ad
checkpoint-status |  |  | checkpoint | 3m taping around windows and sliders around the exterior framings as per the manufacturer specifications
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Lintel Installation |  |  |  |  | Yes | ST - S - Lintel Installation | 9b35ec04-086c-4c89-ae7e-d54b0a3de9b2
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Lintel Installation completed (checked location & level) and no damages
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Rib & Infill Installation |  |  |  |  | Yes | ST - S - Rib & Infill Installation | a2128715-6477-4580-bcf2-ffa2ba6e522c
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Infill Panel SWMS compiled and provided to Ryman for review prior to work starting on site
checkpoint-status |  |  | checkpoint | Ribs inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Infill boards inspected on arrival. No knots, no cracks or other weaknesses across 25% of the width.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" and attached.
checkpoint-status |  |  | checkpoint | Area cleared for propping to be erected in place.
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Propping/Falseworks
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved design.
checkpoint-status |  |  | checkpoint | U Head brackets rotated to support bearers, bearers clipped to U head brackets.
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Inspect against rib install and propping layout drawings. Mark up hard copy drawings accordingly and upload to this checkpoint to verify the specification has been met.
checkpoint-status |  |  | checkpoint | No visual damage to ribs
checkpoint-status |  |  | checkpoint | SWMS implemented and followed.
checkpoint-status |  |  | checkpoint | Ryman Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO RYMAN FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill boards tightly constructed as panels, including 'backbone', 6 to 10 boards in length.
checkpoint-status |  |  | checkpoint | Infill panels fitted tightly between ribs.
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined.
checkpoint-status |  |  | checkpoint | Infill panels locked with timber blocks to prevent lateral movement.
checkpoint-status |  |  | checkpoint | Infill boards secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (No gaps)
checkpoint-status |  |  | checkpoint | Ryman Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO RYMAN FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Facade Timber Framing - Ref: |  |  |  |  | Yes | PRE - S - Timber Framing | a22d1525-7b7a-4777-9727-5e964a202c4f
checkpoint-status |  |  | checkpoint | Building square placed in all internal corners
checkpoint-status |  |  | checkpoint | All walls are parallel
checkpoint-status |  |  | checkpoint | All door openings correct
checkpoint-status |  |  | checkpoint | Check levels and straight edges
checkpoint-status |  |  | checkpoint | All DPC installed to walls
checkpoint-status |  |  | checkpoint | All internal corners have appropriate fixings for plasterboard
checkpoint-status |  |  | checkpoint | Appropriate deflection head gap
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | FC - S - Flashing installation |  |  |  |  | Yes | FC - S - Flashing installation | ae222a5d-dfae-4cde-bcda-86935b52667b
checkpoint-status |  |  | checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint-status |  |  | checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint-status |  |  | checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint-status |  |  | checkpoint | Aluminium window jamb side flashings are installed
checkpoint-status |  |  | checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | ST - S - Precast Flat Slab Installation | ae2e3055-f5db-4aae-ac25-944b640a69d4
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Roof structure - Timber Trusses |  |  |  |  | Yes | ST - S - Roof structure - Timber Trusses | b29e6d41-9667-400e-a3f3-f7794a26fc70
checkpoint-status |  |  | checkpoint | Truss hardware completed as specified
checkpoint-status |  |  | checkpoint | All fixings in place
checkpoint-status |  |  | checkpoint | Truss seating checked and accurate
checkpoint-status |  |  | checkpoint | Tile battens installed and acceptable
checkpoint-status |  |  | checkpoint | Underlay completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-tile checks completed and no issues identified
checkpoint-status |  |  | checkpoint | Load tiles completed and acceptable
checkpoint-status |  |  | checkpoint | Installation and recheck completed and no issues identified
checkpoint-status |  |  | checkpoint | Lay capping completed and acceptable
checkpoint-status |  |  | checkpoint | Ridges installed and acceptable
checkpoint-status |  |  | checkpoint | Fascia gutters installed and acceptable
checkpoint-status |  |  | checkpoint | Trusses are installed correctly and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Hatches - Ref: |  |  |  |  | Yes | FC - S - Hatches | b3e93fb5-2688-4d59-bae4-4df87203c006
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Pour - Ref: |  |  |  |  | Yes | ST - S - Concrete Pour | c6ab0387-43e5-4b68-a342-e8e06433fef4
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | a8f394fb-5ad5-5248-98fe-9d32bd4bcbb6 |  | textbox | Area to be poured:
text | 16a29a7e-a8d2-5291-8fe6-5c190d3c99a0 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 90ff9ea4-aaab-52c6-a985-f4e18cc037fe |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | feecadb9-32a1-55f7-9b83-28eafdc2b43a |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 15068b2f-b9c0-50ca-ac44-135da8b89b07 |  | textbox | Supplier Name:
text | 2020a77b-66c1-558b-9b14-ebdf85b72311 |  | textbox | Specified concrete strength: | mPA
text | 54bf03b3-6993-5156-9fd1-cca1855a3cae |  | textbox | Concrete strength ordered: | mPA
text | dd8481b1-ac1d-5939-b31c-56c008b89283 |  | textbox | Concrete quantity ordered: | m3
button | 9fe90ebf-14e1-5338-b83d-e9e4472837b7 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | aa37fa86-442a-57b9-82af-b3393dcabe58 |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Steel Portal - Ref: |  |  |  |  | Yes | ST - S - Structural Steel Installation | cc262c07-12e8-4108-968b-d8c50d0e1e45
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Hold down bolts in the correct location
checkpoint-status |  |  | checkpoint | Pre erection checks complete
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Steel correct size and type
checkpoint-status |  |  | checkpoint | Welding certificates sited
checkpoint-status |  |  | checkpoint | Installed in the correct location and orientation
checkpoint-status |  |  | checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | All bolts secure/ correctly tensioned
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checkpoint-group |  |  | section | Post-Installation
checkpoint-status |  |  | checkpoint | Welding Visual/Scanning inspections completed
checkpoint-status |  |  | checkpoint | Chemical anchor proof tests conducted on the sample selected by the MV Engineer
boolean | 5c992922-4d4b-5a03-ad3d-6cc5c8ff09ed |  | tickbox | Chemical anchors are tested to 0.7xdesign load
boolean | db3bed6a-1e82-5610-a2f9-475b3eb16e45 |  | tickbox | The test load of the bar is provided by the MV Engineer
boolean | 7f299ce4-bef0-5ef5-8abc-8b59a66cfc4e |  | tickbox | Proof load tests maintained for a minimum of 30 seconds
boolean | ed2f789e-2f90-5e14-9d9c-56ecd9c89514 |  | tickbox | The load did not drop more than 10% during the testing
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Mechanical anchor testing conducted on the sample selected by the MV Engineer and witnessed by the MV Engineer
boolean | 26aa45f1-64d8-5a16-b21c-683cf771be3e |  | tickbox | For trubolt or similar anchors the maximum tightening torque is reviewed
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S -Panel Starter bars Installation |  |  |  |  | Yes | ST - S -Panel Starter bars Installation | d07be0a2-173a-4bfb-9662-3a392acc9574
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/ correct
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc.) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Panel starter bars installed correctly to specifications (location, size, length and spacing) and ready to place the precast panels
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | FC - S - Soffits |  |  |  |  | Yes | FC - S - Soffits | e09bf4e1-b79e-4866-b7e7-295d6ba4cdf9
checkpoint-group |  |  | section | Pre-Installation Checks
checkpoint-status |  |  | checkpoint | Wiring in and anchored down for downlights, checked and accurate
checkpoint-status |  |  | checkpoint | Air Conditioning pre wire and pipe completed and acceptable
checkpoint-status |  |  | checkpoint | Fire sprinklers droppers installed and acceptable
checkpoint-group |  |  | section | Soffits works checks
checkpoint-status |  |  | checkpoint | Framing completed, checked and accurate including sheet joins/blocking
checkpoint-status |  |  | checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint-status |  |  | checkpoint | Villaboard installed, stopped and painted, checked and acceptable
checkpoint-status |  |  | checkpoint | Plaster installed as per spec and painted and acceptable
checkpoint-status |  |  | checkpoint | All soffits completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Insitu Stitch Joints |  |  |  |  | Yes | ST - S - Insitu Stitch Joints | eec354e3-2976-4fe5-95f2-7c9f2d90d96c
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details:
text | 97cddf14-1eda-59b0-8f73-d3d6fde5b320 |  | textbox | Area to be poured:
text | 489e23ce-9c10-5b32-9fa9-9b73a6527f54 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS