## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 04 - Construction Formation | itp |  |  |  | Yes | ITP 04 - Construction Formation | 12a33db2-38b3-446b-852e-29aadcc35f6d
checkpoint-status |  |  | checkpoint | 1 - Subgrade Testing
label | c899317b-012b-5d4f-a5a9-6710b8b6ef9f |  | note | Activity TASK - Review the results of any Scala Penetrometer tests, CBR tests and Benkelman beam test, and where the target values are not achieved, determine the extent of any further undercuts required. Alternative recommend a modification of the pavement layer thicknesses.
label | e3b5350d-5fe0-5680-97d2-6f4c6b91736d |  | note | Acceptance Criteria -
label | 54e91508-3967-537c-96df-2d4880038142 |  | note | • Test Frequency at 15.0m intervals in any one-line, multiple lines or staggered.
label | 25398a08-68f7-5618-9bb0-9d2d801ccfef |  | note | • Scala Penetrometer tests to NZS4402.6.5.2at 150,300, 450 and 600 below the final subgrade level. Take supplementary tests as directed by the engineer where any reading is less than the CBR design value. Scala penetrometer values shall be converted to CBR values by engineers experienced in soils engineering and who have experience with the local soils forming the subgrade.
label | 62449475-270c-518b-ac6e-29ff38a1f4ca |  | note | • Carry out in-situ CBR tests to NZS 4402.6.1.3 at 150, 300, 450 below the subgrade level.
label | 2cc2acaf-adc9-5dc3-a003-a30d60069047 |  | note | • Undertake supplementary tests as directed by the engineer where any reading is less than the CBR design values.
label | a38047dc-8c06-517b-b53f-bee1860e7c3f |  | note | • Carry out Benkelman Beam tests on top of the subgrade to TNZ T/1. Where any reading is more than 1.5 times maximum design value, carry out testing at 5.0m intervals either side of the value to determine the extent of the weak area.
label | c300d8ea-bdbb-580b-b418-7db9b6435cff |  | note | FREQUENCY - Ad-hoc
label | 3392d886-ee16-5521-8863-3cf66c219ce8 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signed Delivery Note and checklist
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 2 - Undercutting
label | 79388ae9-8d0f-50fb-9f2d-0ef59e0d6dcc |  | note | Activity TASK -
label | 438f591a-e765-5a56-bea6-65d06926ebd6 |  | note | • Carefully backfill and compact undercut sections. The minimum undercut size is to be half the road where patchwork is required, or not less than 3.0m width and 5.0m length.
label | 4dff5968-c9b3-5eea-bde4-1d41cc45d969 |  | note | • Undercutting shall not be terminated in a manner that will trap water within the replacement material where material is undercut to a level of 100mm above a drain invert, provide drainage outlet paths either to a subsoil drain, catchpit, or to a free outlet.
label | ac35c82c-ce3e-5123-b1dc-b405434c65b4 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 1e4dc328-d1e8-5136-add1-cb67810868f3 |  | note | FREQUENCY - Prior to Commencing
label | 1f829816-7118-5cb5-a309-427aab500d37 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Results of fill tested.
label | 8c099c0e-c1d5-5604-98fb-13e4a139ff1b |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 3 - Selections for Undercuts
label | 46fbfdfb-1fa6-5bd4-a545-ef65c20f1770 |  | note | Activity TASK -
label | be05778c-a6f6-5ee9-90f5-ec23509d9a3f |  | note | • Road
label | 6b1ace98-b7ee-5561-b86a-c915950f1b91 |  | note | – Subgrade CBR <2% (Undercut 500mm and backfill with sand. Apply geotextile to top surface of sand).
label | 4f2374cd-cf88-5b73-a85d-f5d9adc4f6ab |  | note | – Subgrade CBR <3% (Undercut 300mm Apply geotextile fabric to cut surface, Backfill with sub basecourse).
label | 0873f66f-3b07-5a60-a0b5-1b36bd603209 |  | note | – Subgrade <4% (Undercut 100mm and backfill with sub base course) – Subgrade <5% (Apply geogrid).
label | fbf88204-99a3-5009-b7db-1df08c6e449d |  | note | – Benkelman Beam >3mm (Undercut 500mm and backfill with sand. Apply geotextile fabric to top surface of sand)
label | 33b7c4e7-bd2f-548f-a4da-a07021b9a095 |  | note | – Benkelman Beam >4mm (Undercut 300mm and apply geotextile fabric to cut surface backfill with sub basecourse)
label | 27ad772d-c62f-554c-b95a-861e270d96d1 |  | note | – Benkelman Beam >6mm (undercut 100mm and backfill with sub basecourse)
label | 71f83fd5-3260-5b3d-9bca-7aab6a8891c8 |  | note | – Benkelman Beam >8mm (Apply geogrid)
label | 24954e61-34b7-599a-a2c2-0ea143060718 |  | note | – Subgrade CBR <2% (Cement/Lime stabilise 300mm depth. (Refer 8616 Lime treatment of sub-Grades).
label | 1aac3653-f8a2-5716-95df-092bdb881d2e |  | note | – Subgrade <3% (Cement/Lime stabilise 200mm depth.
label | 0a5cf6a5-2200-56ee-bf4b-905780637ce8 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 494a573c-3ac2-5d23-9aaf-85f38f816fa6 |  | note | FREQUENCY - Prior to work being undertaken
label | e91bb661-a0a3-55fe-905e-9c2eafbfb423 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test results to be send to Engineer with Selection solution
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 4 - Stringing
label | 7e54d5d5-2432-5410-8bef-be9bde21e15b |  | note | Activity TASK -
label | eb4edc6c-f4b6-5a27-abbf-ae0995d1675d |  | note | • Check the formation prior to the placement of sub-basecourse material, by stringing in the presence of the engineer, to ensure that the pavement is constructed to the specified tolerances.
label | f5689f89-ba67-58bb-a32b-f20570df0b29 |  | note | • Do not undertake subsequent phases of the work until stringing is completed and the work approved by the engineer.
label | b500ec46-fe2c-5b9b-be12-291eaf9cb1a1 |  | note | • Pull string lines taut between level pegs. Place level pegs clear of the construction; they shall remain in place during all phases of construction prior to sealing.
label | 7d1582a9-a967-5bae-86bf-ba28740fcac5 |  | note | • Mark pegs to show their relationship to seal or kerb levels. When kerbs have been laid and approved as level, they may substitute for level pegs.
label | d10471d5-f56c-5989-850b-4d4abbc54a58 |  | note | Acceptance Criteria -
label | 0a9c97ce-5621-501e-82fa-33a68bb4d512 |  | note | • Acceptance by Engineer.
label | 60fbb00c-0d97-54b1-81b9-8628b6077db2 |  | note | • Take measurements on roads at the centreline and at each edge and at not more than 5m intervals along the string. Take string measurements at intervals not exceeding 100m along the construction. Check levels by 'eyeing in' longitudinally at the surface level.
label | fd067071-5147-5485-9c8d-0d6387f891fa |  | note | • Additional Survey report will be provided with additional 12 shots per 100m.
label | dd0f5a20-b737-5fce-9f19-03857de317f5 |  | note | FREQUENCY - Ongoing
label | 9a2671ca-8c53-57bb-b2bf-da9b1dd3986b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test results to be send to Engineer with Selection solution
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 5 - Formation Level
label | 33372cbd-dd56-53c8-9478-c59b618fb3c0 |  | note | Activity TASK -
label | 438527cf-fd97-54cc-b151-ada8d598ff53 |  | note | • Following verification of the design subgrade CBR the surface of the subgrade shall betrimmed to line and level to achieve an even grade between level control points.
label | 3517bfba-3f7e-57b0-9184-325f48fba5d5 |  | note | • Ensure the surface of the formation level conforms to the levels and grades within tolerances of 0mm to minus 25mm and that no point in the general surface varies by more than 15mm from either a 3.0m straight edge laid parallel to the centreline of the road, or from a camber board placed at right angles to the centreline. No part of the sub-grade shall have undulations that could cause ponding.
label | e5732adf-c069-5d7a-8ca8-1d6dab4bd2a9 |  | note | • The area of subgrade brought to completion on any one day shall not exceed that which can satisfactorily be covered with metal on the same day.
label | 5695a2dc-7b25-59ef-a1cc-3b4452a70430 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | d696e539-7386-5fe5-a276-63eca1ef7d50 |  | note | FREQUENCY - Ongoing
label | 3b26c60f-c305-5d2a-915f-4e13304c0c37 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test results to be send to Engineer with Selection solution
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checklist-flat |  |  | checklist | ITP 01 - Edge Kerbs & Gutters | itp |  |  |  | Yes | ITP 01 - Edge Kerbs & Gutters | 2b1dd9f3-3964-4ca1-98ee-7a3f5e623593
checkpoint-status |  |  | checkpoint | 1 - Inspection
label | 8282c795-09ff-53a1-9c92-994669c0b5f5 |  | note | Activity TASK - Before starting work inspect the area to ensure that the subgrade is to the specified standard, free from soft spots, to the correct falls and all services completed, to allow work of the required standard.
label | d16cd4d4-fc98-5c3c-a8cf-ae9261d17079 |  | note | Acceptance Criteria - Before you Dig consulted and deployed on site – Inspected by Project Engineer/Project manager
label | 8009cea0-ee72-50a0-9e79-277e14a9a6c9 |  | note | FREQUENCY - Prior to Commencing
label | f50e586f-0eb1-5899-afa7-afcf0c54b238 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Before you Dig report and marking on site
label | 15e05e79-ac71-59c7-83c3-6ab39148ee67 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
label | 2b657f91-0818-546b-9dff-175656287503 |  | note
checkpoint-status |  |  | checkpoint | 2 - Form Kerb and Channel Sub-Base
label | 372fa695-c6e9-5fc1-8d84-84b4b0d90f33 |  | note | Activity TASK - Ensure the formation to bedding sub-base level for kerb and/or channel is well compacted, smooth, uniform and to the required level.
label | 13a10bac-6b72-5154-a1ad-5d02775268f1 |  | note | Acceptance Criteria - Unless otherwise shown on drawings, bed concrete on not less than 75m thick compacted sub basecourse layer forming the adjacent pavement or GAP40. – On site inspection by Project manager.
label | e1424a47-a299-5da2-a564-4867dc39b5d8 |  | note | FREQUENCY - Every new section of Kerb and channel.
label | 29c7894f-d4de-5784-8cb3-8bad843a86fb |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence with Comments to Client Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 3 - Slip formed Kerb and Channel
label | ae1aa56f-f753-5b41-bf88-7459170e8633 |  | note | Activity TASK - The finished kerb and channel shall be made using 20 MPa Concrete in accordance with the Territorial Authority Standard Detail for slip formed kerb and channel, or if the Territorial Authority does not have its own standard, in accordance with that shown in NZS4404. (Figure 3.7 Kerbs and Dished Channels)
label | fbe99566-22b8-5412-925e-e641ffc18560 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | e341a1e1-8fce-5905-bb57-bfcc10ea063d |  | note | FREQUENCY - Prior to commencing.
label | 5ab54caf-4405-549c-bb91-43b457a96843 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence with Comments to Client Engineer / Project Manager
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 4 - Alternative Slip Form sections
label | a3b55413-b74e-5157-9582-389a3f567097 |  | note | Activity TASK -
label | 47210621-772e-5497-ad90-5c0153558fdf |  | note | • Confirm the use of forms for extruded or in situ kerbs which vary in section from those detailed.
label | 9e3049d9-9145-55c5-b487-48fce455ccb9 |  | note | • Unless the contractor has obtained the prior written approval of the territorial authority and is able to satisfy the engineer that the finished product will be satisfactory in both quality and alignment, alternative cross sections will not be permitted.
label | 03ff46a3-27d1-5ac6-851d-a858975a294f |  | note | Acceptance Criteria - On-site inspection and acceptance by Engineer.
label | 886191e8-5e3d-5cca-af02-4c6ec01cc063 |  | note | FREQUENCY - Prior to work being undertaken
label | d77fb22d-8b53-5142-8fbc-cf1f7a2ff7e4 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 5 - Alignment
label | 4b6bde0f-0786-5e89-844e-1cc09d8cc7af |  | note | Activity TASK - Lay edging, kerbs and gutter channels, true and straight to grade, alignment and level. Curves to sweep evenly around bends without kinks, flats or angles. Form bends in precast kerbing with purpose-made corner blocks.
label | abbfc055-6e40-5b14-b391-1907ee7a9d46 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | fc071b0a-17e2-59be-8a60-43bdf131a784 |  | note | FREQUENCY - Ongoing
label | a7916eb7-e68f-5b54-b8d1-c8d8dfef7c5d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence to Project Manager
label | c451558a-7931-5bf8-b5bb-e3ce7210cceb |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 6 - Construction Joints
label | aac7b38f-39e2-5bd8-86c5-19a4fd3050e8 |  | note | Activity TASK -
label | 333d7638-a251-5915-9757-e9b2cb3439c6 |  | note | • Form construction joints in boxed channels at 4.0m maximum centres either by pouring alternate sections and painting exposed ends with bitumen emulsion paint, or by providing bituminous fabric or fibreboard stops in the formwork.
label | 70ca99e4-8026-503c-8b6f-f47e8d93dd10 |  | note | • Form construction joints in-situ or extruded kerbs and channels by cutting to 30mm deep max at 3.0 metre centres maximum and at each side of the vehicle crossing. Form around catchpits and sumps.
label | a15e5a64-eb9b-54bf-a48d-5b310441abf8 |  | note | Acceptance Criteria - On-site inspection and acceptance by Engineer.
label | 3cb95898-daf8-5d83-ad70-79c6107d3889 |  | note | • Tolerances:
label | d2c105e6-b133-563b-8212-830fd60ba20c |  | note | • Maximum deviation from alignment:
label | 754871fe-5219-573d-8416-42cf91577811 |  | note | • Vertical: 3mm in 2.0m
label | 13125615-8a82-5a70-aeac-46364a982efd |  | note | • Horizontal: 3mm in 2.0m
label | db0e86a7-9944-5a0c-bbae-97fd319033fa |  | note | FREQUENCY - Ongoing
label | b48f1fe0-68a1-5f7d-9cb7-bf3bb60aca54 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
label | b9755206-6dcb-5f9a-acef-730f1b47dc8b |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY -
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 7 - Forming in Situ Dish Channels.
label | 54c852e7-cf28-548c-b493-35461c9d4eaa |  | note | Activity TASK -
label | b5aceab2-0505-5ffb-a819-188f27cd5ed1 |  | note | • Excavate, box for in situ concrete dish channel, place 3 x 10mm diameter reinforcing and cast as detailed using 20 MPa concrete, with construction joints every 4.0 metres maximum.
label | a2f1788f-c649-57b1-a93b-7717df9bd7f4 |  | note | • Channel to be 600mm wide and 200mm deep with 30mm dish as detailed. Form around catch pits and sumps. Exposed surfaces to show an even surface texture, with no honeycombing, hollows, fins, steps or air bubbles.
label | 72fd6363-d98b-5723-b63f-9457962ba8c0 |  | note | • Allow concrete to cure before making good the adjoining basecourse.
label | d5505476-5bd8-5f57-aaf4-aa6e38f8aba0 |  | note | Acceptance Criteria - On-site inspection and acceptance by Engineer.
label | 9195aff2-8a9a-52d2-bc95-db25a84521f5 |  | note | FREQUENCY - Inspection upon completion of drainage and prior to backfilling.
label | 6b7056d1-b649-5711-9c71-8ecceb23eb20 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 8 - Forming flush Kerbing
label | 19f019e2-7a8b-5797-aa47-590423f4ea42 |  | note | Activity TASK -
label | 12df1349-e09a-5e8c-826f-d759af85c436 |  | note | • Excavate, box for in situ concrete flush kerb and gutter channels and cast as detailed using 20 MPa concrete, with construction joints every 4.0 metres maximum.
label | a326544c-1ec3-5ac6-a4c2-aa93ff0143a0 |  | note | • Exposed surfaces to show an even smooth surface texture, with no honeycombing, hollows, fins, steps or air bubbles.
label | 09b73902-8052-5100-b7d6-af04ad24d8de |  | note | • Allow concrete to cure before making good the adjoining basecourse.
label | 6fa36cc6-ee72-5246-aba4-c32f6ba23092 |  | note | Acceptance Criteria - On-site inspection and acceptance by Engineer.
label | 4ecb92f4-3df1-5456-b538-baf083275a80 |  | note | FREQUENCY - Inspection upon completion of drainage and prior to backfilling.
label | a6bdd9c6-2f80-5775-8eb2-c8ac41f4b518 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 9 - Formwork
label | 6c268aba-842d-5261-9bd6-a99a4d201e88 |  | note | Activity TASK - Boxing shall be true and straight and shall conform to the lines and levels shown on the drawings. It shall not be set up until after the sub basecourse has been laid and shall not be stripped until the concrete is at least 36 hours old.
label | cd6eff12-6af5-58db-b789-c94dd172fd02 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager
label | dff97bbb-655f-55e5-a762-1fd6aaae6bb0 |  | note | FREQUENCY - Ongoing
label | e9c5bb23-4dec-51f4-96f7-5998ce74d2f8 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence to Project Manager
label | 1c0f748f-b8bd-5a50-bbaa-513152a7db53 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 10 - Backfill to kerbing
label | 2b6ae657-a31c-5f0a-a53c-a43f2f894b15 |  | note | Activity TASK -
label | 85be32c1-7450-5aa4-a3fa-959223d74bb3 |  | note | • Carry out backfilling and compacting behind the kerb in conjunction with base course construction to ensure even support to the kerb.
label | eb9ac70c-8b00-5590-928c-24aad477ba7e |  | note | • The fill operation shall be carefully controlled to ensure that the kerb is not displaced or damaged and the subbase and basecourse are not contaminated by the backfill material.
label | 5f48d00a-dbeb-55bb-9ee7-d8f4cd5a2a59 |  | note | • Do not carry out basecourse construction immediately adjacent to the kerb until at least three days after the kerb poured.
label | f84697f2-b523-5457-9ddb-92c67e1fe587 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 0309e09a-b8a1-5047-9887-9eca08ce76eb |  | note | FREQUENCY - Ongoing
label | 474d101d-fb7b-5b5b-95b2-f64d5bc20078 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence to Project Manager
label | eccd6ae9-f50b-576c-8f90-56839bd64016 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checklist-flat |  |  | checklist | ITP 06 - Fencing & Clearing | itp |  |  |  | Yes | ITP 06 - Fencing & Clearing | 404a1577-60d0-4223-9d42-d7824ef45468
checkpoint-status |  |  | checkpoint | 1 - Fencing
label | 34c0af66-5623-510f-945c-24921f0fa7f9 |  | note | Activity TASK - Install permanent fencing where such fencing is not affected by clearing or subsequent works. Install temporary fencing to secure the site where permanent fencing is not stalled, to prevent unauthorised access.
label | 862df625-c80f-5003-a440-ec81520b6447 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | b6ccda2a-c693-5304-a774-eeb8aa6a6e88 |  | note | FREQUENCY - Prior to commencing earthworks
label | 6a98b1e6-63a4-51f3-ac76-356402fb1d5f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo evidence of installed fence.
label | 3ca0f81d-291c-5d44-a569-abe177e0ca2e |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 2 - Clearing
label | 1c4a3e87-36a9-5137-b2f0-57a0c61a7ccb |  | note | Activity TASK -
label | 297f9f8e-d90b-53b9-bb5a-c9f683fc705b |  | note | (a) Clear the area required to complete the works or as otherwise indicated on the drawings. Carry out clearing for earthworks construction to TZ F/1, 3 clearing.
label | ec9903b1-a58e-599a-9ec4-2412e76c9960 |  | note | (b) Remove all rubbish, trees, stumps, obstacles, vegetation, roots, turf, organic matter and other deleterious or unwanted material from areas of operation.
label | 7e1d2feb-06bc-571d-8e11-c7dbe6dd1b54 |  | note | • Include all above and below ground structures and fences within the area of the site to be worked.
label | f66981fd-9a66-5d67-a4db-39a6453449c0 |  | note | (c) Remove tree stumps such that no roots exceeding 100mm remain. Stumps that are chipped shall have chipping material removed from the site.
label | 60e616a0-68c2-54cd-a3ef-5e3583de0d81 |  | note | (d) Materials of value shall be salvaged and stacked as directed on the site. They remain the property of the Principal/Landowner unless otherwise stated.
label | e478f5ed-3de1-58d8-9f59-12d1127ad420 |  | note | • Cart and dispose of all unwanted materials, vegetation and debris to an approved landfill. Burning or burying waste materials is not permitted. Repair or re-erect boundary fences, structures and other objects of value not scheduled for removal but which are damaged or destroyed by the work.
label | 9b6ceb03-186a-5dd7-bab6-25dd93351e31 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 91a57780-4a0c-532b-b8a1-c9bdd49f238b |  | note | FREQUENCY - Prior to commencing earthworks
label | d9f45725-e570-5fd8-80bc-fe9bdeb741e3 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo evidence of cleared area.
label | 6ab826d3-2743-52d7-9fe3-e683e33569ec |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 3 - Archaeological Discovery
label | a66f0122-462e-5155-b708-74f0789e45e6 |  | note | Activity TASK - If fossils, antiquities and other items of value are found refer to the general section 1220 Project for actions to be taken.
label | 97a9d8e9-8f7e-5df0-9b05-d10bc3a6e9b4 |  | note | Acceptance Criteria - On-site inspection and acceptance by Engineer.
label | 6454f876-8acc-5253-aa6e-9366ac169545 |  | note | FREQUENCY - Prior to commencing
label | 3fe4a499-491d-5a10-8486-22487d87aa1e |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo evidence of cleared area.
label | ea17617a-5e1f-5255-83a4-f65866604206 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checklist-flat |  |  | checklist | ITP - Stabilising |  |  |  |  | Yes | ITP - Stabilising | 7bcce166-9972-467f-9938-0502240961ec
checkpoint-status |  |  | checkpoint | Cement Supply
label | f934fa5d-8622-55e5-b2e5-1267722ae3d4 |  | note | SPECIFICATION REFERENCE - TNZ B5
label | 62cb2cea-7d04-5fc4-bc8b-89b4a257b868 |  | note | TEST REQUIRED - Supplier Documentation
label | be10169d-23d4-52f1-94ad-c64ebd5fb8af |  | note | INSPECTION BY - Visual Inspection
label | 40d7371f-3b29-5cb6-a52e-e74a1a3ca416 |  | note | TASK TIMING OR TASK FREQUENCY - TNZ M/15 / AS1672 Compliance Certificate to accompany all batches of cement delivered to site.
label | 563afad0-e6da-5741-99e5-65b515f63436 |  | note | ACCEPTANCE CRITERIA - Meets NZS 3122
label | 55b9ede7-9202-50bb-90eb-a4a383320147 |  | note | W
checkpoint-status |  |  | checkpoint | Record Depth
label | 4475964c-0376-5298-98ba-0f99d36ac05e |  | note | SPECIFICATION REFERENCE - Email from Engineer
label | 63030adc-00fa-56ca-8c2f-ad0d3934818e |  | note | TEST REQUIRED - Visual Inspection
label | fbe63b43-dd6e-5379-9fcc-599baa01870a |  | note | INSPECTION BY - UCC Rep
label | 2c7abe7a-df3c-57bd-819c-ce6f76335d69 |  | note | TASK TIMING OR TASK FREQUENCY - Application rate shall be recorded for each run
label | 70e1183a-4839-5841-9ffa-6170ecb08f86 |  | note | ACCEPTANCE CRITERIA - Depth must be equal to 150mm
label | 1073a4fe-a294-5bb0-830b-6fce55edd880 |  | note | W
checkpoint-status |  |  | checkpoint | Application Rate
label | 214e2660-4f2b-5010-b625-0f33ef81ba04 |  | note | SPECIFICATION REFERENCE - Email from Engineer
label | bbdb9a99-e632-5f26-977e-040af66bf313 |  | note | TEST REQUIRED - Mat Test
label | bc7e8b87-dfa9-5ae9-a9de-dfc0d73d85d5 |  | note | INSPECTION BY - UCC Rep/ Engineer
label | 5d7b1deb-f114-58b9-98d6-9cfb4a84edaf |  | note | TASK TIMING OR TASK FREQUENCY - Every 400m2
label | f6ecf61b-0765-5086-9745-43f5d772dc51 |  | note | ACCEPTANCE CRITERIA - Within +- 0.5kg/m2 of the specified rate
label | 4d813dae-75c1-5a29-ba37-4c8a9fa20eec |  | note | W
checkpoint-status |  |  | checkpoint | Application Rate (1)
label | ec6f22b4-4fbc-5d89-862d-f43c268731a2 |  | note | SPECIFICATION REFERENCE - Email from Engineer
label | 26f1ea3a-688d-5599-b41a-76689b8cc57f |  | note | TEST REQUIRED - Average Usage Test
label | 35738dd9-c8ef-5908-8c4b-eeeb442bc71b |  | note | INSPECTION BY - UCC Rep/ Engineer
label | 410857ef-9ac7-5b76-a24b-4bd354afd9c5 |  | note | TASK TIMING OR TASK FREQUENCY - Upon Emptying the spreader and bulk truck
label | a647da2e-8bb8-55c2-aafd-df376b8b30ca |  | note | ACCEPTANCE CRITERIA - Within +- 2.5% of the specified rate
label | 0fa9812e-3722-5861-ac54-75523857a612 |  | note | W
checkpoint-status |  |  | checkpoint | Compaction of Cement Stabilised Material
label | 26538710-e5d6-5032-8637-3deb2f9558f5 |  | note | SPECIFICATION REFERENCE - TNZ B5
label | d872fe18-c952-525e-b79c-26608f924144 |  | note | TEST REQUIRED - MDD using NDM
label | dc4a0d95-d29d-523b-8e2c-6c198456cc36 |  | note | INSPECTION BY - UCC Rep
label | 5ff069ff-b73a-5362-8e86-70ee957fa13b |  | note | TASK TIMING OR TASK FREQUENCY - Compaction must commence the same day as mixing. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m intervals on each lane.
label | 1c2ff394-2312-5bcb-99ad-a2ccd79df43b |  | note | ACCEPTANCE CRITERIA - Value of density tests shall be an average of 95% of MDD with no single test below 92%
label | 0fd08551-0cdd-54e5-bac0-05d9514fd76a |  | note | H
holdpoint |  |  | signoff | HOLD POINT
checklist-flat |  |  | checklist | ITP 05 - Storm Water Drainage | itp |  |  |  | Yes | ITP 05 - Storm Water Drainage | 88c52176-57eb-495d-8a34-acaeada343b2
checkpoint-status |  |  | checkpoint | 1 - Concrete
label | 98647e15-3c9b-542e-be7a-613c63a78e2c |  | note | Activity TASK -
label | 44f61d06-d854-5fbe-802f-a8ef46f48f0a |  | note | • All Concrete for cast in-situ structures to be ordinary grade concrete in accordance with NZS 3104, having a minimum crushing strength of 20Mpa at 28 days.
label | ba537b0b-c73f-591b-a65c-9697aa996c56 |  | note | • Bedding, capping and surround concrete, where specified, to be normal grade concrete with a minimum crushing strength of 20.0 MPa at 28 days.
label | 19915968-f299-53cd-9783-7db2a1f83ed3 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 9cb11f12-3b2e-523b-be08-4001e804abbc |  | note | FREQUENCY - Ad-hoc
label | f669c6b6-4375-5876-a1f4-551075396c3f |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 2 - Reinforcing Steel
label | 13ecb835-b1a0-5274-b205-7c85c757520a |  | note | Activity TASK - Grade 300 deformed bars to AS/NZS 4671, and mesh to AS/NZS 4671 (Any 500E mesh to AS/NZS 4671 as modified by NZS B1/VM1)
label | 18eace6a-a8e9-5e47-aed5-295fc9d27ef4 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 62147fa8-3efb-5f02-8c4a-0a5b0f968755 |  | note | FREQUENCY - Ad-hoc
label | 836bfc41-a8d6-57df-85bf-b2e14c30b8bb |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery Docket
label | 435f3ca3-cc2b-5917-b11f-aaf813473018 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 3 - Manholes
label | cd2ed887-fed6-541a-a0f9-de9dd2e3ef03 |  | note | Activity TASK - Standard precast concrete to NZS3109. Construct to NZS4404 figure CM-004, CM-005 and CM-006 or as shown on the drawings or specific Territorial Authority detail
label | 4e790999-9c08-52af-b7cc-993a50aab9a3 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 6b8a0fa5-1009-5556-bd98-83fe0e076f84 |  | note | FREQUENCY - Ad-hoc
label | 8d0fc232-1687-527c-b437-81086e4fdef7 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery Dockett & Product specifications
label | 0f518ec9-ce56-5280-bfa8-d965fba9580f |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 4 - Manhole lids
label | fba6a7d7-41d0-5c2f-8e80-f136d8e0a6cd |  | note | Activity TASK - Metal lids and frames to suit application. Cast Iron to AS1830, Ductile iron and metal lids to AS3996, Class B to Class G. Class A only to be used if specifically stated.
label | e2032714-4b5f-56c2-9b02-7c6c8ad3b586 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | ffb23b61-96fa-5646-bdd1-604e4f5666e4 |  | note | FREQUENCY - Ad-hoc
label | 6a76a7fa-1386-558a-9d6c-661269db0dac |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence to Project Manager
label | 57dbc830-40bd-5c02-9ad7-ea0ef61f207a |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 5 - Bedding Material
label | d88edb61-ce34-5fe9-857f-4179465f71bd |  | note | Activity TASK -
label | f1bf55a4-c378-575e-8863-f2b31b7dd773 |  | note | • Bedding and side zone backfill for uPVC and ceramic pipe to GAP 7. Bedding for concrete pipes to be GAP 20. Side and overlay zone backfill for concrete pipes to AS/NZS 3725, GAP 20.
label | a5a2bea1-ef26-5a36-a027-c8e3295ceb25 |  | note | • Side zone backfill for concrete pipes to NZS 4404, selected site won material free from stones larger than 40mm in diameter or other material liable to damage the pipes.
label | da9b6cc9-3b7e-55f4-9a47-d95ceabbce38 |  | note | • Bedding and surround for perforated drainage pipes to NZTA F2.
label | 49542de3-b4a5-55e5-afe3-d8ed1f3a59b2 |  | note | • Form weak concrete bedding with strength of between 5MPa and 7MPa by adding 12mm all in clean aggregate mixed with sufficient cement to the granular bedding material.
label | 4d72c1fe-ee08-5a9c-b4e4-e13cdab94531 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 4b3c5dd5-fe62-5128-9001-121dd9692b48 |  | note | FREQUENCY - Prior to work being undertaken
label | 4441ca62-abce-57ea-81df-d85fe20c25c5 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 6 - Backfill – outside pavement areas
label | 1a02d6d5-7aa2-5585-bcf0-21f65802a4ec |  | note | Activity TASK - The first 300mm of backfill above the pipe and 1.0m outside pavement areas to be selected site won material free from stones larger then 40mm in diameter or other material liable to damage the pipes. The balance of the backfill to be approved site won material.
label | b8c9be6f-132d-57f3-8422-5160d5a1c3bc |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | bc50019f-30d5-5078-80ac-b5c7b2e03ce8 |  | note | FREQUENCY - Ongoing
label | a53b2633-085b-5fc7-9e14-ebfd6d79229f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Project Engineer/Project manager
label | b9dcd2d0-637e-5cfc-aff0-4e2c5d33d249 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 7 - Backfill - inside pavement areas
label | 85f077b9-1423-5011-a5fa-30b7d55a9e06 |  | note | Activity TASK - The first 300mm of backfill above the pipe and 1.0m inside pavement areas to be well grade GAP 20. The balance of the backfill to subgrade level to be well graded GAP 65
label | 1b7d0760-23a6-5542-9ca5-7f21bc83b401 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 0f114cda-4e03-59bc-b77a-0b9992ef5a7f |  | note | FREQUENCY - Ongoing
label | b201f6d2-8e2b-5534-a9ba-62112e82b32e |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 814b3f0d-2059-521b-b9fb-48673feb7a65 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 8 - Trench Excavation
label | 69957a3d-b258-5aa1-abc9-43e8a447e7a7 |  | note | Activity TASK -
label | 2e5462c7-517c-51d4-892c-f8ffafbdcfab |  | note | • Excavate to the grades and levels shown on the drawings by open cut unless otherwise approved by the engineer in writing. Make the trench of a sufficient width to permit all operations necessary for the trimming or placing of bedding and for jointing of pipes to be carried out effectively.
label | e9fdb903-3233-57c1-85d5-94fc51468567 |  | note | • Prevent excavated material rolling into trenches in all excavation works.
label | 4e5b48f8-f6bb-579f-8e79-502d42fc040c |  | note | • Trench widths and foundation depths to be specific for each pipe type and size to AS/NZS 2032 and AS/NZS 2033 for PVC and polyethylene pipes respectively, and AS/NZS 3725 for concrete pipes, or as shown on the drawings.
label | a955c596-eee6-5a1c-8c48-7108e8470bed |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 36f70824-a30e-52a7-bb96-f81b3e090aa1 |  | note | FREQUENCY - Ongoing
label | daca832a-2fd5-5597-a3a6-a1253f969a29 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | faab94a8-881c-5b39-9e19-b656caf38a8b |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 9 - Over Excavation
label | 131fd838-6db0-5ab1-ae28-95b30dcdf51f |  | note | Activity TASK -
label | 41e214d9-66e8-51fd-839d-2fcf2057cfed |  | note | • Excavate only such ground as is necessary for the proper execution of the work, and if any excavation is made deeper or wider than required, reinstate as follows at no extra cost.
label | fe4826e0-4d2b-5ec2-94b9-7eb16e09c177 |  | note | • Where the trench or structure void is excavated below the grade specified in the drawings, without specific instructions to do so, it shall be refilled to grade at the contractors expense with crushed rock compacted as specified.
label | 8e4299dd-adc1-546b-84bc-0c348b6b6e2f |  | note | • Where the trench or structure void is excavated to a greater width than is shown on the drawings or specified, the engineer may require extra work or remedial measures to be carried out by the contractor at the contractors expense.
label | ccfad0bf-0772-58b0-863e-745f2ffe6f3f |  | note | • If in the opinion of the engineer any extra width will result in more load being placed on the pipe than it can safely carry, the contractor will be required to provide improved concrete bedding or stronger pipes or make the trench narrower by pouring low grade 10 MPa concrete along the sides of the trench so that the clear distance between opposite faces does not exceed the distance shown on the drawings.
label | b444c8e0-8e82-5b2b-a02f-5ac3895a30d4 |  | note | • The width of the trench for this purpose is between excavated surfaces, and includes the thickness of any timbering or shoring.
label | fd1d5aa7-feca-5712-a8b5-d067dd2c15c7 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | dd6791c8-4696-5cbd-8f61-36c2b9bac284 |  | note | FREQUENCY - Ongoing
label | 1e8baba4-3acb-57e4-9a75-3fc81662990d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 10 - Subsoil Water
label | 3d07c8a1-b99b-5221-af69-697da1f7057e |  | note | Activity TASK -
label | 1e112e4d-e513-5b30-977a-c62293d0f026 |  | note | • Keep subsoil water below the level of joints or concrete or moisture sensitive fine-grained bedding by means of approved side channels or perforated pipes and pumping as necessary, until the concrete has set sufficiently to prevent damage occurring or backfill extends above the top of the pipe.
label | fcdc98d2-f6d2-5b6c-a727-32b1d5b80283 |  | note | • Pumped water to be discharged to sediment treatment devices to the approval of the territorial authority, prior to discharge to the stormwater system or watercourse. Control groundwater levels to prevent floatation of pipes.
label | 904204c9-b1f7-50d2-b7de-c562e822fd46 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 8d6b2b51-bd65-57d7-8ee6-4777f05d3e9c |  | note | FREQUENCY - Ongoing
label | d20249af-d153-5dfd-86e1-7415fa9ecf22 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 753da3a2-1a46-569e-b876-461c47955121 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 11 - Sleep Gradients
label | efba335f-5c85-5b1b-ad58-c485f98e8d62 |  | note | Activity TASK - Where the gradient of the pipe is 1 in 10 or steeper, add sufficient cement to the granular bedding material to produce a weak concrete with a strength of not less than 7MPa. Where the gradient of the pipe is 1 in 5 or steeper, install anti-scour blocks to be located at pipe sockets at no less than 6.0m centres.
label | 0066fc36-a153-5415-9c94-231d9c624fc2 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 3b538d28-d2a3-5385-a358-444af9b715f4 |  | note | FREQUENCY - Ongoing
label | e8fa4013-261d-5475-8208-3e94cbf0361a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 47446c61-0fa0-5f5a-8654-b73513241807 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 12 - Backfilling
label | 873d496e-b514-5aef-89ab-12581e03b3e4 |  | note | Activity TASK - Compact carefully in pipe side zones in 150mm layers by means of a mechanical tamper or hand rammed as appropriate. Consolidate the remainder of the trench using plant or mechanical tampers in 200mm layers until the backfill material is at least as dense as the surrounding undisturbed ground or as approved.
label | 82d11c90-fb1f-5e52-b021-1be0fed695ff |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 75e9b74b-2277-5528-96a7-9dd9e0836e48 |  | note | FREQUENCY - Ongoing
label | 56297d4d-0941-5b99-b68f-e63afc38cc06 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | a68bf75c-85f3-55fb-8ab0-743d3cd8692b |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 13 - Cover
label | 65b61909-0150-5461-a2d1-cf9239d79e31 |  | note | Activity TASK -
label | 5ad8bff5-175c-53b4-8859-9db52a39eabe |  | note | • The minimum cover to be 750mm beneath berms and landscape areas, and 1.0m beneath pavements, shared use paths and other areas subject to wheel loads. Where these requirements cannot be met protect the pipes by concrete capping constructed from 100mm of 20MPa concrete over the full width of the trench.
label | f9fbeee9-e3db-5adb-a5b8-41e66f0dadf4 |  | note | • In situations where pipes are installed beneath pavement areas and are dependent upon pavement courses being in place to achieve the minimum cover requirement, the contractor shall be responsible for protecting those pipes against damage from construction loads until such time as pavement construction has been completed.
label | 6e84a0c0-2784-5bc5-abd3-7bba15588558 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | cffe3523-bed9-576f-8064-7b02d9be1a18 |  | note | FREQUENCY - Ongoing
label | 1c6f1545-add9-59d9-aeda-1fb41b3b9985 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 14 - Construct Manholes
label | 06a31470-853a-516f-9fd8-6b8875f6094b |  | note | Activity TASK -
label | de79bb04-e813-53fb-9b63-963519130152 |  | note | • Manholes to be precast 1050mm diameter unless shown otherwise. The base for a precast manhole shall be cast in-situ concrete a minimum of 150mm thick below the lower pipe invert and to a diameter of 1500mm, or at least 300mm • greater than the external diameter of the manhole.
label | 61015783-8785-53d7-b7fd-f1f4092d5c5b |  | note | • Lower the manhole risers into the base concrete and trowel the concrete neatly to a 45° finish at least 150mm up the outside of the riser.
label | 9606db2f-ecd5-5f3a-939a-f54bd02e7ed1 |  | note | • Select riser sections to suit the height of the manhole. Clean both faces of the joint before placing each riser section. Seal joints with a rubber/bitumen preformed sealing strip laid in the joint before placing each riser section.
label | d7f7432e-6df7-5e40-9e9a-b9250392557e |  | note | • Carefully stop all leaks and make the manhole watertight.
label | b3b77582-8d7f-5f97-a8c0-2515797a334d |  | note | • Place and align precast sections to provide vertical sides and vertical alignment of the ladder rungs over the outlet hole. Place the access hole in the lid over the ladder rungs, sealing the joint with preformed strip.
label | 99125acf-850d-5873-bf9d-4c95f19a9d65 |  | note | • Clamp joints with standard clamps to maintain strength and water-tightness.
label | 805489da-0c8d-5e07-b88e-a4d7ebbdfc50 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 748765e5-8cf9-5a0c-9746-5cadf6d722fd |  | note | FREQUENCY - Ongoing
label | 59f30459-355c-5976-a5c1-f4ea6d37deac |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 15 - Concrete Manhole Lid
label | 812c6204-ac00-5b80-9250-b02741763e21 |  | note | Activity TASK - Standard flat precast top slabs to NZS 4404, fig CM004, heavy duty 150mm thick for road carriageways and road berms, 100mm thick elsewhere.
label | 8eb418e2-4b6e-5246-b2e4-794dbd57dda8 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | abc3e3e6-b935-5eac-88f3-180051d915dc |  | note | FREQUENCY - Ongoing
label | 231bf26d-738e-580d-aecd-6c31c551309f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | e2709a77-7f4f-58bf-999d-12dc6ef047a8 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 16 - Manhole Cast Frame + Lid
label | 315831a5-7693-5018-9aa7-7666d9c5d725 |  | note | Activity TASK -
label | 61a56a85-58ea-5fe8-a1a9-0db9efcb9c2f |  | note | • Cast iron to AS 3996, heavy duty for road carriageways, pavement areas and road berms, light duty elsewhere.
label | 04c03cc4-7067-5559-a8aa-9f4a504ca95c |  | note | • Set manhole lid frames in normal grade concrete to ensure that the tops lie flush with and have the same cross fall as the final ground levels.
label | fa9315b0-5f3b-5cd0-bd22-d9e20699a6d3 |  | note | • Use precast adjustment rings if necessary to maximum 450mm total throat height (including lid and top slab). Fix or cast in the lid frame to the manhole top slab, to the manufacturer’s requirements.
label | e9d4a73e-209b-5244-83d1-71d83f351aa4 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | a98b68e0-ccfe-5545-ab1c-65d37bb9845c |  | note | FREQUENCY - Ongoing
label | 9bea50da-4c27-5c24-9d9d-10f639cbb97f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 5a108d5d-ec70-5c47-9fd1-4a8fd541afc7 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 17 - Catchpits
label | 02c6da0d-c932-57e4-b6b2-8a8db5e0471d |  | note | Activity TASK -
label | b2192fdb-6f8f-5b55-886d-b00c4f5b5b1e |  | note | • Catchpit leads to be 300mm RCRRJ or as shown on the drawings.
label | 70605871-a51c-5f7a-998e-4118304a2d39 |  | note | • Catchpits to be pre-cast as indicated on the drawings.
label | a76238a5-91f4-5611-877c-0fd2e8121d9f |  | note | • Bed on 50mm minimum depth of low-grade concrete and not directly on the excavated ground. Catchpit outlet pipe diameters should be shown on the drawings.
label | a59e1636-95ce-5933-912f-1f34afa6cef5 |  | note | • Set catchpit gratings in a concrete surround as shown on the drawings. Clear out all catchpit silt chambers on Practical Completion of the Contract Works.
label | 88c873a5-15ca-5957-9c4a-54437bf0e8f2 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | cfb0ffe4-8952-5d27-b0cc-e6436e9bb062 |  | note | FREQUENCY - Ongoing
label | 4752f2d2-3dbd-5fee-a86c-e6bd52fa3b15 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 553cd017-6aa5-5dea-a123-12da1b36086b |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checklist-flat |  |  | checklist | ITP 07 - Subsoil & Subgrade drainage | itp |  |  |  | Yes | ITP 07 - Subsoil & Subgrade drainage | 94167253-891c-4a65-a9c5-13a1ebdc484d
checkpoint-status |  |  | checkpoint | 1 - Tests
label | be6c06c6-2dc2-5d0e-be83-92fead1c7c66 |  | note | Activity TASK -
label | a7ff4ca9-7610-5a89-9c56-beaf8f075e79 |  | note | • Refer to SELECTIONS for test acceptance requirements. All sampling and testing shall be undertaken by IANZ accredited soil technicians.
label | 6783bb6f-b5e8-51d5-882d-215c219aca9f |  | note | • Alternatively, suitably experienced staff may be considered with express approval from the engineer.
label | 40f2a861-675a-5bd8-93ab-e0e875e40026 |  | note | • Methods of testing soil to NZS 4402.2.1(Determination of water content), NZS 4402.4.1.1(Dry density/water content), NZS 4402.5.1.1 (Soil Density), NZS 4402.5.1.3 (In Situ Density), NZS 4402.6.1.3(CBR In situ), and the Manual of Soil Laboratory Testing Vol 2, section 10.6. by KL Head. NZS 4407, test methods for aggregates; 3.6, 3.7, 3.8, 3.10, 3.11. Benkelman Beam test to TNZ T/1.
label | c5fe9df4-10f9-5912-9c60-d6076f5b1453 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 6f52152c-6e78-5afb-a5cc-8bd668acf6fa |  | note | FREQUENCY - Ad-hoc.
label | f6e069ed-2dd7-5279-accc-6163e990723e |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 2 - Basecourse Aggregate
label | 3fd22848-4f08-56ce-bf66-a2d2a19a5ac2 |  | note | Activity TASK -
label | 8ddbeddb-eb3b-54b3-924c-10525311fa7b |  | note | • Ensure the sub-basecourse for unbound granular pavement construction complies with the following Sub-basecourse criteria in all respects for all pavement.
label | 08accf73-262a-5b67-b1b0-a0f8e5974618 |  | note | • Comply with the following;
label | ecb93485-5e0d-5cf8-9da6-9127e7a55894 |  | note | – Crushing resistance minimum 200kN for sedimentary rock, and 130kN for other rock types.
label | 4396c4d3-c42a-52fa-975e-be6ebe81914b |  | note | – Weathering quality minimum AA, AB, AC, BA, BB, or CA.
label | 99998fa2-1be7-5425-9d57-c68078612fd9 |  | note | – Sand equivalent minimum 40.
label | 2edb7e59-eb24-5112-9592-08069a024a62 |  | note | – Permeability greater than 0.0001 m/s. - The three aggregate fractions between 37.5mm and 4.75mm sieves to have not less than 70% by weight, and have two or more broken faces- Grading which falls within the table below.
label | d1150acd-f82b-52ca-8dbf-074892063e8c |  | note | Acceptance Criteria -
label | b353c99b-4d02-5876-9d2a-4a77eb16d7a3 |  | note | Onsite inspection by Project Engineer/Project Manager.
label | 796d2975-e5df-5c2e-a79e-eaa6d3794be9 |  | note | • Particle Size Distribution
label | 392562e5-fab1-5317-84b0-78bb093eb717 |  | note | • % Passing by mass % passing by mass
label | 4d488f9c-e8c1-5e46-b004-1e2ca1238f7c |  | note | ○ Sieve Size/GAP 65/GAP40
label | 3b5351b1-c885-53a5-a3d9-3f020cf065c9 |  | note | ○ 65mm / 100 /100
label | 7d6f219c-e11f-5d64-812e-c408844455e0 |  | note | ○ 37.5mm / 80-90 / 100
label | f1adcc92-ce9f-54a4-8f90-529a938bb925 |  | note | ○ 19.0mm / 53-65 / 66-81
label | da242ea6-3654-5939-8a88-0c56162cf0d0 |  | note | ○ 9.5mm / 32-48 / 43-57
label | 520eef16-b64d-5584-935d-ee9296ff8745 |  | note | ○ 4.74mm / 20-35 / 28-43
label | af159d28-38d4-58ef-87ea-013b4f5eb21b |  | note | ○ 2.36mm / 12-25 / 19-33
label | 4f1cfb93-7a24-5663-ae4b-8e117542595f |  | note | ○ 1.18mm / 7-18 / 12-25
label | 3c66448b-81dc-5911-867d-8d0303cdab8d |  | note | ○ 300μm / 3-10 / 3-14
label | b66872a4-6371-596a-ba78-c4b4a9e1414a |  | note | ○ 75μm / 1-5 / 1-7
label | d16532b8-9fd4-53f7-84f5-a53d25386a02 |  | note | FREQUENCY - Ad-hoc
label | b19f140f-91c1-5e7a-bdef-bc7c85f3fd6f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery Dockett
label | ae7ff53c-bece-567e-bc36-ea981f3cb979 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 3 - Subbase Preparation
label | 39fb254d-126b-57be-a1a2-edeb322fd782 |  | note | Activity TASK -
label | 87692879-6840-5fff-981d-42267ccd4b70 |  | note | • Spread and compact sub-base-course aggregate or base-course on the compacted subgrade within 48 hours of the sub-grade being prepared and approved by the engineer.
label | e75db210-920a-5113-9cdf-a7aa0552e8af |  | note | • If rain should fall after the sub-grade has been approved and before the placing of the material, then do not place material until further approval from the Engineer has been given.
label | f5640946-e736-567b-846d-3c2f5c510542 |  | note | • Ensure the sub-grade conforms to the levels and grades before application of any aggregate.
label | a2b6ef04-3f05-5902-9fc4-942b0e1e3f61 |  | note | • Should pot-holes or ravelling develop in the subgrade, scarify the affected area, add approved material and re-compact in its place to the satisfaction of the Engineer.
label | e39cd1f3-c95a-5ff0-b5a8-b8184026f0ac |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 0a4715d2-7d2f-5da4-a209-06ae013f9e27 |  | note | FREQUENCY - Ad-hoc
label | 7332341a-62f8-5196-8f8d-c959a6b8eb45 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence to Project Manager
label | 5d8a5238-7a50-50d6-bb56-ef892b8dbd87 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 4 - Sub-Base course placement
label | 52d5af7d-1b50-56c5-b7e5-88bfa0c8a914 |  | note | Activity TASK -
label | 8b54c358-ccbd-5f85-8e78-54a71a0debf0 |  | note | • Do not lay sub-basecourse until the subgrade meets acceptance criteria.
label | cc7ebfcb-6328-5815-9f81-6445ec58d6ea |  | note | • Spread sub-basecourse aggregate on the prepared subgrade and compact as specified for basecourse aggregate.
label | e5da0c98-462d-55c9-8e4b-fa862e3c07f2 |  | note | • Compact in layers to TNZ B/02(Specification for construction of unbound Granular pavement layers) After compaction, finish the sub-basecourse surface to the required levels and grades as specified on the design drawings.
label | 75c33f61-10a4-54a7-a1c3-b18fe02f8222 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 3da21ee7-4522-5778-8f6a-4eead9229476 |  | note | FREQUENCY - Ongoing
label | 450620e7-e4a9-58fe-b33e-456443912e3e |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Project Engineer/Project manager
label | a3597d1e-4221-5ac2-b107-b8a54f930ca4 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 5 - Base Course Placement
label | 378967bb-5c7d-5391-8fcb-dee477d92c4d |  | note | Activity TASK -
label | 6fc17a50-e264-559a-b6e6-73350d800e4c |  | note | • Do not lay basecourse until the sub-base meets density and deflection requirements.
label | 57fcb23e-a669-5004-9e49-3d02199cbb70 |  | note | • Place the basecourse aggregate on the prepared sub-grade or sub-basecourse in layers without segregation and compact in layers as specified in TNZ B/02, (Specification for construction of unbound Granular pavement layers) except where a compacted layer of 150mm or less is required. In this case place the material in a single layer.
label | b11054d6-5d19-518a-9657-e8fb64d6bb0b |  | note | • Place the layers so that the compacted surface complies with the levels and grades shown on the design drawings.
label | ffe3e8a4-5f52-5bcd-8861-cbaaf665ad30 |  | note | • Restrict the laying procedure to essential shaping and final trimming, with minimum working of the final surface to achieve the specified aggregate density.
label | 044dd52e-b0ec-52e2-a7af-788579f2db72 |  | note | • Keep the surface of each compacted layer moist until covered with the next layer. Compact each layer of the aggregate by multiple passes of a smooth steel wheeled roller or suitable vibrating roller as selected by the contractor.
label | 67731935-729c-56b7-b492-148e96cfd645 |  | note | • Do not use alternative compaction equipment without specific approval from the engineer.
label | 5e83634a-b53c-5fa9-a449-cf4058cf8a30 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | a4642475-27fe-5c1a-952f-12cc7e36a3d1 |  | note | FREQUENCY - Ongoing
label | dd747d82-6e41-5b97-84be-283e0d9c1184 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Project Engineer/Project manager
label | 215065e8-0857-53bc-a0f3-8180c451379a |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 6 - Surface Finish
label | 2646cb64-e527-5977-9baa-3eeedf9e8ba2 |  | note | Activity TASK -
label | f541c489-5edd-5727-93ae-2cf902856c1c |  | note | • Finish the surface of the basecourse aggregate by blading or with the appropriate equipment as approved by the engineer.
label | 50dd8e11-45e3-56ff-9f9d-3fb800f97f85 |  | note | • Should an open textured portion occur on the top of the final compacted basecourse surface, scarify the area to a depth of 72mm, add new material, and blend and re-compact the layer to achieve the required grade. If the finished surface is above the plan grade, cut back to grade and rerolled.
label | 979c2d2e-72b0-597f-b3d8-f3019f0ea0a8 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | c1af12c4-7b4f-519b-a52f-40f9a69ab0c8 |  | note | FREQUENCY - Ongoing
label | aa80c3fa-2964-508f-9b15-381bfbf0b5cc |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 7096d01c-da2f-5bd7-b71f-c045d21ce2e2 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 7 - Maintain The Surface
label | 8914caf1-9b74-509a-929f-66ad55aaf210 |  | note | Activity TASK -
label | 1d62a9ef-5cb7-561c-9615-27d61ebeda33 |  | note | • Maintain the finished aggregate surface to the specified levels and grades by watering as required, blading, planning, rolling and by taking appropriate measures to ensure the even distribution of traffic.
label | f4e7c011-0502-59eb-8749-2cf47184f5e5 |  | note | • Ensure that the surface of the basecourse does not pot-hole, ravel, rut, or become uneven.
label | aa18cf3e-9d50-5e0d-9138-78496245b969 |  | note | • If this happens, patch the surface with suitable aggregate and completely scarify and recompact.
label | 7dd7514e-17ad-5ede-a378-549509cd77cc |  | note | • Maintain the surface until the end of the Defects Liability Period, or until such time as the sealing and surfacing material is placed in accordance with the contract requirements.
label | 994d5f93-8058-56eb-ba6f-901c9977ff4b |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 70caa363-9b7d-5e57-9aa2-1f6d85330801 |  | note | FREQUENCY - Ongoing
label | c70610db-12a4-5e3d-ab76-52607eacdf04 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | 00f17082-9f10-5fd3-9699-8720728d11c9 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 8 - Final inspection and Testing
label | d9828f26-d8c5-5397-9ef4-6b9b5c825d1a |  | note | Activity TASK - No point in the general basecourse surface shall vary more than 10mm from either a 3.0m straight-edge laid parallel to the centreline of the road, or from a cross section camber board placed at right angles to the centreline of the road. No part of the basecourse shall have depressions that would hold water.
label | 68c6cb17-eae7-585a-8ed5-d3611dbd7dcb |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 694e44a5-735f-52ab-b5a7-0d3f57ad3e90 |  | note | FREQUENCY - AD-hoc
label | d291f1b1-916b-5a38-997a-b0cce61d5d89 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Project Engineer/Project manager
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 9 - Pre-sealing requirements
label | fd8a8589-accd-5278-b322-56a13267c61a |  | note | Activity TASK -
label | a7851411-f579-5c48-b1df-6473b5f8bec7 |  | note | • The degree of saturation shall be determined on the completed basecourse to TNZ B/02,12 (Specification for construction of unbound Granular pavement layers), Do not apply the seal coat unless the water content at each test point of the basecourse layer is such that the degree of saturation is less than 80%.
label | 97bd957b-cc56-5608-899c-21dabbf5e706 |  | note | • Further testing shall be undertaken to determine the degree of saturation should any of the following occur:
label | e5ab30c8-bb45-50ef-9975-c46f9320507b |  | note | – If there are any failed results.
label | cd238b15-4c80-58fa-acc5-a3487b5cdf71 |  | note | – Where there has been a delay in sealing for more than 12 hours.
label | 7471966f-1013-59ea-9855-71b8d3ec562a |  | note | – Where there has been significant rainfall between pavement testing and sealing. - As directed by the pavement(road) designer.
label | aa366319-b893-57dc-b594-c83dc6dc5dba |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 84316949-3e39-526b-923d-3b55c3d89cb0 |  | note | FREQUENCY - Ongoing
label | 78b63d68-da36-5b52-871e-9cb18db0cb89 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | afa58aa5-2e84-5a46-83df-4141d0a84cc4 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 10 - Aggregate quality at the frequency in the table below.
label | a3554fc9-33bd-5a47-b9fc-557759bc6c77 |  | note | Activity TASK -
label | 6f2914c9-77d9-5ffd-bff3-828b084713e4 |  | note | • Test Minimum Test Frequency:
label | 764308bb-9b3e-5f57-9582-ab38be577954 |  | note | ○ Crushing Resistance 1 test per 10,000m³,
label | a80b9f38-508d-5e0f-ac8d-662f6ecc927c |  | note | ○ WQI (Weathering Quality Index) 1 test per 10,000m³,
label | ec3e7383-ca12-5ad5-af5b-dcbfcb39ce44 |  | note | ○ Soaked CBR (Basecourse only)
label | 53e1f509-b53a-5d30-987d-8e219739e900 |  | note | ○ 1 test per 10,000m³,
label | ae0055f4-3eb7-5dc9-b9d2-a357ef9b5fda |  | note | • Particle Size Distribution
label | b7aad3af-8c7b-5416-aeeb-6216b4953390 |  | note | ○ For stockpiles larger than 4,000m³
label | c4e6dc7b-4acf-5eea-b6d5-f3820b092a7c |  | note | ○ Sand equivalent 1 test per 1,000m³
label | 762a7935-8b9a-59fe-85ed-7394d82b29c0 |  | note | ○ Broken Faces For stockpiles smaller than 4,000m³
label | 1f2fa658-e605-5db3-a10c-c1d0bc868bd0 |  | note | Acceptance Criteria -
label | 175f1514-e53e-5bb1-8156-d386283a1392 |  | note | • Onsite inspection by Project Engineer/Project Manager.
label | 388efdc6-1fcf-5365-89f5-830b06581f63 |  | note | • Minimum Test Frequency for each 20 linear meter for each lane
label | 7cc9c1e1-31dc-5fee-bebb-7ed94d5ae34b |  | note | • Acceptance Values (Sub-basecourse ≥95% mean / ≥92% minimum)
label | 114272df-241a-5d2a-85d9-23d80d9e8403 |  | note | • Accepted Values (Base course ≥98% mean / ≥95% minimum)
label | 33f039c1-1efe-5ef4-877e-d09055b8f9dd |  | note | FREQUENCY - Ongoing
label | 2c79ec28-36ed-5178-ac58-56c1ddb31c54 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Reporting to Client Engineer / Project Manager.
label | a34346c7-149c-58fa-b91a-88a5db59338d |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
label | 895b84e8-0b92-5fb9-a33d-75d26982a022 |  | note
checklist-flat |  |  | checklist | ITP 03 - Bulk Earthworks | itp |  |  |  | Yes | ITP 03 - Bulk Earthworks | ed89a8f8-3151-4a97-809d-ecd7372f02d1
checkpoint-status |  |  | checkpoint | 1 - Winter Work
label | c941841e-7fe7-51af-b1f1-1aafc6e61895 |  | note | Activity TASK -
label | be235037-a998-5ac4-beb4-9c405090b3ae |  | note | • Where the Contractor intends to undertake earthworks outside the permitted earthworks season and not covered by existing consents, the Contractor is responsible for obtaining approval from the relevant authority(s) to undertake that work.
label | 91fc8b88-c98e-5a53-9ce6-546bcbacbd89 |  | note | • Select backfill material for suitability of placement and compaction during winter conditions. Backfill to meet compaction criteria without the requirement for drying, and not be excessively sensitive to erosion.
label | f4dc5bdd-8b5a-5c66-95e1-e535a0e8436b |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 65b3c5cf-6090-5373-aeb3-95180baf64e0 |  | note | FREQUENCY - Ad-hoc
label | b8ec7d39-39bc-51df-971c-278f34aa1f88 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signed Delivery Note and checklist
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 2 - Testing
label | b9e0c92a-ba5d-53fb-8fa1-3ca7a24c93fe |  | note | Activity TASK -
label | 1ad89161-f58a-55ca-9b55-d4c60e48465d |  | note | • Test all earth-Fills other than those specifically identified as uncontrolled fill in accordance with NZS 4431 using standard testing procedures as set out in NZS 4402.
label | 781babde-54c3-5f73-b0a7-a252132edec7 |  | note | • In any situation where the engineer is not satisfied that the plant operator is operating the test equipment efficiently, In order to test the particular material the engineer may at the contractors cost arrange for an independent operator and/or item of equipment to be brought to the site to undertake the test.
label | 54a47de2-b048-5841-b4c1-dc898eeb8b84 |  | note | • To permit the engineer to conduct any inspections and tests required with complete safety and accuracy of test results, work maybe interrupted and/or operations diverted and surface materials removed to expose soils at the levels too inspected required at no extra cost.
label | 33728915-1081-58c6-aa11-2b86830716f4 |  | note | Acceptance Criteria -
label | 0db66634-5540-5cef-a38a-7ad25911e0c8 |  | note | • Inspected by Project Engineer/Project manager
label | 179b2a96-368c-5094-863b-e0ef6d01b488 |  | note | • Test Methods
label | 016c923c-3d7e-5469-8459-97f0b9f057fb |  | note | – NZS4402.2.1, (Water Content)
label | 0599628d-55ce-5b7a-b0d0-f6a14d34ae60 |  | note | – NZS4402.4.1.1, (Dry Density/Water Content)
label | c9614b2e-6d29-5ece-974a-2e27e53c3617 |  | note | – NZS4402.4.1.3, (Dry Density)
label | fe0c5f78-f6d1-55e9-8fe9-fd35c04ffcf9 |  | note | – NZS 4402.5.1.1, (In Situ Density)
label | 566e7d7a-2bfb-54e0-a561-9733094e02d0 |  | note | – NZS 4402.5.1.3, (In Situ Density)
label | 340052d2-e042-5ad1-ab6e-8b8b33214c83 |  | note | – NZS 4402.6.1.3, (Soil Strength Test)
label | cf258b52-9d05-5ae7-99f2-859ead8427f4 |  | note | – NZS4402.6.5.2, (Soil Strength Test)
label | 9bbfe348-ed65-5f27-8aaa-f66725bf008a |  | note | – TNZ T/1, (Benkelman Beam test)
label | 71616318-2c4f-5441-84f4-ffff94747e06 |  | note | – NZS4407 3.6 / 3.7 / 3.8 / 3.9 / 3.10 / 3.11 / 3.15 (Testing Aggregates)
label | 768727b0-08a8-57c8-829d-78eeaf258377 |  | note | FREQUENCY - Prior to Commencing
label | 0bae08f6-b4c6-52bb-a050-b5c338e1442d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Results of fill tested.
label | c3241ca8-2d02-5113-96c9-8ea9341bee8a |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 3 - Inspections
label | 7d242b51-be87-558e-927b-8037802da445 |  | note | Activity TASK -
label | 754f57fa-7df8-5458-9ba5-987074396480 |  | note | • After setting out of clearing area and prior to all clearing and stripping, and before the placing of any fill material on that ground.
label | 47cac55d-1b86-5f75-929d-dd82741b5504 |  | note | • After all topsoil has been removed prior to earthworks.
label | 87c784aa-2b94-5031-89b4-a1d3c858cd9c |  | note | • Inspection that all unsuitable materials have been removed prior to filling
label | 5c0d25d3-aecd-51f0-82ec-7afa2bfdcdfa |  | note | • After any drain has been constructed, and before that drain is covered by fill material.
label | 565a1591-d43f-5022-9443-fa7b77c8cf84 |  | note | • Batters and benches prior to filling.
label | 11e43649-6041-5d0c-b921-e896cafa5978 |  | note | • Shape, level and consistency of subgrade and associated drainage.
label | 515c9501-10c4-52e0-85a4-bafa5f94f67b |  | note | • As necessary to assess the standard of fill material and its compaction.
label | 669cfce7-c87e-565c-987c-3b86e13e34f1 |  | note | • As necessary to carry out check tests of the soil properties, moisture content and the standard of compaction being achieved in the fill, confirm it meets the requirements of NZS4431.
label | 8d1e715e-623a-591c-9e27-e9bba4489201 |  | note | • Finished surfaces prior to topsoiling.
label | 39b4ed2f-b379-58b0-a01f-4813816851d6 |  | note | • Completed topsoil prior to final leveling and seeding.
label | 11b41342-a44e-5ab6-a3e6-373c015bdfa2 |  | note | • Arrange fill construction to accommodate testing to be carried out as work proceeds.
label | e37636c3-4667-53d9-97a6-62a5c296191c |  | note | • Provide excavating equipment and remove material from above the test level (If necessary) and subsequently backfilled
label | ab0cb4d1-baf4-5d3f-b95f-8b40fd8c1a9b |  | note | Acceptance Criteria - Facilitate inspection by the engineer at all times during construction of the following activities.
label | ff3bd90c-f19f-590f-9c32-60bfd7971880 |  | note | FREQUENCY - Every new section of Kerb and channel.
label | 4f6ae63d-2c08-5854-bde3-3592a1f47c7d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence with Comments to Client Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 4 - Management Plan
label | 80894492-0160-50a1-ac7d-5911e39abff3 |  | note | Activity TASK -
label | 93ca8374-793e-5154-a272-9cd988115df5 |  | note | • Illustrate by tabulation and graphical presentation the proposed earthworks sequence.
label | f21a7f14-0ac4-5972-b535-b7a7604add6d |  | note | • Monitor volumes in cut and fill areas, including unsuitable materials and disposal areas for all earthworks.
label | b9dccfe4-bd2c-53e3-8d62-5192a6977551 |  | note | • Report earthworks volume monitoring results and the actions taken and proposed to ensure optimal rate of construction without compromising the standards required by this specification.
label | 8ec0a810-3d11-5cb1-a6aa-e05410f7c7f5 |  | note | • Sow how the suitability of materials will be assessed and how required treatment will be determined, in advance of earthwork operations
label | ed768923-a415-50ac-981c-60f441cc55a1 |  | note | • Show how environmental compliance requirement affect earthworks operations and how these are to be satisfied.
label | 0436b857-3433-5aae-8cab-a842e9e4a9ea |  | note | Acceptance Criteria - Visual Inspection/ Asbuilts
label | 7d254adc-412e-5db4-afaf-ac326c50f1d2 |  | note | FREQUENCY - Ongoing
label | 9c8e48a7-143d-5f84-be95-24424bc921f7 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence coupled with Reporting to Client Engineer / Project Manager.
label | c4ced110-aedc-58ae-884f-fb92a2759f8f |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 5 - Clearing
label | a1eef564-c101-5058-b6a3-ad0eb2924e79 |  | note | Activity TASK -
label | 1078ad59-60ec-5caa-bc47-c2b7a54cbc31 |  | note | • Remove all rubbish, trees, stumps, fences, obstacles, vegetation, roots, turf, organic matter and other deleterious or unwanted material from the areas of operation.
label | 05a704de-80ea-55d8-9f2b-51eea370faf1 |  | note | • Include all above and below ground structures and fences within the area of the site to be worked.
label | 3424d9ea-b17e-5b6b-9458-84b6986cd227 |  | note | • Remove tree stumps such that no roots exceeding 100mm remain. Stumps that are chipped shall have chipping material removed from site.
label | b32d0534-db2a-5a19-803d-ec3fa8a9ceba |  | note | • Materials of value shall be salvaged and stacked as directed on the site. They remain the property of the principal/landowner unless otherwise stated.
label | a8119100-1ede-5ffa-8f22-c2ebea151d15 |  | note | • Cart and dispose of all unwanted materials, vegetation and debris to an approved landfill. Burning or burying waste materials is not permitted.
label | 1cdd7d64-12b2-5e39-9702-4f1b943587ee |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | 2ba22ce3-e5ed-5166-9630-79aa18cc5486 |  | note | FREQUENCY - Ongoing
label | 46e9eebe-87d4-53de-baaa-9cd0beb3710a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photo Evidence coupled with Reporting to Client Engineer / Project Manager.
label | a3dff52e-5278-51b2-b179-40a1ea512438 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 6 - Benching
label | fd90f76f-5644-5e2d-abc1-0742dfd54a1f |  | note | Activity TASK - Benching to TNZ F/1 unless stated otherwise on the drawings. Where shown on the drawings, or where seepage is encountered, bench the ground and install subsoil drains to collect the seepage and discharge it to an approved location clear of the fill.
label | 2c6e88c9-6bdd-594d-aa2d-8db31a00a8c7 |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 9af217d6-6884-5457-bc46-f243c79f2024 |  | note | FREQUENCY - AD-hoc
label | de78340e-e9f5-562b-b3a2-0c441079e4c0 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 7 - Preparation
label | 75486550-f094-5253-b4f1-99f24c40bb3e |  | note | Activity TASK -
label | ac19a743-9566-5bce-b146-0062889df1eb |  | note | • Proof rolls any prepared surface to identify any soft sports in the ground that may be removed on instruction by the engineer.
label | 830f3f7d-15ac-5a94-b52d-139c931ec9e5 |  | note | • Prior to any fill placement, compact the exposed existing natural ground surface to a depth of 150mm to achieve compaction at least equal to that specified for the new fill material.
label | 6e2f63c2-5392-5fda-afda-3fa729127b5c |  | note | • If necessary, to meet the requirements, blade the ground until it is uniform, free of large lumps and brought to a suitable moisture content prior to compaction.
label | bc4babc1-79d2-5bfb-8bff-cd631b06dfea |  | note | • If there is a delay between surface preparation and fill placement, the surface shall be protected against drying, wetting or erosion.
label | 9457cc79-0604-5550-a4ae-69f90b12f759 |  | note | • Prior to placement of fill, in-situ cohesive material shall be tested with a hand-held shear vane in accordance with the procedures outlined in the NZ geotechnical society guidelines for hand shear vane test, and classified into the following end uses.
label | 728e5c8f-5161-52fa-b1d0-8d48e1ae40f3 |  | note | • In situ materials to have fill placed over shall be undercut and replaced with engineering fill where the in-situ material fails to meet the following criteria.
label | bec7b14a-c2bb-5039-bd3e-ca4bc71b6b29 |  | note | Acceptance Criteria -
label | cab676c6-4265-5722-b03b-4a4aba40f0d7 |  | note | • On-site inspection and acceptance by Engineer.
label | affef468-e682-5783-8155-cafde88f3176 |  | note | • In situ Vane Shear Strength
label | 7ded3aa1-97d8-5947-a077-653899f08529 |  | note | • Less than 40kPa or as specified on the drawings. (Proposed Fill = Waste)
label | a381f24a-dca0-563d-932f-60b679d87a48 |  | note | • 40kPa – 70kPa (Proposed Fill = Landscape, bunds and surcharge fill)
label | 9aa0e428-2fbd-53dc-a885-bed367df4592 |  | note | • Greater then 70kPa (Proposed fill = Engineered and additional fill)
label | b2c041cc-8ab8-5ba8-b0c4-546f0e1fe658 |  | note | (All granular cut is expected to be suitable for use as engineered fill, subject to confirmation that is suitably graded material)
label | 799463d6-6479-5091-91b1-0222f014f6a7 |  | note | FREQUENCY - Prior to fill placement
label | fdc5b6be-2513-5c19-99be-2c8fab5c5b24 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 8 - Undercut to Waste
label | 76b13438-a754-56d6-8812-fdc09000e055 |  | note | Activity TASK - Undercut to waste materials are defined as materials below design sub-grade level that have an in-situ Vane shear strength of less than 40kPa measured using a hand-held shear vane in accordance with the NZ geotechnical society guidelines for hand held share vane test.
label | faf451bd-13f0-5e52-ac07-0f84b369873b |  | note | Acceptance Criteria -
label | 676736f1-495a-5de8-b8e3-b115d5a30a3f |  | note | • On-site inspection and acceptance by Engineer.
label | e5f741a8-b588-5640-a118-e3ca3333d4e4 |  | note | • Hand Held Shear Vane Test
label | 34fa9620-5363-5887-a188-c3ade324d229 |  | note | FREQUENCY - Pre undercut
label | 13a45669-5add-5ba2-9a49-05a483d1b863 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Signoff by Engineer.
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 9 - Placing fill Material
label | 2d9a940a-6562-5820-9df3-52d1c8b66041 |  | note | Activity TASK -
label | 75b677e3-0810-5376-bb02-7c982e242e74 |  | note | • The method of excavation, transport and depositing of fill material shall ensure the fill is as uniform a mixture as possible.
label | 8f42284e-e3e3-5607-a13b-fd20f7f45d12 |  | note | • Vary the path of transportation plant over the top compacting fill surface. Place fill in a systematic manner, with near horizontal layers of uniform thickness of materials being deposited progressively across the full area of a fill.
label | f122f998-6967-5d4b-b11f-78d7ccba224d |  | note | • The uncompacted thickness of each layer shall be no greater than 200mm, and shall be limited to ensure that the bottom of each layer can be adequately compacted.
label | dfed8a7d-26c4-539c-bcc5-e2ae71c139e0 |  | note | • Fill batter’s steeper than 1 vertical to 4 horizonal shall be overfilled and subsequently trimmed to the design lines. This is required to ensure that the specified compaction standards are achieved over the full design embankment cross section.
label | 3f76a4d4-e7f6-5d25-adbd-51dd9e266cae |  | note | • Before any loose layer of fill material is compacted, break up the soil so that it is free of lumps which exceed 150mm
label | a58f1d28-5ca3-541c-a834-6593324f4e41 |  | note | Acceptance Criteria - Onsite inspection by Project Engineer/Project Manager.
label | fa020bed-4e37-56ec-886e-7f75fda3d8e1 |  | note | FREQUENCY - Ongoing
label | 298fc4a8-53b2-51cf-a48d-7bd59c0e9bdf |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection of material by Project engineer / Site supervisor
label | 529f1b39-01bb-5826-8f30-13febe513190 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
checkpoint-status |  |  | checkpoint | 10 - Compacting
label | 2e51166d-acb9-578a-8804-07a55ea6d6de |  | note | Activity TASK -
label | 8897de88-b4cd-5222-877d-11f4a8428af5 |  | note | • Compact fill accordance with TNZ F/1 (1997) together with the following additional clauses.
label | bae620a1-50af-5895-ac20-a4c6566a2501 |  | note | • Compact each layer of fill material to at least the specified density, using plant specifically designed for compaction of the material classification following patterns of parallel tracks which work progressively across the surface of the fill, with sufficient passes to ensure the specified compaction is achieved.
label | 8256764a-7f16-59cc-8756-78380beac57e |  | note | • Select compaction plant to consistently achieve the specified standard of compaction over the entire area of fill. Generally vibrating rollers will be required for non-cohesive materials and tamping type taper foot rollers for cohesive materials. Compaction plant shall be separate from the used for earthmoving.
label | 0cc34470-2463-5669-a0a4-2c2b6f2e6576 |  | note | Acceptance Criteria -
label | f587f232-23bd-5deb-a302-1d8f3e0bd381 |  | note | • Testing to be carried out by a laboratory with IANZ accreditation for the specific tests. General Fill areas and more than 500mm below road and parking area subgrades in cohesive soils.
label | 98d3a6c7-87ad-5860-bc0b-fda2ad0a49cc |  | note | – Average undrained shear strength (by hand vane) of 130 kPa in any group of 10 tests with no single test less than 90 kPa.
label | 3f916423-12fd-5533-855b-78925c9f3ee4 |  | note | – Average air voids of not more than 10% in any group of 10 tests with no single test exceeding 12%. Within 500mm of road and parking area subgrades, in cohesive soils, average undrained sheer strength (Hand Vane) of 140kPa in any group of 10 tests with no single test less then 100kPa.
label | 53fe3e7a-8ae6-57b9-8b14-bbf5dbb3a0ca |  | note | – Average air voids of not more than 8% in any group of 10 tests with no single test exceeding 10%.
label | 6c43a595-ca9d-5a06-8939-89cfe79881ed |  | note | – Soaked CBR not less than 5. One test per material type (Compacted to NZS 4402(1986) Test 4.1.1). Dry density not less than 92% min and 95 average of the maximum dry density of the soil as determine by NZS4402.4.1.3 (Continue Compacting Item -14)
label | 7ed6f377-9ab0-546d-8eac-eb622eb99e62 |  | note | FREQUENCY - Ongoing
label | b9d6cfe2-4369-56af-83dd-97554008438f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test results send to Engineer / Project manager
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 11 - Compacting
label | 6f824119-20ff-5227-90c1-b79e5e8b22ad |  | note | Activity TASK -
label | 56cc176c-bb4a-5f41-bf18-67fa8e5c20c4 |  | note | • Testing to NZS 4407:2015 test 4.2 (NDM backscatter)
label | 4f917d9d-1e51-5444-872f-ba052db64b9a |  | note | • As well as accomplishing the minimum standard of compaction as set out above, the contractor must ensure that the fill is not over-compacted to the extent that weaving of the fill is produced.
label | 71d9f40a-3608-5dcb-9c7a-5b8373910964 |  | note | • In any areas of fill where tests show that the required compaction has not been obtained, the contractor shall, at his own expense, remove the faulty material and carry out such compaction with or without adjustment of moisture content, as may be necessary to comply with the specification.
label | 9dc6dd22-79d2-5e62-8ade-2a4c86da07dc |  | note | Acceptance Criteria -
label | e44fcffd-7479-5344-94c4-2c0b8093dbd6 |  | note | • Test Frequency shall be one test per 1000m3 and not less than lifts of between 0.6m and 1.0m depth of fill placed, with the additional criteria that the first 1000m3 of fill placed shall have 3 sets of tests and all fill shall have a min of 5 sets of tests.
label | 2063a584-7a94-530f-ab88-fcd1f16d0a8f |  | note | • Differential settlement shall not exceed 25mm over 6.0m horizontally.
label | aa41ba63-d2a1-5723-b620-a985ed2fa34b |  | note | • The methods adopted for cut and fill operations shall be such as to maintain the moisture content as near as possible to optimum and between the limits off 2% below and 4% above optimum moisture content.
label | db62bd67-de41-541c-acf6-88bbef387806 |  | note | FREQUENCY - Ongoing
label | 4c8b5700-77e6-5e8a-86c7-dba6ee46cc0b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test results send to Engineer / Project manager
holdpoint |  |  | signoff | CRITICAL HOLD POINT - Hold Point
checkpoint-status |  |  | checkpoint | 12 - Erosion and sediment Control
label | e8d06cd9-67fc-5417-bdb6-af033f9edce0 |  | note | Activity TASK -
label | c2b69087-59d1-5722-ab11-e93c596710d0 |  | note | • Inspect all the erosion and sediment control measures not less than weekly, and/or immediately before and after any significant rainfall event while carrying out earthworks, and at least monthly or after any significant rainfall event, between earthwork.
label | 1c7d00d7-ea89-5495-8cc9-cbec5538bd6f |  | note | • In Addition, whenever a significant storm event is forecasted, inspect and repair all erosion and sediment control measures prior to storm event. (Including cleaning our sediment
label | 1f205db9-6e7f-5e35-a1b0-2be1186bc49f |  | note | Acceptance Criteria -
label | b6fcd0ef-ecef-5587-a780-e20f0962c790 |  | note | • Onsite inspection by Project Engineer/Project Manager.
label | c3ee9863-9d86-55d6-9e30-40a25e50e3e5 |  | note | • During inspections, determine and log the depth of sediment build up within the sediment retention ponds. Provide a copy of the log at the scheduled site meetings. Where the silt build up exceeds 15% of the total storage of the pond, clean out the pond of all silt and place silt over fill areas to dry and be incorporated in the fill.
label | 00b25d2e-6bdf-59a2-ad7d-24a067639bb9 |  | note | FREQUENCY - Ongoing
label | ea6d3bfa-d87f-5947-b723-08467691c43e |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Site inspections from Project Engineer / Project Manager
label | ca6c882d-a0d5-550a-897c-52da5a8f5873 |  | note | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - Internal Project Engineer / Project Manager
label | 1dec6601-ea5c-5fff-8ad3-9f54876234ea |  | note