## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP 08 - Pavement Construction | itp |  |  |  |  | ITP 08 - Pavement Construction
checkpoint | Preconstruction
label | SPECIFICATION REFERENCE - IFC Drawings
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Before Construction
label | ACCEPTANCE CRITERIA - IFC (Issued for Construction)
label | H
holdpoint | HOLD POINT
checkpoint | Sub-Basecourse Placement
label | SPECIFICATION REFERENCE - Spec - 8631 - 3.4
label | TEST REQUIRED - Signoff/ Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Before Construction of Sub-Basecourse
label | ACCEPTANCE CRITERIA - Ensure Subgrade meets all quality and control testing requirements of 8613 CONSTRUCTION TO FORMATION before placing basecourse
label | H
holdpoint | HOLD POINT
checkpoint | Base-Course Placement
label | SPECIFICATION REFERENCE - Spec - 8631 - 3.5
label | TEST REQUIRED - Signoff/ Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Before Construction of Basecourse
label | ACCEPTANCE CRITERIA - Ensure Sub-Basecourse meets all quality and control testing requirements before placing Basecourse
label | H
holdpoint | HOLD POINT
checkpoint | Aggregate Compliance
label | SPECIFICATION REFERENCE - 8621 - 2.1
label | TEST REQUIRED - Visual inspection
label | INSPECTION BY - UCC Rep & Engineer
label | TASK TIMING OR TASK FREQUENCY - Before & During Construction
label | ACCEPTANCE CRITERIA - >Crushing Resistance -1 test per 10,000m2
label | >Weathering Quality Index - 1 test per 10,000 m3
label | >Soaked CBR - 1 test per 10,000 m3
label | > Particle Size Distribution - For Stockpiles larger than 4000 m3
label | > Sand Equivalent - 1 test per 10,000 m3
label | > Broken Faces - For Stockpiles larger than 4000 m3
label | H
holdpoint | HOLD POINT
checkpoint | Aggregate Compliance (2)
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep & Engineer
label | TASK TIMING OR TASK FREQUENCY - Before Construction
label | ACCEPTANCE CRITERIA - Comply with following:
label | (a) Crushing resistance minimum 200kN for sedimentary rock, and 130kN for other rock types.
label | (b) Weathering Quality minimum AA, AB, AC, BA, BB or CA.
label | (c) Sand Equivalent minimum 40.
label | (d) Permeability greater than 0.0001 m/s.
label | (e) The Three aggregate fractions between 37.5mm and 4.75mm sieves to have not less than 70% by weigth, and have two or more broken faces.
label | (f) Grading which falls within table in the comments.
label | H
label | COMMENTS - Ensure the sub-basecourse for unbound granular pavement construction complies with following sub-basecourse criteria in all respects for all pavement.
label | Particle Size Distribution
label | _ ¦¦ % passing by mass ¦¦ % passing by mass
label | Sieve size: ¦¦ GAP 65 ¦¦ GAP 40
label | 65mm ¦¦ 100 ¦¦ 100
label | 37.5mm ¦¦ 80-90 ¦¦ 100
label | 19.0mm ¦¦ 53-65 ¦¦ 66-81
label | 9.5mm ¦¦ 32-48 ¦¦ 43-57
label | 4.74mm ¦¦ 20-35 ¦¦ 28-43
label | 2.36mm ¦¦ 12-25 ¦¦ 19-33
label | 1.18mm ¦¦ 7-18 ¦¦ 12-25
label | 300µm ¦¦ 3-10 ¦¦ 3-14
label | 75µm ¦¦ 1-5 ¦¦ 1-7
holdpoint | HOLD POINT
checkpoint | Construction of Pavement
label | SPECIFICATION REFERENCE - Spec - 8631 - 3.2 TNZ B/02 Drawings
label | INSPECTION BY - UCC Rep
label | ACCEPTANCE CRITERIA - Carry out all sub-basecourse and basecourse contruction to TNZ B/02
label | W
checkpoint | Stringline Checks Each Layer
label | SPECIFICATION REFERENCE - TNZ B/02 - 5.0
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pavement Surface every 20m
label | ACCEPTANCE CRITERIA -
label | ○ Width:
label | Unconstrained: -20mm +100mm
label | Constrained: Zero
label | ○ Vertical Without Concrete Channel:
label | Subbase: -25mm+5mm
label | Basecourse: -5mm+15mm
label | Vertical With Concrete Channel:
label | Subbase: -25mm +5mm
label | Basecourse: by lip of channel -5mm +5mm other areas -5mm +15mm
label | H
holdpoint | HOLD POINT
checkpoint | Surface Shape
label | SPECIFICATION REFERENCE - TNZ B/02 - 7.7
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Pavement Surface
label | ACCEPTANCE CRITERIA - No point in the surface shall vary by more than 10mm from a 3m straigh edge placed on the road with no depressions that allow water to pond where lateral or longitudinal fall is greater than 1%
label | W
checkpoint | Surface Finish
label | SPECIFICATION REFERENCE - TNZ B/02 - 7.8
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Pavement Surface
label | ACCEPTANCE CRITERIA - The Basecourse finish shall present a tightly consolidated surface when swept in particular:
label | – Large aggregate is exposed to the surface and held in place with a matrix of smaller aggregates
label | – Smaller aggregates held in place by fine material and the matrix does not displace under normal trafficing or sweeping
label | W
checkpoint | Lime/Cement Supply
label | SPECIFICATION REFERENCE - TNZ B5
label | TEST REQUIRED - Supplier Documentation
label | INSPECTION BY - Visual Inspection
label | TASK TIMING OR TASK FREQUENCY - QA sheet from the supplier.
label | ACCEPTANCE CRITERIA - Meets NZS 3122
label | W
checkpoint | Record Depth
label | SPECIFICATION REFERENCE - Email from Engineer
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Application rate shall be recorded for each run
label | ACCEPTANCE CRITERIA - Depth must be equal to 150mm
label | W
checkpoint | Application Rate
label | SPECIFICATION REFERENCE - Email from Engineer
label | TEST REQUIRED - Mat Test
label | INSPECTION BY - UCC Rep/ Engineer
label | TASK TIMING OR TASK FREQUENCY - Every 400m2
label | ACCEPTANCE CRITERIA - Within +- 0.5kg/m2 of the specified rate
label | W
checkpoint | Application Rate (2)
label | SPECIFICATION REFERENCE - Email from Engineer
label | TEST REQUIRED - Average Usage Test
label | INSPECTION BY - UCC Rep/ Engineer
label | TASK TIMING OR TASK FREQUENCY - Upon Emptying the spreader and bulk truck
label | ACCEPTANCE CRITERIA - Within +- 2.5% of the specified rate
label | W
checkpoint | Density (Sub-basecourse)
label | SPECIFICATION REFERENCE - TNZ - B/02 - 7.6
label | TEST REQUIRED - Compaction Testing
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Ever 20 Linear meters for each lane
label | ACCEPTANCE CRITERIA - Density >= 95% mean, Density >= 92% minimum
label | H
holdpoint | HOLD POINT
checkpoint | Density (Basecourse)
label | SPECIFICATION REFERENCE - TNZ - B/02 - 7.6
label | TEST REQUIRED - Compaction Testing
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Every 20 Linear meters for each lane
label | ACCEPTANCE CRITERIA - Density >= 98% mean, Density >= 95% minimum
label | H
holdpoint | HOLD POINT
checkpoint | Beams
label | SPECIFICATION REFERENCE - TNZ - T1
label | TEST REQUIRED - Deflection Testing
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Every 20 Linear meters for each lane
label | ACCEPTANCE CRITERIA - Subbase 1.8mm, Basecourse 1.2mm with Max of 1.6mm
label | H
holdpoint | HOLD POINT
checkpoint | Pre-Seal Inspection
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineers Rep/UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Prior to placement of subsequent pavement layers.
label | ACCEPTANCE CRITERIA - Before sealing inspect the base course is to the specified standard, correct crossfalls, all kerb & channel completed, to allow work of the required standard.
label | H
holdpoint | HOLD POINT
checkpoint | Presealing Requirements
label | SPECIFICATION REFERENCE - TNZ B/02
label | TEST REQUIRED - Degree of Saturation
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Carry out testing at a frequency of one test per 20m of traffic lane to be sealed
label | ACCEPTANCE CRITERIA - > 80% Saturation
label | H
label | COMMENTS - DO NOT apply seal coat unless water content at each test point of basecourse layer is such that degree of saturation is less than 80%
holdpoint | HOLD POINT
checkpoint | Seal Widths
label | SPECIFICATION REFERENCE - NCC Drawing - Typical Cross Section
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Marked Out Every 20m
label | ACCEPTANCE CRITERIA - Width of pavement to be 3.25m each lane or 6.5m overall
label | W
checkpoint | Material Properties - Grade 3 & 5 Sealing Chip
label | SPECIFICATION REFERENCE - First and Second Coat Chip Sealing
label | TEST REQUIRED - NZTA T10
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Each Application
label | ACCEPTANCE CRITERIA - Acceptance from the Engineer
label | H
holdpoint | HOLD POINT
checkpoint | Pavement Markings
label | SPECIFICATION REFERENCE - Spec. 16.0 NZTA M/7Design / IFC Drawings
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - After setout of permanent line markings.
label | ACCEPTANCE CRITERIA - Match Design
label | W
checkpoint | Weak Post Guardrail
label | SPECIFICATION REFERENCE - Design / IFC Drawings
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - All NU-Guard Guardrail
label | ACCEPTANCE CRITERIA - NZTA M23:2009 System with 12g W-Beam Guardrail and 2.67mm Thick Nucor Posts
label | W
checkpoint | Weak Post Guardrail Installation
label | SPECIFICATION REFERENCE - Design / IFC Drawings
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - Testing and installation as per manufacturers instructions
label | ACCEPTANCE CRITERIA - To be installed into compacted Engineered Fill (NZTA Spec M4 Materials compacted to NZTA B2 Spec) or insitu material confirmed as suitable to min. of 1200 deep
label | W
checkpoint | As-Builting
label | SPECIFICATION REFERENCE - 8613 - 1.6
label | INSPECTION BY - UCC Rep
label | TASK TIMING OR TASK FREQUENCY - At completion of the pavement and before completion of the defects notification period
label | ACCEPTANCE CRITERIA - Provide As-Built and RAMM records before Practical Completion:
label | – Plan showing Base-Course materials and depths
label | – RAMM data and completed database sheets for Council
holdpoint | HOLD POINT