## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: |  |  |  | B | Report by Breach | CM | Construction Manager
Contract Number: |  |  |  | C | Check | CR | Cust. Representative
Area/ Sub-System: |  | Lot ID Number: |  | D | Dimension Inspection | IP | Inspection Personnel
|  |  |  | E | Examine | MC | Material Controller
ITP Number: |  | Version: |  | H | Hold Point | OP | Operations Manager
ITP Description: |  |  |  | I | Inspection | PM | Project Manager
Discipline: |  |  |  | M | Monitor on Random Basis | PS | Project Supervisor
Specification: |  |  |  | O | Operation | QE | Quality Engineer
|  |  |  | R | Review | QM | QA Manager
Drawings: |  |  |  | S | Subcontractor | SP | Supervisor
|  |  |  | V | Visual Verification | ST | Superintendent
Prepared By: (Name) |  | Date: |  | W | Witness Point | SV | Surveyor
Quality Specified: | [5 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer | Name: |  | Signature: |  |  |  |  | Date:
Downer Approval | Name: |  | Signature: |  |  |  |  | Date:
Customer Approval | Name: |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1 | Capping Layer Compaction | Filling is to be carried out in horizontal even layers not exceeding 0.15m in loose thickness and is to be thoroughly compacted with appropriate equipment. Total thickness of the capping layer (existing and new material) is to be not less than 1 .0m after compaction at any point. | Density of at least 97% of maximum dry density with moisture content between OMC +2% and OMC + 4%. | Density Report | Tests to be done every 350m3 of fill using a nuclear densometer. 2x for every 10m x 5m area of capping | NDM Testing
2 | Capping Layer Air Voids | The air voids content of the capping layer shall be calculated for each density test. | Air voids shall not exceed 6% for each single test, and shall not exceed 5% for a running average of 5 consecutive tests. The air voids calculation using a nuclear densometer for a single test will comprise an average calculated from the results of 4 density measurements. Each measurement position shall be located by rotating the densometer about the density probe in 45 degree increments. The test area is to be trimmed level and smoothed below the compacted surface. | Density Report | 2x for every 10m x 5m area of capping | NDM Testing
3 | Undrained Strength of Capping Layer |  | Single test minimum value of 85kPa and a running average for 10 consecutive tests minimum value of 100kPa | Field Testing Document | Test shall be done on a 25m x 25m grid. A single test comprises an average of six readings from within a 1m square area. | Visual
4 | Permeability Test | Permeability Test on Capping Layer as per specifications | No greater then 1x10^-7m/s | Field Testing Document |  | Field Testing
5 | Capping Approval and Topsoiling | The capping layer is to be kept moist, as described above, until the topsoil layer has been placed over it, following an inspection and approval. The topsoil layer is to be lightly rolled. |  |  |  | Hold point
6 | Compaction Trial | A compaction trial is to be carried out using representative samples of the capping material before commencement of the capping layer construction to determine the compaction effort required to meet the specified density, undrained shear strength and air voids criteria. The compaction trial is to consist, as a minimum, of the construction of a 10m x 5m area of capping, constructed to the full make-up depth of 1 .0m. | For the trial to be considered successful it is to meet the criteria stated for 2 density and air voids tests, 5 shear vane tests and 1 permeability test. | Go ahead from NTRLBU |  | Hold point

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: