## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 1.0 PRE-CONSTRUCTION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 1.0 PRE-CONSTRUCTION
section | 1.0 PRE-CONSTRUCTION
checkpoint | 1.01 - Check IFC Drawings
label | DRAWING / SPECIFICATION REF.: Kiwirail – North Auckland Line Recovery 136km Construction Issue (Rev A)
label | SPECIFICATION DETAIL SUMMARY: Ensure latest revision is being used
label | ACCEPTANCE CRITERIA: Correct drawings
label | TEST SPEC AND FREQUENCY: Prior to works, updated accordingly based on formal correspondence
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Controlled IFC drawings being used – Checkpoint on QA
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): Internal
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T