## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 14.0 CIVIL SPECIFICATION - TRENCHING, BEDDING, AND BACKFILLING | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 14.0 CIVIL SPECIFICATION - TRENCHING, BEDDING, AND BACKFILLING
section | 14.0 CIVIL SPECIFICATION - TRENCHING, BEDDING, AND BACKFILLING
checkpoint | 14.01 - Trenching
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.2.5.1.1
label | SPECIFICATION DETAIL SUMMARY: Trench excavation to be carried out in accordance with KiwiRail Civil Engineering Standard Culverts C-ST-CD-4103 Section 7.1.2.
label | ACCEPTANCE CRITERIA: Excavation in line with KiwiRail Civil Engineering Standard Culverts C-ST-CD- 4103 Section 7.1.2..
label | TEST SPEC AND FREQUENCY: For every section of trench
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 14.02 - Unsuitable Foundation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.2.5.1.4
label | SPECIFICATION DETAIL SUMMARY: If trench bottom material isn't suitable for pipe foundation, Contractor must over- excavate upon receipt of order from the Engineer, and backfill with approved material.
label | ACCEPTANCE CRITERIA: Over excavation required if trench invert is less than the CBR values in Table 10.1 (snippet below).
label | ○ Replacement material tested for strength using Clegg Hammer or Scala and shall achieve equivalent CBR strength values given in Table 10.1.
label | – – – – – – – – – – – – – – – – – –
label | Table 10.1 Trench invert strengths
label | Trench situation ¦¦ Minimum required CBR value at trench design invert level
label | – – – – – – – – – – – – – – – – – –
label | In non-road areas ¦¦ 3.5
label | In permanent road areas with depth to trench invert less than 0.6 m ¦¦ 5
label | As in 2. but with depth to trench invert greater than 0.6 m ¦¦ 3.5
label | Beneath temporary construction haul roads ¦¦ add 3 to the above permanent road case CBR's
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: For pipe diameters < 1,000 mm: testing at 10 m maximum centres for each placed layer.
label | ○ For pipe diameters 1,000 mm to 1500 mm: testing at 5 m maximum centres for each placed layer.
label | ○ For pipe diameters CHAR(62) 1,500 mm: testing at 2.5 m centres for each placed layer.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Clegg and or Scala Test Results, Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 14.03 - Pipe Bedding & Support
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.2.5.2
label | SPECIFICATION DETAIL SUMMARY: Pipe bedding to be carried out in accordance with KiwiRail Civil Engineering Standard Culverts C-STCD-4103 Section 7.1.3.
label | ACCEPTANCE CRITERIA: Pipe bedding in line with KiwiRail Civil Engineering Standard Culverts C-STCD- 4103 Section 7.1.3
label | TEST SPEC AND FREQUENCY: For every section of pipe bedding and support
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheets, Photos, Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 14.04 - Backfilling
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.2.5.2
label | SPECIFICATION DETAIL SUMMARY: Backfilling to be carried out in accordance with KiwiRail Civil Engineering Standard Culverts C-ST-CD-4103 Section 7.1.3.
label | ACCEPTANCE CRITERIA: Backfilling in line with KiwiRail Civil Engineering Standard Culverts C-STCD- 4103 Section 7.1.3
label | TEST SPEC AND FREQUENCY: For every section pipe backfilled
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheets, Photos, Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T