## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 15.0 CIVIL SPECIFICATION - TRENCHLESS METHODS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 15.0 CIVIL SPECIFICATION - TRENCHLESS METHODS
section | 15.0 CIVIL SPECIFICATION - TRENCHLESS METHODS
checkpoint | 15.01 - Rock Armour Grading
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.3.1.1
label | SPECIFICATION DETAIL SUMMARY: Rock armour material shall be well graded as indicated on the drawings.
label | ACCEPTANCE CRITERIA: Poorly graded or gap graded armour rock shall not be permitted except as approved by the Engineer.
label | TEST SPEC AND FREQUENCY: For every section of rock armour
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Rock Specifications
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 15.02 - Rock Armour - Placement
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.4.4
label | SPECIFICATION DETAIL SUMMARY: The placement method of armour and underlayers directly on geotextile filter fabric shall be approved by the Engineer prior to placement
label | ACCEPTANCE CRITERIA: Engineer to approve methodology
label | TEST SPEC AND FREQUENCY: Prior to rock armour placement
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Method Statement, Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15.03 - Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.5.2
label | SPECIFICATION DETAIL SUMMARY: Rock materials must be placed according to the drawings' levels, dimensions, and slopes, and the surface profile must be measured using the specified tolerances:
label | ○ Subgrade levels: -0.1 m to +0.1 m
label | ○ Armour underlayer thickness (average per profile): -0.1 m to +0.2 m
label | ○ Armour rock thickness (average per profile): 0.1 m to +0.5 m
label | ACCEPTANCE CRITERIA: Tolerances are adhered to
label | TEST SPEC AND FREQUENCY: For every section of rock material placed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T